PUBLIC BOARD, 18 May 2022

TITLE: Quarterly Change & People Update

Executive Sponsor: Kirsty Shaw - Chief Operating Officer
Presenter: Amy Pritchard, Director of Transformation / Gill Nicholson, People Director
PURPOSE: FOR ASSURANCE

This paper is provided to enable the Board to fulfil their duties in relation to:
- Monitoring the progress and delivery of strategic change programmes
- Ensuring financial probity and the efficient and effective use of resources

PROPOSAL OR RECOMMENDATION

Information for Board to be aware of:
- Impact on CQC and stakeholders - the continuation of Target Operating Model and Strategy implementation
- Timeline for delivery – ongoing until FY24/25
Board are asked to note on the delivery performance.

BACKGROUND

This paper is an established component of CQC’s governance of its strategic transformation portfolio, it provides visibility of performance against delivery for the quarter ending April 2022.

KEY POINTS
Summary
Key achievements over the last quarter include:
- The announcement of the Regulatory and Operations Leadership appointments represents a significant milestone in moving towards the new organisation structure.
- In our Regulatory Model work we have developed the Single Assessment Framework and scoring approach which will now be used as we test the first phase of our new regulatory approach and transition into the new operational structures
- ​Our Transforming Data and Insight work is on track and the new Data & Insight unit has been launched.
Transformation Update
Performance Summary
Our overall portfolio performance has remained at Amber/Green, all major milestones for this first phase have been met and we have finalised our end of year Transformation spend with our agreed budget.
The latest Portfolio internal audit concerning Change Programmes Governance & Management has concluded and noted a clear improvement in the maturity of the programme governance and risk management baseline. Despite the ongoing recruitment and retention challenge, programmes remain confident in the finalisation of the objectives for the first phase of our transformation and we are now transitioning in to phase 2.
During the last period we completed a substantial cascade of communications focusing on the implementation plan for the coming year and what this means for colleagues, providers and the public.

Programme Performance
Portfolio Pillar 1: Regulatory Framework
This pillar is focused on the design of our regulatory model to guide how we develop our new regulatory services and shape what skills we need for the future.
The Programme remains on track and has now completed the next iteration of the Regulatory Model Handbook. The Closed Cultures and Directing and Controlling Care work is broadly on track to formally close as planned.
The Single Assessment Framework and scoring approach is now being used to test the first phase of our new regulatory approach.

Portfolio Pillar 2: Organisational Design and Development
This Pillar will deliver our organisational changes to ensure we have the skills and culture we need to deliver our new strategy.
Overall, the programme continues to progress in line with its schedule and has concluded all high-level design for operations, as set out in our delivery plan. The launch of a single Operations Group and Regulatory Leadership Function represents a significant milestone as we progress implementation of our new organisational structure.
Our transitional regulatory governance model has been developed with Regulatory senior leadership. This ensures that we have clear decision-making routes for our new leadership structure.
Portfolio Pillar 3: Regulatory Services
This pillar will develop and deliver new services, processes, data and technology aligned to embedding our new policy and regulatory approach as defined under pillar 1.
In our Regulatory Platform work, the focus in this period has been on the opportunities for early delivery of services with an ‘Early Adopters’ initial launch planned for July. Further launches are planned for August and September, prior to the main implementation commencing in October.
We formally launched the new Data & Insight unit 31st March and the first set of Data & Insight products have been published onto our new Enterprise Data Platform.
In our Finance Transformation work we are completing our design phase which is due to conclude by the end of June. We are working with our internal stakeholders to promote early buy-in and adoption of the new ways of working.
The final components of the Portfolio Management tool have now concluded. A Portfolio Management maturity assessment has been completed and the project is now in its closure stage as we transition this work into our regular business practice.

People Strategy Update
Capability building
As the Data and Insight Unit has now been launched, focus is on firming up individual and collective needs and the development or procurement of learning solutions to meet these needs. As reported last quarter, we also continued the focus on building capability across CQC in managing change, at all levels; adapting our approach based upon the lessons learned from the Data and Insight management of change process.

Development of learning solutions regarding the Regulatory Platform has commenced and we are confident that these solutions will be available in line with project expectation. A new learning needs analysis is underway, in relation to line management capabilities, based upon an evaluation of the existing programme and engagement with senior stakeholders.

Culture
The cultural principles and approach to driving cultural change was supported by Audit and Corporate Governance Committee (ACGC). Senior Leaders have started using the principles to consider how they drive cultural change through their leadership.
An engagement plan is being developed to ensure cultural aims are embedded across transformation and organisational messaging, the stories we share and how we connect and engage people in CQC’s work. Work is also progressing on aligning the cultural work with the development of CQC’s People Plan, learning priorities and leadership team development.

Recommendation
None
Discussion and implications
None
Conclusion and Next Steps
Key priorities throughout April include:
- Commence testing for all phase 1 outputs and complete assurance of our phase 1 objectives
- Launch internal communications campaign to help colleagues understand what the changes could mean for them

Appendices
None
Those who contributed to this paper
- Nina Snell – Head of Transformation Delivery
- Gill Nicholson – People Director

 CONTRIBUTIONS

The following groups/people have been involved in forming this paper:

Groups/people	Involvement?	Feedback
HR	Yes	People update comes directly from HR colleagues.
Finance	Not applicable
DHSC	Not applicable
Executive Team	Not applicable
Board Committee	Not applicable
Executive Committee	Not applicable
Trade Unions	Not applicable
Staff Networks	Not applicable
Other – please specify	Not applicable