PUBLIC BOARD 20 July 2022

TITLE: Annual Board report on delivery of our Equality Objectives

Executive Sponsor: Ian Trenholm
Presenter: Lucy Wilkinson, Head of equality, health inequalities and human rights

PURPOSE: FOR ASSURANCE

This paper is provided to enable the Board to fulfil their duties in relation to:
- Holding the Executive to account for performance and the proper running of the organisation
- Monitoring the progress and delivery of strategic change programmes

PROPOSAL OR RECOMMENDATION

- Approve this annual report on delivery of our Equality Objectives.
- Agree to receive a further report in February 2023, to agree delivery priorities for 2023/24

BACKGROUND

We have a statutory duty to publish equality objectives at least every four years. We published equality objectives in July 2021, following Board approval. The Board also agreed to receive an annual report on delivery of the objectives and the Executive Team receive a six-monthly update. This is the first annual report. The regulatory equality objectives are a major delivery vehicle for the core aim in our strategy of tackling inequalities and will be delivered over four years. Our workforce-focussed equality objective is delivering our Diversity and Inclusion strategy and is a core pillar of our People Plan.

Our five Equality Objectives, agreed by Board in July 2021 are published in full on our website. They are:

1. Amplifying the voices of people more likely to have a poorer experience of care or difficulty accessing care
2. Using data to understand and respond to equality risks
3. Working with others to improve equality of access, experience and outcomes
4. Using our independent voice to reduce inequalities
5. Our inclusive future: delivering on our diversity and inclusion strategy

Progress on delivery in year 1:
- This year has been foundational. To enable strong longer-term delivery, we have integrated the equality objectives into Independent Voice priorities, research programme priorities, data strategy, People Plan and into the draft Public Engagement Strategy.
- Senior leadership support is vital. In May, we held a workshop for senior leaders where attendees made personal commitments to support the delivery of the Equality Objectives. Oversight of the Equality Objectives has also been developed over the year, with 6-weekly meetings for senior responsible officers and development of the quarterly Equality, Health Inequalities and Human Rights Oversight group.
- In developing our new Single Assessment Framework, we have included robust Quality Statements to cover equity in access, experience and outcomes from care and workforce equality. The new regulatory model, including a focus on required evidence will form a foundation for us in tackling inequalities and contribute to effective delivery of the equality objectives.
- Our regulation of Integrated Care Systems will bring opportunities to influence equality in access to care and in how local areas are tackling wider determinants of inequalities in outcomes. The development of local multidisciplinary operational teams will also bring opportunities.

Of the 34 deliverables across all 5 objectives, 21 are rated green, 8 amber and none are rated red. Five have not commenced yet (see appendix). There have been some notable early successes in delivery of specific objectives:

  - Equality Objective 1 - Amplifying voices:
  - Launch of our British Sign Language service for our contact centre.
  - Development of trusted intermediary work with voluntary sector partners to hear more from specific groups of people. more likely to experience poor care or difficulty accessing care.
  - Agreeing a Quality Statement that providers need to understand and respond to the experiences of people facing inequalities. This will be assessed for all providers and for ICSs.

  - Equality Objective 2 – Data on equality risks:
  - Exploratory work on ethnicity coding in mental health data sets and analysing patient safety reporting by equality characteristics.
  - Continuing to build best practice in addressing inequalities through the NHS Patient Survey programme which we manage– across survey methodology and analysis and widening participation and impact of findings.
  - Launch of Workforce Equality Risk and Oversight Group including escalation of operational risks where we have concerns about workforce equality in providers.
  - Building a programme of work to deliver commitments in our GP Inequalities report.

  - Equality Objective 3 – Working with others:
  - Hosting an agenda item at the regular Chief Executives of Arm’s Length Bodies group, to discuss joint work to tackle inequalities – including a survey – work on priorities will be taken forward jointly.
  - Initiating an Improvement Coalition for the NHS Accessible Information Standard, which is now being hosted by NHS England.

  - Equality Objective 4 – Using our independent voice
  - A focus on inequalities in State of Care.
  - Publication of the Maternity safety, equality and engagement report.
  - Publication of GP Inequalities report. This focussed on fairness in CQC regulation but including the wider context of the challenges faced by many ethnic minority-led GP practices working in areas of high deprivation. This led to a successful bid to the government’s Regulator Pioneers Fund, to develop how we can give regulatory recognition to NHS GP providers in their work to reduce health inequalities and share innovative practice in this area. The report on this project was published in May[1].
    [1] Regulators' Pioneer Fund project: Regulatory recognition and sharing of innovative practice by NHS GP providers to reduce health inequalities - Care Quality Commission (cqc.org.uk)
  - Publication of Insight reports on tackling inequalities when restoring elective waiting lists and ethnicity recording in mental health.

Equality Objective 5: Our Inclusive future
  - Independent Panel Members are now in place for recruitment to all posts at Grade A and above.
  - Introduction of 12 Diversity and Inclusion Coordinators across CQC directorates (averaging 2 Coordinators per directorate) – a voluntary role to lead local actions and promote good practice.
  - “Carers Confident” level 1 achieved.
  - Stonewall Silver Employer award in recognition of our support of LGBT+ colleagues.
  - Anti-bias and fairness mandatory learning launched – with practical learning about reducing bias in decision-making.

Success measures:

Success measures were published for each Equality Objective (see appendix). It is too early to measure many of the indicators (13 out of 30). Of those that are measurable, 8 are green, 7 amber and 2 red. The high level of amber reflects the early stage we are at with delivery. Some key findings are:
- 70% of people more likely to have poor care who have shared information with us said it was easy to do so, compared to 93% of other people. This shows the importance of delivering equality objective 1.
- There is evidence from services that our work encourages them to reduce inequalities (88% of services agreed with this in our annual survey, completed by 17733 providers). However, they are less convinced that we currently have sufficient focus on tackling inequalities and feel that more can be done in calling out unwarranted variation and inequalities in health and care.
- People who have chosen a care home, carers, those aged 55+ were more likely to have a negative perception of CQC as a regulator (from our Public Awareness survey, based on 589 respondents aware of CQC). We will work to understand the concerns of these groups through our planned engagement work.

Managing delivery risks:

There have been three main risks in the year. All these risks have management and mitigation plans in place.

Capacity to drive Equality Objectives delivery: The Equality, Health Inequalities and Human Rights Team has been strengthened to drive delivery of our core ambition to tackle inequalities. Capacity is other parts of CQC to assist delivery, for example Engagement, remains a risk.

Operational capacity, capability and confidence: Work on previous equality objectives shows that there is variation in the confidence of CQC colleagues in making assessments on equality-related aspects of our regulation. The assessment of Integrated Care Systems (ICSs) and development of multidisciplinary teams brings new opportunities to do this more effectively. We are developing plans to support local teams in their role in tackling inequalities. This includes capacity and support for local outreach to hear from people at greatest risk of poor care. The new regulatory model, based on required evidence, should also drive higher consistency of assessment.

Technical data risks: There are some technical issues in collecting equality monitoring data from both people who use services, to assess inequalities in care, and providers, to assess fairness in regulation. There will also be some challenges in analysing text-based data (e.g., people’s experiences) for inequalities implications. Also, many data sets that we use from other sources have weak equality data. We are tackling this on a case-by-case basis through our “equality by design” approach to data and intelligence.

Setting priorities for Year 2:
- The Executive Team discussion in February 2022 agreed delivery priorities for 2022/23 to align with the CQC Business Planning year. These are shown in the Appendix.
- It is proposed that in future these are also agreed by the Board. So, the next report to Board will be February 2023, to enable Board to discuss and agree delivery annual priorities, aligned with Business Planning cycles.

CONTRIBUTIONS
 The following groups/people have been involved in forming this paper:
Groups/people	Feedback
HR	Organisational development colleagues have contributed content for equality objective 5
Finance	N/A
DHSC	N/A
Executive Team	This paper has been agreed by Executive Team on 28 June 2022
Board Committee
Trade Unions
Staff Networks	Staff networks are represented on Equality, health inequalities and human rights oversight group
Other – please specify	Equality, health inequalities and human rights oversight group – Chaired by Joyce Frederick, Director of Policy and Strategy senior leaders responsible for Equality Objectives delivery (from Regulatory Leadership and Operations) plus representatives from other directorates

NEXT STEPS
- Promotion of this Board report to CQC colleagues, with messaging about how they can contribute to delivery of the objectives: Ian Trenholm/ Lucy Wilkinson (by September 2022).
- Continued delivery of 2022-23 deliverables, subject to any changes agreed by the Board: Lucy Wilkinson (March 2023)
- Continue work on mitigating risks to delivery: Lucy Wilkinson (March 2023).
- Board paper on 2023-24 deliverables to progress the objectives: Joyce Frederick/ Lucy Wilkinson (February 2023).

APPENDICES

Report on progress against agreed deliverables for 2022- 2023 and success measures for Equality Objectives FOR INFORMATION.

Author: Lucy Wilkinson, Head of equality, health inequalities and human rights