PUBLIC BOARD, 21 September 2022

TITLE: Quarterly Change & People Update

Executive Sponsor: Kate Terroni: Chief Inspector of Adult Social Care, Integrated care and Interim Chief Operating Officer
Presenter: Amy Pritchard: Director of Transformation / Gill Nicholson, People Director
PURPOSE: FOR ASSURANCE

This paper is provided to enable the Board to fulfil their duties in relation to:
- Monitoring the progress and delivery of strategic change programmes
- Ensuring financial probity and the efficient and effective use of resources

PROPOSAL OR RECOMMENDATION

Information for Board to be aware of:
- Impact on CQC and stakeholders - the continuation of Target Operating Model and Strategy implementation
- Timeline for delivery – ongoing until FY24/25
Board are asked to note on the delivery performance.

BACKGROUND

This paper is an established component of CQC’s governance of its strategic transformation portfolio, it provides visibility of performance against delivery for the quarter ending July 2022.

KEY POINTS
Key achievements over the last quarter include:
- We successfully delivered Phase 1 of our transformation programme which included;
  - The design of a new Single Assessment Framework
  - The launch of a new Data and Insight Unit
  - The design and implementation of regulatory organisational structures and roles
- Phase 2 is about implementing the Single Assessment Framework in live operations through the provision of new digital services as well as concluding the people and cultural change necessary to support new ways of working. We hit our first milestone on this, launching digital services that allow Home Care providers to submit a Registration and Hospices to submit SN16 Notifications.

Transformation Update
Performance Summary
Throughout the first quarter of this financial year, our overall portfolio performance remained at Amber/Green with all major deliverables met as outlined above. We are currently reviewing our roll-out approach for Phase 2 of the transformation to ensure we do it safely, have allowed adequate time to accommodate some of the complexity in the technology build, as well as being sensitive to the change load on the organisation. We expect to finalise the plan at the end of September.
Programme Performance
Portfolio Pillar 1: Regulatory Framework
This pillar is focused on the design of our new regulatory model, it includes our Single Assessment Framework as well as our approach to Assessing Integrated Care Systems and performing Local Authority Assurance. This work informs the people, process, digital and data requirements that are delivered by other programmes in the portfolio.
Further to completing the design of the Single Assessment Framework, ‘Test & Learn’ exercises have now been conducted on the approach and methodology for Local Authority Assurance and Integrated Care Systems, the next stage is to begin thinking about the organisational structures needed to support this.
Portfolio Pillar 2: Organisational Design and Development
This Pillar focuses on delivering the people changes needed to support our new regulatory model, their role is to ensure that we have the right skills and culture in place to deliver on our new approach.
To date, the team have completed a full re-design of all regulatory operations leading to the creation of a new Regulatory Leadership function, as well as the introduction of a centralised Hub supported by Networks of Multi-Disciplinary Teams (MDTs). To note; for future reporting, following feedback from colleagues, MDTs will be known as Integrated Assessment and Inspection Teams We expect this design will provide our people with greater agility and flexibility to respond to risk, as well as strengthening our impact in driving improvement at both a local and national level. Implementation of this design will continue throughout the year, aligned to the roll-out of new digital services.
Portfolio Pillar 3: Regulatory Services
This pillar focuses on the delivery of new digital and data services that are key to:
- Embedding our regulatory framework in daily practice
- Unlocking our ability to become insight driven, dynamic and responsive to regulatory risk
- Creating seamless, more efficient and effective interactions for all people who interface with us as an organisation (internally and externally)
To date, we have launched a new Data and Insight unit, along with a new data platform. Over time, the insights and capability provided through this unit will allow us to become much more focussed on where we hone our regulatory effort. We have also begun the roll-out of new digital services for Notifications and Registration at a micro scale with a small group of providers. The plan is to gradually build out these services, offering them to larger cohorts of Providers over a given timeframe – we refer to this phase as ‘Early Adopters’. Once we are satisfied that services meet the needs of our users, and can accommodate all types of complexity, we will look to implement them at scale.
People Strategy Update
Capability building
We continue to deliver the priority areas of technical development to enable the Data and Insight Unit to support and maintain the Enterprise Data Platform. The Enterprise Data and Reporting team is being upskilled in the support and maintenance aspects of the platform, and colleagues have been supported to refresh their existing technical skills and knowledge in relation to the cloud technology used. The Data Quality team has also received interventions to upskill in the use of the data quality tools. Across the Data and Insight Unit we continue to engage and advise colleagues in taking ownership of their learning, through informal development initiatives at team and function level and formally through funded routes where a need is identified. The unit is starting to embed new ways of working; a programme of Senior Leadership Team development is in place, we have launched local induction, and culture workshops will be rolled out through Q3.
In readiness for the next phase of change in Operations Group, a detailed learning needs analysis and creation of role-based learning paths is underway. Colleagues will be supported in the same way as the Data and Insight Unit with available learning identified for colleagues in advance of moving into new roles and with more detailed learning needs to follow on specific areas, based on priority need. We will commence with the induction of the Deputy Directors in Operations Group in October and will be rolling out a two-day management development programme through Q3 and Q4 for those with line management responsibilities.
We are continuing to develop the learning modules to support colleagues in the use of the new Regulatory Platform, the new Single Assessment Framework and associated policies, processes and systems aligned to current project timescales.
Culture
The cultural principles continue to be woven into work-in-progress, including CQC’s internal engagement strategy, people/pulse survey and planning for the next all colleagues’ conference.  Work is underway to map out the next phase of the Senior Leadership Teams’ development journey and the use of Microsoft Viva Insights data to create habits for working well in a hybrid environment.
The Operations Senior Leadership Team has started their team culture journey to lead the function and enable and support the new Network Deputy Directors and teams to create a high performing delivery function. A culture package and toolkit has been developed, including an interactive tool based on our culture principles. A series of master classes will be rolled out to leaders in Operations Group to enhance line management capability and confidence in embedding new ways of working and brining to life our cultural principles.

Recommendation
None

Discussion and implications
None

Conclusion and Next Steps
Key priorities throughout April include:
Conclude the roll-out approach for Phase 2 of the Transformation portfolio

Appendices
None

Those who contributed to this paper
- Nina Snell – Head of Transformation Delivery
- Gill Nicholson – People Director

 CONTRIBUTIONS

The following groups/people have been involved in forming this paper:

Groups/people	Involvement?	Feedback
HR	Yes	People update comes directly from HR colleagues.
Finance	Not applicable
DHSC	Not applicable
Executive Team	Not applicable
Board Committee	Not applicable
Executive Committee	Not applicable
Trade Unions	Not applicable
Staff Networks	Not applicable
Other – please specify	Not applicable