No	Ref	Subject	Action Required	Owner	Date Raised	Date Due	Progress/ Comment	Date / Completed	Status
1	CM/05/22/05	Corporate Performance Report	CU to improve the clarity of the business overview RAG ratings and include data on secondments by ethnicity and disability in future performance reports.	Chris Usher	18/05/22	14/12/22	RAG status revised to improve clarity. Work ongoing with People directorate to ensure people data is available in an accessible format. The focus has been on core people data but secondment information will be included in the next quarterly update.

Status key:
Red-overdue
Green- on track
Blue-complete or propose to close.