No	Ref	Subject	Action Required	Owner	Date Raised	Date Due	Progress/ Comment	Date / Completed	Status
1	CM/05/22/05	Corporate Performance Report	CU to improve the clarity of the business overview RAG ratings and include data on secondments by ethnicity and disability in future performance reports.	Chris Usher	18/05/22	14/12/22	RAG status revised to improve clarity. Secondment information will be included in the next quarterly update to December Board.
2	CM/09/22/03	Corporate Performance Report	Future performance updates should separate out activities that we provide on behalf of DHSC	Chris Usher	21/09/22	14/12/22	Amendment to be included in December Board meeting pack.

Status key:
Red - overdue
Green - on track
Blue - complete or propose to close.