INFORMATION APPENDIX: CURRENT STATUS OF EQUALITY OBJECTIVE DELIVERABLES AND MEASURES OF SUCCESS
Summary of deliverables for 2022/23
		July 2022	January 2023
Red	Successful delivery appears to be unachievable.	0	0
Amber Red	Successful delivery in doubt and urgent action required to resolve risks/issues and to establish if delivery still feasible	0	2
Amber and Amber *	Successful delivery feasible, however management attention required to resolve significant issues/ / Amber * denotes transformation delays issues	6	8
Amber Green		0	11
Green	On track for time, cost and quality	24	15
Not started yet		6	0
Total		36	36

Summary of Measures of success
		July 2022	January 2023
Red	If a sentiment indicator: 50% or below agreement= red, or an indicator is moving in an adverse direction	3	2
Amber Red	If a sentiment indicator: 50% or below agreement=, but we need more data for full coverage = amber/ red,	0	1
Amber	If a sentiment indicator: 51-75% agreement =Amber	7	9
Amber Green	If a sentiment indicator: 51-75% agreement, but we need more data for full coverage =Amber green or an indicator is moving in the right direction but we have not met the target yet	0	6
Green	If a sentiment indicator Above 75%=green	11	6
Too early to assess		8	5
Total		29	29

Table 1: Equality Objectives: 2022/23 deliverables
Amplifying the voices of people more likely to have a poorer experience of care or difficulty accessing care
Activity	Deliverables 2022/23	RAG rating July 2022	RAG rating January / 2023
Increasing range of feedback we receive from people more likely to have poor care or have difficulty accessing care	Continue developing consistent equality monitoring across information collection from people and how we can disaggregate this	Amber	Green
	Further develop targeted campaigns/ activities to increase feedback from specific groups (e.g. Because we all care)	Green	Green
	Consider additional tools needed to gather feedback from some groups	Green	Amber*
	Develop approach and expectations for local teams in proactive outreach/ gathering of feedback from specific groups of people	Green	Green
Ensuring we use feedback well and countering epistemic injustice	Test how much feedback from people in different equality groups has an impact on our regulatory action through Single Assessment Framework piloting work	Not started	Amber *
Encouraging providers and local systems to respond to people more likely to have poor care	Test through Single Assessment Framework piloting work / Consider communications to raise expectations	Green	Amber *

Using data to understand and respond to equality risks
Activity	Deliverables 2022/23	RAG rating July 2022	RAG rating January / 2023
Strategic development	Evaluate “equity by design” approach	Not started	Green
Testing and building data requirements	Build equality risks data required evidence for providers, ICSs and LAA for single assessment framework and test as part of regulatory model development	Green	Amber*
	Make use of the data we have now before the new regulatory model comes in including how we report on it consistently.	Green	Amber*
Hearing from frontline staff in providers about equality	Deliver revised approach to WRES and expand to other workforce equality issues in NHS Trusts and to other sectors	Green	Amber Green[1]
Using evidence to ensure CQC decision making is fair	Integrate equality monitoring into IOM2	Green	Amber*
	Deliver recommendations of GP Inequalities report	Green	Amber Green[2]
Working with others to improve equality of access, experience and outcomes
National joint working	Look at priorities for developing other improvement coalitions on equality/ health inequalities-based aligning with Strategy theme on accelerating improvement	Green	Green
	Actions arising from Chief Execs of Arm’s Length Bodies meeting on tackling inequalities	Amber	Green
Building improving equality/ tackling inequalities into joint work through Memoranda of Understanding	Deliver small action plan – Align with wider work on Memoranda of Understanding	Green	Amber[3]
Build our own capacity to escalate issues to others and respond to recommendations from others	Embed recommendations into relevant CQC Research and Development priorities. Test in regulatory model pilots – including different approaches. Align with MOU development work ( we will have a focus on this in Q4)	Amber	Amber Red[4]
Using our independent voice to reduce inequalities
Activity	Deliverables 2022/23	RAG rating July 2022	RAG rating January / 2023
Strategic development	Delivery of tackling inequalities priorities in Independent Voice plan	Green	Amber [5]
	Delivery of tackling inequalities priorities in Research & Development plan	Amber	Green
Tackling inequalities in local areas	Develop communication about role of ICSs in reducing inequalities in ICS nationally, including potential joint work with EHRC and NHSEI	Amber	Green
National reporting	Develop inequalities theme in State of Care	Green	Amber Green[6]
Using findings to improve how we address inequalities in our own regulation	Develop narratives about addressing inequalities within strategy themes on safety and improvement	Green	Green
[1] Delay in data sharing agreement but now resolved and is a priority
[2] Transformation delays but we were able to bring some of this work into the current model
[3] Wider work on MOU’s delayed which may have an impact on delivery
[4] Need to rescope solution. Will be a priority in quarter 4
[5] Prioritisation mechanism is not settled yet
[6] Need attention for State of Care 22/23 regarding building our own data

Our inclusive future: delivering on our diversity and inclusion strategy
Activity	Deliverables 2022/23	RAG rating July 2022	RAG rating January / 2023
Inclusive Leadership and Accountability	Introduce the second cohort of Reverse Mentoring targeted at our Senior Leaders and Black and minority ethnic and/or disabled colleagues.	Amber	Amber Green
	Develop and introduce the “Inclusive Leadership Pathway” (ILP). The ILP has been designed for disabled and/or Black and Minority Ethnic colleagues. It includes stretch projects, funded learning, and coaches.	Green	Green
	Procure, design and develop an inclusive Leadership Programme. Everybody will be exemplars of our behavioural framework, our cultural principles and our values. Diversity and inclusive leadership will be a golden thread running through the programme.	Green	Amber Green
Inclusive Policies and Practices	QI project underway examining our recruitment process and areas which may need improving. Under the project scope includes piloting Independent Panel Members (IPMs) in the shortlisting process of all recruitment panels at Grade A and above. As well as evaluating the success of IPMs.	Not started – Starting from Sept 22	Green
	Review and update comms and our offer to disabled candidates to discuss any required reasonable adjustments for all parts of the recruitment process.	Green	Amber Green
	Begun a QI project to improve the experience of disabled colleagues acquiring reasonable adjustments.	Green	Green
	Ensure our internal and external recruitment campaigns and job adverts are inclusive and demonstrate our commitment to improving the representation of disabled colleagues at senior grades. Review how effective diversity job websites have been to attract diverse talent at our Grade A and Executive advertised roles.	Not started – Starting from Sept 22	Amber Green
	Refresh and update Academy’s Mentoring program and promote places for Black and minority ethnic and/or colleagues with disabilities.	Green	Green

Activity	Deliverables 2022/23	RAG rating July 2022	RAG rating January / 2023
Inclusive Cultures	Achieve Disability Confident Level 2 Q2 2022 (completed) and work towards any actions necessary to achieve level 3 by March 2023	Green	Amber Green
	Work towards any actions necessary to achieve Carer Confident employer level 1 by March 2022 and level 2 by March 2023.	Green	Amber Green
	Develop a rhythm of showcasing and reporting on D&I data more frequently throughout the year to encourage local action from colleagues across the organisation.	Not started –Starting from Sept 22	Amber Green
	Build and implement the “Living Library” and Academy’s “Confidence with Difference” learning as tools to raise awareness of different experiences between colleagues in the organisation.	Not started – Starting from Sept 22	Amber Green
	Develop a “Share and Declare” PowerBI dashboard and campaign targeting different directorates at a time, in order to encourage colleagues to self-report so we can highlight the importance of having accurate ESR data.	Green	Green
Inclusive Engagement	Introduce an accessibility working group to identify and remove accessibility barriers within CQC.	Green	Green
	Support the development of working relationships between the new CSO roles and Network Chairs, D&I Coordinators and Wellbeing Leads, to align and support Equality Networks and directorates diversity and inclusion activity.	Work underway to implement new roles	Amber red

Table 2: Equality Objectives: Measures of success November 2022
- Measures of success for each equality objective were published in July 2021, within our Equality Objectives. Many of the measures were designed to align with strategy indicators and supplementary data points to make collection and analysis more streamlined.
- The 2022/23 Annual Provider, Stakeholder and Awareness surveys have not yet been released. The results of the Annual Awareness Survey will be available soon as it is in its final stage. This year’s Annual Provider Survey closed recently therefore findings will be available between January and February. The Stakeholder Survey is due to be run in January with findings to follow in approximately April. This means that many of the measures are using the same figures as the July Board report.
- All figures given are for 2022/23 unless otherwise stated.
- Ranges applied for RAG rating sentiment indicators: 50% or below agreement= red, 51-75% agreement =Amber, Above 75%=green
Please note the following caveats (for more information please see Table 3 at the end of the document):
- Not all data is yet available to assess the equality objectives, with more objective data being absent. This means there is an emphasis on the views of people, services and stakeholders.
- As we have undertaken extensive engagement to articulate our strategic intent providers and stakeholders may be feeding back based on what we plan to do, rather than actual delivery. We may therefore see results temporarily decline from high baselines as we begin to implement our strategy but before it is fully realised.
- Some data is based on low sample sizes this year, and others are unweighted (i.e. the stakeholder survey). They may, therefore, not be fully reliable and shifts in results next year for these indicators will therefore need to be treated with caution.
# Overarching measures of meeting the needs of people more likely to have poor care
These measures are taken from our Annual Awareness survey from 2021. They are not included in measures of success for specific equality objectives but are relevant across all objectives. As highlighted, we have no updated measures to share for 2022/23 as yet
- 63% of the public (n=1000) and 63% of those more likely to have poor care (n=326) agreed CQC does what they want as a regulator of health and social care. (8% of the public disagreed). 71% of the public (that were aware of CQC n=569) and 69% of those more likely to have poor care agreed CQC does what they want as a regulator of health and social care.
- Those that have chosen a care home, carers and those aged 55+ were more likely to have a negative perception of CQC. We will do more work to understand the concerns of these groups. Following Board feedback, we are undertaking further work to understand the reasons for this.
Table 2: Measures of success
Equality Objective	Reference	Measures	Performance data	RAG rating July 22	RAG rating January 23
Amplifying the voices of people more likely to have a poorer experience of care or have difficulty accessing care	1.1	Feedback from people (including those more likely to have poor care) that we use in our regulation	12% of all inspections were triggered by information of concern, including whistle blowing, complaints and concerns shared by people, care staff and other stakeholders. Of those inspections that have a recorded risk trigger (not regulatory history), 51% are triggered by information of concern.[7] Note. Not currently measuring whether this information is from people more likely to have poor care. / For Q2 of 2022 (July-September), 38%[8] of people involved in different types of engagement activity to develop our approach were people more likely to have poor experience of care* / *people may have been counted more than once due to counting by characteristic rather than by people / Note: This is not directly comparable with the previous figure of 48-81% as this is too broad and was based on a range of different activities . Going forward, figures will be directly comparable with the 38% recorded	Amber	Amber / →
	1.2	People, including those more likely to have poor care, say it is easy to share information with us.	In 2021, 84% of the public who have shared information with CQC say it was easy to do this (n=67). For those more likely to have poor care (n=21), 70% agreed it was an easy process to share compared to 93% of those less likely to have poor care (n=43)[9]. / NB No new data available since last report	Amber	Amber / (No new data since July) / →
	1.3	Assessment and review outputs include the views of people – including those more likely to have poor care	Not currently measured – however of those who have used CQC information to understand standards of care they expect to receive, 91% of those more likely to have poor care agreed (n=33) that CQC's information about the standards of care they can expect focuses on what matters to them and their loved ones. This is higher than the 85% of those less likely to have poor care (n=62) though based on small numbers[10]. / NB No new data available since last report	Too early	Too early / (No new data since July) / →
[7] CRM data
[8] Public Engagement Insight Log
[9] Annual Awareness Survey 2022
[10] Annual Awareness Survey 2022

Equality Objective	Reference	Measures	Performance data	RAG rating July 22	RAG rating January 23
1. continued	1.4	Operational colleagues say we give appropriate weight to people’s experiences of care	We are not collecting this yet but will ask this on our next survey / NB No new data available since last report	Too early	Too early / (No new data since July) / →
Using data to understand and respond to equality risks	2.1	Data items in risk models relating to equality risks	Risk models for our new approach are still being finalised. Data and Insight have, however, confirmed these are being reviewed and updated and a data analysis for equality data items is underway. Commitments have also been made to look at potential impacts of risk stratification on GP practices under new regulatory model. / 13/ 34 quality statements in our new regulatory model are directly related to equality risks, compared to 8/27 Key lines of enquiry for health services and 10/21 key lines of enquiry for adult social care in our existing model[11]. Development of our new approach based on “required evidence” for each quality statement is also likely to increase data items related to equality risks.	Too early	Amber / →
	2.2	Data on equality risks that triggers regulatory action	We are not measuring this yet. / However Quality statements on equity in experience, outcomes and access are core to our new regulatory model and D&I teams have begun work to understand how we can use frameworks such as the Core 20 plus 5 to support our assessment of quality (for example in ICS assessment).	Too early	Too early / →
	2.3	Use of information on equality risks in the reports we publish about our assessments	We are not measuring this yet. / However Quality statements on equity in experience, outcomes and access are core to our new regulatory model and D&I teams have begun work to understand how we can use frameworks such as the Core 20 plus 5 to support our assessment of quality (for example in ICS assessment).	Too early	Too early / →
[11] Desktop comparison of published assessment frameworks

Equality Objective	Reference	Measures	Performance data	RAG rating July 22	RAG rating January 23
2 continued	2.4	Services, local stakeholders and operational colleagues who say we maintain an up-to-date picture of quality of services, and in local systems, through a range of information	45% of local stakeholder survey respondents (n=159) agree with this (7% disagreed, 23% neither agreed nor disagreed and 25% did not know)[12] [This is an aggregation of the figures below] / We asked local stakeholders whether CQC maintains an up to date picture of quality using a range of information for the following sectors; / Adult Social Care (n=53) 68% agreed / Primary Medical Services (n=53) 32% agreed / Acute Services (n=53) 36% agreed / 82% of services (n=17,768) say CQC maintains an up to date understanding of quality at their service using a range of information (4% disagreed)[13] / Not yet measured for operational colleagues. / NB No new data available since last report.	Red	Red (local stakeholders) / too early (other groups) / (No new data since July) / →
Working with others to improve equality of access, experience and outcomes	3.1	Local stakeholders say our work has sufficient focus on reducing inequalities in access, experience and outcomes for people using services	78% of services (n=17769) agree with this (17% of services neither agreed nor disagreed[14]). / Information not collected yet for local stakeholders. / NB No new data available since last report.	Green (services)/ Too early (other groups)	Green (services)/ Too early (other groups) / (No new data since July) / →
[12] Annual stakeholder survey
[13] Annual provider survey Nov-Dec 2021
[14] Annual provider survey Nov-Dec 2021

Equality Objective		Reference	Measures	Performance data	RAG rating July 22	RAG rating January 23
3 continued		3.2	Volume of feedback about people's experiences of care from our strategic partners and stakeholders that we can act on	We are not measuring this yet. / Note: this measure may need to be removed as it may not be possible to quantify this.	Too early	Too early / →
		3.3	The number of people, services and local stakeholders who say we act quickly where services fail to improve safety	54% of the public that are aware of CQC [15] say we act quickly where services fail improve safety, up from 52% in 2021. In 202, 72% of services [16](n=17,723) and 66% of local stakeholder survey respondents (n=53)[17] say we act quickly where services fail to improve safety (3% of services and 19% of local stakeholders disagreed). Of the public, those that have chosen a care home, those aged 55+ were more likely to have a negative perception. / NB No new data available since yet for services and stakeholders.	Amber	Amber / →
		3.4	Strategic partners and other stakeholders say they have taken action to address safety concerns following information we have shared with them from our regulatory activities.	74% of our strategic partners and other stakeholder survey respondents[18] (n=125) say this / NB No new data available since last report	Amber	Amber / (No new data since July) / →
	3.5		Our commitments with other organisations to tackle inequalities in access, experience and outcomes as measured through revised memoranda of understanding	Only one Memorandum of understanding/ Joint working agreements has been updated and published since the Equality Objectives came into place. This refers to joint working on equality issues. The Equality, health inequalities and human rights team are working closely with EHRC to refresh their MOU action plan and information sharing approach. xiii.	Green	Amber[19] / ↓
	3.6		Evidence of our response to recommendations made by others concerning inequalities in access, experience and outcomes.	A process of setting up a system to track recommendations to CQC needs to be established, there is a project initiated but it is in very early stages and requiring additional resourcing. This is a priority for quarter 4.	Too early	Amber Red [20] / ↓
Equality Objective	Reference		Measures	Performance data	RAG rating July 22	RAG rating January 23
Using our independent voice to reduce inequalities	4.1		Services and local stakeholders that say our work has encouraged them to reduce inequalities in access, people feeling safe, care (and treatment) meeting people's needs, overall experience and satisfaction, and health and care outcomes	88% of services (n=17733) say our work has encouraged them to reduce inequalities in access, experience and outcomes for people who use, or need to use, their services[21] (9% of services neither agreed nor disagreed). This question will also be asked of local stakeholders, but this information is not collected yet. / NB No new data available since last report	Green (services)/ too early (other groups)	Green (services)/ too early (other groups) / no new data since July) / →
	4.2		Number of services, local stakeholders and our operational colleagues who say our work has sufficient focus on reducing inequalities	78% of services (n=17769) say our work has sufficient focus on reducing inequalities in access, experiences and outcomes for people using services (17% of services neither agreed nor disagreed)[22]. This question will also be asked of local stakeholders and our operational colleagues / NB No new data available since last report	Green (services)/ too early (other groups)	Green (services)/ too early (other groups) / no new data since July) / →
	4.3		The amount of content in our national reports about addressing inequalities in access, experience and outcome from using care services.	In the second year of the Equality Objectives to date (from 1st April 2022), we have published 9 national reports, 4 had a main focus on inequalities and a further 2 had some content on inequalities[23]. / In addition national reports on Safehouses and Oral health are due to publish in the new year. Both have an inequalities theme. / In comparison, from 1st August 2021 – July 2022, we published 10 national reports, 5 had a main focus on inequalities and a further 3 had some content on inequalities.	Green	Green / →
[15] Annual Awareness Survey: Dec 2021-Jan 2022
[16] Annual provider survey Nov-Dec 2021
[17] Annual stakeholder survey
[18] Annual stakeholder survey
[19] Expectation that at this point more should have been achieved
[20] Need to rescope solution. Will be a priority in quarter 4
[21] Annual provider survey Nov-Dec 2021
[22] Annual provider survey Nov-Dec 2021
[23] Desktop review of publications on CQC website

Equality Objective	Reference		Measures	Performance data		RAG rating July 22	RAG rating January 23
	4.4		Evidence that learning from our independent voice work develops our own approaches to regulating to reduce inequalities, for example through changing our methods	Reports which have influenced our regulatory approach to reducing inequalities include: / Out of sight Report / Safety equity and engagement maternity services / Regulators' Pioneer Fund project: Regulatory recognition and sharing of innovative practice by NHS GP providers to reduce health inequalities / State of Care 2021/22; / Monitoring the Mental Health Act in 2021/22; / Who I am matters; / 4,000 voices.		Too early	Green ↑
5. Our inclusive future: delivering on our diversity and inclusion strategy for our workforce		5.1	By March 2025 we will have increased representation of colleagues from Black and minority ethnic groups/ communities at all levels of CQC to at least match the economically active population levels and increase the proportion of colleagues from Black and minority ethnic groups/ communities progressing from application to shortlisting to offer, for all internal and external recruitment.		Representation / The proportion of Ethnic Minority people in the economically active population is 13.32%. (Office for National Statistics, 2021 January-March data). / In March 2021, the total headcount of CQC staff members was 3173. / 13.8% (438) of total staff were from an Ethnic Minority group, / 2448 were White staff and 287 did not state their ethnicity. / Progressing from shortlisting to appointment / WRES 2021 data shows Ethnic Minority staff being appointed from shortlisting- compared to White staff-is 1.432. / A score between the range of “0.80 -1.25” is considered “non-adverse”. / *Data taken from Electronic Staff Record 31st March 2021.	Amber	Amber / →
Equality Objective		Reference	Measures		Performance data	RAG rating July 22	RAG rating January 23
5 continued		5.2	By March 2022, colleagues from Black and minority ethnic groups/ communities will experience equal opportunities for career progression, promotion and development; as measured by internal recruitment outcomes, access to funded learning opportunities and survey data.		Ethnic Minority staff are more likely to access the Individual Learning Request (ILR) process than White staff (the figure is 0.667). / March 2021 People Survey: / 38.2% of Ethnic Minority respondents (96 respondents out of 251 Ethnic Minority respondents) and, / 51.7% White respondents (968 respondents out of 1872 White respondents) reported they believe that the CQC provides equal opportunities for career progression or promotion.	Amber	Amber Green / ↑
		5.3	Year-on-year reduction in the proportion of colleagues from Black and minority ethnic groups/ communities reporting that they have personally experienced discrimination of any form.		March 2021 People Survey: / 11.5% of Ethnic Minority respondents (29 respondents out of 252 Ethnic Minority respondents) and, / 4.9% White respondents (92 out of 1885 White respondents) / reported they experienced discrimination from managers, team leaders or other colleagues.	Red	Amber Green / ↑
		5.4	Improve disability, ethnicity, sexual orientation, religion and belief declaration rates in Electronic Staff record to target of 95%		November 2021 / Disability 94.4% / Ethnicity 91% / Sexual Orientation 84% / Religion and belief 64%	Green	Amber Green / ↓

Equality Objective	Reference	Measures	Performance data	RAG rating July 22	RAG rating January 23
5 continued	5.5	Improve representation of disabled colleagues in Exec and C, D and E roles to 7.5%	WDES 2021 data*: / Grades C, D and E combined representation for disabled colleagues is 8.2%. The overall total of Grades C,D and E is 8.4%. (2021 WDES report) in the CQC. / Executive Grade staff have self-reported: / 3% disabled, 89.6% non-disabled, and 7.5% have ”not stated” whether they have a disability or not. / The “not stated” figure is higher than the overall grades “Not stated” figure of 5.6%. / *Data taken from Electronic Staff Record 31st March 2021.	Amber	Amber Green / ↑
	5.6	Increase likelihood of disabled applicants being appointed from shortlisting	WDES 2021 data* shows disabled candidates being appointed from shortlisting – compared to non-disabled candidates – is 1.197. / A score between the range of “0.80 -1.25” is considered “non-adverse”. As such, a score of 1.001 suggests equal likelihood of being appointed from shortlisting. / *Data taken from Electronic Staff Record 31st March 2021.	Green	Green / →
	5.7	Reduce gap between disabled colleagues and non-disabled colleagues who say that they have experienced bullying or harassment	WDES 2021 data*: / 16.9% of disabled respondents (around 84 out of 497 disabled respondents) and, / 6.7% of non- disabled respondents (around 113 out of 1679 non-disabled respondents) / reported experiencing bullying, harassment or abuse from other CQC staff. / *Results taken from the March 2021 Pulse Survey.	Green	Amber / ↓

Equality Objective	Reference	Measures	Performance data	RAG rating July 22	RAG rating January 23
5 continued	5.8	Reduce gap between disabled colleagues and non-disabled colleagues who say that we provide equality in career progression and that their contributions to CQC are recognised	WDES 2021 data* : / 37.4% of disabled respondents (around 186 out of 497 disabled respondents) and, / 53.2% non-disabled respondents (around 893 out of 1679 non-disabled respondents) / reported they believe that the CQC provides equal opportunities for career progression or promotion. / *Results taken from the March 2021 Pulse Survey.	Red	Amber / ↑
	5.9	Improve percentage of colleagues who have had reasonable adjustment requests met from 51% to 100% by March 2022	WDES 2021 data*: / 67% of disabled respondents (294 out of 392 disabled respondents) responded positively about CQC making appropriate reasonable adjustments to enable them to carry out their work. / *Results taken from the March 2021 Pulse Survey.	Green	Red / ↓
	5.10	Achieve Disability confident employer level 3 by March 2023	We received the Disability confident employer level 2 award in June 2022. / We are planning to work towards Level 3 this year.	Green	Amber Green / ↓
	5.11	Achieve Carers Confident employer level 1 by March 2022 and level 2 by March 2023.	Carer Confident employer level 1 was achieved prior to March 2022. / We are planning to work towards Level 3 this year.	Green	Amber Green / ↓

Table 3: Caveats or limitations of data
Evidence sources	Overview	Caveats or limitations
Annual Awareness Survey	Computer Assisted Telephone Interviews which lasted approximately 15 minutes. This was conducted between December 2021 and January 2022. / This was a nationally representative sample of 1000 adults in terms of English region, age, ethnicity and gender. The sample also includes at least 100 responses from CQC’s key sub-groups (carers, recent healthcare users, people with long-term health conditions, and those aged 65+) to allow for meaningful comparisons
Annual Provider Survey	The Annual Provider Survey is sent to all providers (Registered Manager or Nominated Individual for all registered locations). The survey ran from November to December 2021.Received a response rate of 36.9%. / Results from the Annual Provider Survey have been weighted to ensure the responses are representative of the population we surveyed.	Findings from the annual provider survey showed a high level of positivity. To help us understand what was driving the answers, and whether the results are appropriate to use as a baseline, we are exploring why providers responded the way they did.
Annual Stakeholder Survey	The Annual Stakeholder survey was sent to 980 organisations whom CQC has worked with over the past year. This was made up of; / Arms length bodies / Commissioners of health and care / Other regulatory bodies / Integrated Care System leads / Other commissioning groups / Other public representatives / Professional Associations / Statutory public representatives. / There survey ran from December 2021 to February 2022 (extend a month due to Covid). / There was a 23% (227/980) response rate	Low response rates overall and per stakeholder group. Due to low response rates, we were unable to weight the results. Unweighted results are reported which means that the survey results are not representative of the population surveyed and are therefore findings of the groups that responded.
CRM data	System data on our performance
Internal monitoring- Public engagement log	Log of insight / co-production undertaken by the Public Engagement Team	Identifying whether co-production/insight that has informed CQC’s definition of quality was undertaken retrospectively therefore there could be some errors. / The log reflects work the Public Engagement Team have conducted. This log does not capture coproduction activity that the team is not made aware of.

References in tables