PUBLIC BOARD, 01 February 2023

TITLE: Quarterly Change and People Update

Executive Sponsor: Kate Terroni, Chief Inspector of Adult Social Care, Integrated Care and Interim Chief Operating Officer and Mark Sutton: Chief Digital Officer

Presenter: Amy Pritchard: Director of Transformation and Jackie Jackson, Director of People

PURPOSE: FOR ASSURANCE
This paper is provided to enable the Board to fulfil their duties in relation to:
- Monitoring the progress and delivery of strategic change programmes
- Ensuring financial probity and the efficient and effective use of resources
PROPOSAL OR RECOMMENDATION
Information for Board to be aware of:
- Impact on CQC and stakeholders - the continuation of Target Operating Model and Strategy implementation.
- Timeline for delivery – ongoing until financial year 2024/2025.
Board are asked to note on the delivery performance.
BACKGROUND
This paper is an established component of CQC’s governance of its strategic transformation portfolio, it provides visibility of performance against delivery for the quarter ending December 2022.
KEY POINTS
Key achievements over the last quarter include:
- Board endorsement of the revised roll out approach for transforming our Regulatory Services (a service is what our people provide, as an act of valued, meaningful activity).
- Appointment of Service Directors across our Regulatory Transformation work to provide robust leadership of the changes we are making to our Regulatory Services.
- Corporate Services Design approach approved by the Executive Team.

Transformation Update
Performance Summary
The revised roll out approach and plans to deliver the second phase of our transformation work have now been fully endorsed by our Executive Team and Board. We have mobilised our teams to deliver against these and, learning from our transformation work to date, we have strengthened and improved practice across our transformation teams.
Portfolio Pillar 1: Regulatory Framework
This pillar is focused on the design of our new regulatory model, it includes our Single Assessment Framework as well as our approach to Assessing Integrated Care Systems and Local Authority Assurance. This work informs the people, process, digital and data requirements that are delivered by other programmes in the portfolio.
Work continues to deliver our approach for Local Authority Assurance and Integrated Care Systems assessment by April 2023. The requirements to deliver our strategic solution are included in our work to transform our Regulatory Services.
Portfolio Pillar 2: Organisational Design and Development
This pillar focuses on delivering the people changes needed to support our new regulatory model, their role is to ensure that we have the right skills and culture in place to deliver on our new approach.
Working with senior operational leaders, we are focusing efforts to ensure we have the right environment for the safe and successful transition to Integrated Teams by the end of March. We are taking the time to build confidence and trust in the new ways of working; ensuring colleagues feel confident and empowered to undertake their new roles.
Portfolio Pillar 3: Regulatory Services
This pillar focuses on the delivery of new digital and data services that are key to:
- Embedding our regulatory framework in daily practice.
- Unlocking our ability to become more insight driven, dynamic and responsive to regulatory risk.
- Creating seamless, more efficient and effective interactions for all people who interface with us as an organisation (internally and externally).
Our new Data & Insight products continue to be released for use; providing our operational teams with accurate and insightful data from which to drive activity. Revised plans to deliver new Regulatory Services have been agreed. We have appointed Service Directors, supported by subject matter experts from their teams, to agree the detailed scope and activities required in order to transform our Regulatory Services.
Portfolio Pillar 4: Corporate Services
This pillar focuses on the delivery of our support services to departments focusing on our Finance Transformation and Corporate Services to ensure they:
- Create cost efficient functions that provide value for money​.
- Professionalise capabilities delivering high quality standards and ensuring effective ways of working that enable front line delivery of services.
Our Executive Team have approved the approach for the Corporate Services re-design. This takes learning from our transformation work to date with a structured, Director-led, participatory design approach that will allow for the involvement of a greater number of colleagues.
People Strategy Update
Culture
CQC’s Pulse Survey Advisory Group has been established and is supporting engagement in Directorate action planning in response to survey feedback.
Operations Leadership Teams will participate in workshops during February to May to enable them to individually and collectively process their experience of change and move forward positively in building a culture where there is trust, confidence and empowering ways of working.
CQC’s Executive Team will review the alignment of CQC’s cultural direction with strategic intent and operational activity this quarter, agreement of further cultural activity will follow this.
Capability building
We continue to support colleagues with the development of specialist Data and Insight learning packages to ensure they have the right skills and capabilities to perform their roles effectively.
Operations leadership teams have completed induction activities to support the transition to Integrated Teams and a development programme is also ongoing through Q4 for Operations Managers with line management responsibilities. Finally, we are continuing to develop the learning modules to support the Regulatory Transformation work and will be planning a programme of data literacy through 2023/24 to build the required data and digital capabilities as we progress through transformation.
Conclusion and Next Steps
Key priorities include:
- Commence the Corporate Services design work.
- Mobilise our teams in line with the revised roll out approach for Regulatory Transformation.
Those who contributed to this paper
- Nina Snell – Head of Transformation Delivery
- Jackie Jackson – Interim Director of People
CONTRIBUTIONS
The following groups/people have been involved in forming this paper:
Groups/people	Involvement?	Feedback
HR	Yes	People update comes directly from HR colleagues.
Finance	Not applicable
DHSC	Not applicable
Executive Team	Not applicable
Board Committee	Not applicable
Executive Committee	Not applicable
Trade Unions	Not applicable
Staff Networks	Not applicable
Other – please specify	Not applicable