CQC Business Plan 2023-26

Contents:
Introduction [to follow – joint Chair/ CEO] / Business plan – Our objectives / Business plan – Our key results

Appendix A – Risks / Appendix B – Budget / Appendix C – Detailed objectives and key results

Introduction

[To follow]

Our objectives
People & Communities
1
We will respond to information we receive and incorporate it into our regulation.
We will deliver reliable, flexible processes and technology and measure that that they are responding to our needs and priorities.
8
We will manage within our financial resources and measure that we are delivering effectively, efficiently and economically.
7
We will train and develop our people, so they have appropriate capabilities and personal and career development; respond to their well-being needs and reinforce our equalities ambitions; whilst ensuring the key results for our people are supportive of cultural expectations.
6
We will use insight to measure risk at service and national level and use the insight to prioritise our activities.
We will use insight to measure risk at service and national level and use the insight to prioritise our activities.
5
4
We will manage our organisation well, determining and measuring this through appropriate assurance.
3
Smarter Regulation

2
Through our regulation we will work in partnership and collaboration with other sectors and regulators.

Core Ambition: Accessing Local Systems
14
We will examine and understand how quality of care is experienced in local systems and use our findings to share best practice, challenge unwarranted variances and drive improvement.
We will develop our approach to health and care inequality reduction through work with our partners, aligning our evidence base and improving our skills for assessment of providers and local systems
13
Core Ambition: Tackling Inequalities in Health & Care
We will spotlight priority areas that need to improve, enable access to support where it’s needed most and where relevant encourage innovation and research.
12
Using our independent voice, we will communicate our findings on the sectors and poor practice and develop our knowledge of what good looks like.
11
Accelerating Improvement
We will listen, learn and respond to people’s concerns about our organisation.
10
We will respond to information we receive and incorporate it into our regulation.
9
Safety Through Learning
Performance 2023

Our key results
People & Communities
Achieve a 60-80% response rate on NCSC call lines
Create and test quality measures for NCSC by July 2023
Process time from receipt to transferred to Operations (where required)
Deliver volume of commitments on partnership assessments per quarter
We will respond to information we receive and incorporate it into our regulation.
1
2
Through our regulation we will work in partnership and collaboration with other sectors and regulators.
Smarter Regulation
Develop, test and then implement a new quality framework by September 2023
90% of audit recommendations are complete within agreed timescales
Deliver the internal audit programme within the financial year
Launch National and Service level profiles by October 2023
We will manage our organisation well, determining and measuring this through appropriate assurance.
3
4
We will use insight to measure risk at service and national level and use the insight to prioritise our activities.
Design and develop productivity metrics
Increase % of inspections triggered by risk
Monitor and analyse for trends the % of risk inspections resulting in rating less than good
Reduce the average time between assessments
5
We will use insight to measure risk at service and national level and use the insight to prioritise our activities.
Increase by 5% site visits out of hours.
Monitor and improve days per quarter that Experts by Experience and Specialist advisors are used as part of assessment.
6
We will train and develop our people, so they have appropriate capabilities and personal and career development; respond to their well-being needs and reinforce our equalities ambitions; whilst ensuring the key results for our people are supportive of cultural expectations.
Monitor % colleagues passing probation (equivalent for internal candidates)
% of colleagues promoted from within the organisation
% of colleagues with career development plan
Increase in completion of development opportunities
Increase of % of colleagues with protected characteristics at all grades
Increasing reporting of protected characteristics to 95%.
Widening the People/Pulse Survey and ESR protected characteristics data capture (e.g. trans and non-binary, disability and neurodivergence breakdown), and going further than the Equality Act characteristics
Increase positive sentiment on ‘Recommend CQC as a place to work’
Baseline (then increase) positive sentiment, ‘I feel empowered by my line manager.’
7
We will manage within our financial resources and measure that we are delivering effectively, efficiently and economically.
Within 1% of our available fee funded envelope
Within our available Grant in Aid funded envelope
8
We will deliver reliable, flexible processes and technology and measure that that they are responding to our needs and priorities.
Availability of systems - target 99.9%
Public and Provider Customer Satisfaction on our systems – target 90%
Increase in positive feedback during people survey, for question ‘I have the equipment / technology to carry out my role’
We will monitor and improve the timeliness of mental health act reviews.
Create and test process for understanding quality of registration service across Q1 and Q2
We will reduce the volume of applications pending completion that are over 10 weeks old
All staff and providers are using the new single assessment framework, regulatory framework and Regulatory Platform by 31 March 2024.
All staff and providers are using the new single assessment framework, regulatory framework and Regulatory Platform by 31 March 2024.

The detailed metrics are available in appendix C
Build evidence to enable us to assess equity in access, experience and outcomes in providers (Q3)
Safety Through Learning
% of services that require enforcement action following regulatory activity
Monitor % of civil enforcement which receive representations
Process time from receipt to transferred to Operations (where required)
Monitor % of successful prosecutions and guilty pleas
We will respond to information we receive and incorporate it into our regulation.
9
10
We will listen, learn and respond to people’s concerns about our organisation.
Accelerating Improvement
Publication of our major reports across the financial year
Monitor and improve the number of people who access our major reports and publications through our website
Using our independent voice, we will communicate our findings on the sectors and poor practice and develop our knowledge of what good looks like.
11
Output of quarterly analysis
Through using our people’s experience framework and piloting inequalities local outreach plans (Q3)
Launch of improvement campaigns
Evaluate impact of improvement campaign
12
We will spotlight priority areas that need to improve, enable access to support where it’s needed most and where relevant encourage innovation and research.
Publish research into improvement cultures in services
Produce strategic improvement plan by end of Q2
Baseline (and then improve) timeliness in criminal enforcement
Reduction in prosecution of common incidents
Baseline the timeliness in our complaint’s responses
Baseline the timeliness and volumes of Freedom of Information requests we receive and respond to
Quarterly analysis of ratings review
Support the Covid-19 inquiry
Monitor % of recommendations with progress and on track.
Core Ambition: Tackling Inequalities in Health & Care
Core Ambition: Accessing Local Systems
13
We will develop our approach to health and care inequality reduction through work with our partners, aligning our evidence base and improving our skills for assessment of providers and local systems
Establish an appropriate structure for both enhanced internal and external working (Q1)
Test our health inequalities data (Q1)
Obtain health inequalities reduction plans and align our findings to the CORE20PLUS5 (Q2)
14
We will examine and understand how quality of care is experienced in local systems and use our findings to share best practice, challenge unwarranted variances and drive improvement.
Create and publish a map to show service rating by integrated care system (ICS) and overlay the population data. (Q1)
Engagement activities with integrated care systems, providers and other regulators. (Q2)
Volume of published Integrated Care Systems (ICS) assessments
Volume of published Local Authority assessments
Milestone
Result
Key
Appendix A – Risks
RISK CATEGORY		STRATEGIC RISK TITLE
Strategy Risk	S1	Our strategy does not match the current needs of the sector.
	S2	We do not have effective governance and risk management frameworks in place.
	S3	We do not deliver our organisation transformation effectively.
	S4	We do not obtain enough feedback from people to ensure that user voice is central to our regulatory activity.
	S5	We are unable to obtain the right data from external stakeholders to accurately assess the risk in services we regulate.
	S6	We do not have enough quality data to be an intelligence-based regulator that shares information with others so they can act.
	S7	We are unable to drive improvement and therefore do not add value to the health and social care sector
Operational Risk	O1	Our operational workforce is not as productive as it should be.
	O2	We do not make an accurate assessment on the quality of care for people using services.
	O3	Our operational workforce do not comply with policies and procedures.
	O4	Our operational processes and controls are not flexible enough to respond to changing demands and priorities.
	O5	There is the risk that IT disaster recovery arrangements do not meet business needs.
	O6	If risk within the sector significantly increases there is a risk that we do not have operational resources to respond in a timely manner
Reputational Risk	E1	We do not have a productive relationship with key stakeholders.
	E2	The current legislation is inappropriate to cope with innovations.
People Risk	P1	We cannot attract and retain our workforce.
	P2	Our colleagues don’t have the appropriate skills (including clinical skills).
	P3	Our colleagues are insufficiently engaged in our culture change and ways of working.
	P4	We have not delegated roles and responsibilities appropriately, clearly and/or effectively.
Security Risk	C1	Interruption to our technology systems due to ransomware or other malign attacks.
	C2	Unauthorised access to our systems and misuse of information we hold.
Financial Risk	F1	The fees we charge are considered to be excessive by those we regulate.
	F2	We do not get appropriate funding to deliver our commitments.
	F3	We do not have appropriate departmental controls and financial oversight.

Appendix B – Budget

Budget 2023-24	£m
Pay	190
Non-pay	44
Expenditure	234
Depreciation	11
Total net expenditure	245

Fee income	-212
Funded Activity	-2
Grant in Aid	-20
Non-cash	-11
Total funding	-245

Appendix C – Key results and metrics (Detailed)
Strategic Theme: People and Communities
Objective	Key Result	Desired Impact	Owner
1. We will respond to information we receive and incorporate it into our regulation	1.1 A measure will be included here in relation to how we utilise and respond to safeguarding and whistleblowing information once the LLR is published. The proposed measure will be discussed with ET in April and Board in May 2023.
	Result: Achieve a 60-80% response rate on NCSC call lines (60% general enquiries, 70% registration, 80% concerns & 80% mental health)	1.2 To ensure we capture key regulatory information and provide an effective service, calls to our National Customer Service Centre (NCSC) will be responded to quickly, processed promptly and information captured to a high standard to inform our regulation	Director of Operations Hub
	Result: Process time from receipt to transferred to Operations (where required)
	Milestone: Create and test quality measures for NCSC by July 2023. (linked to 3.1)
	Result: We will monitor and improve the timeliness of mental health act reviews.	1.3 Ensure people detained under the Mental Health Act have access to a complaints process where they feel listened to and to increase public knowledge of the experience of people detained.	Director of National Operations
2. Through our regulation we will work in partnership and collaboration with other sectors and regulators	Result: Deliver volume of commitments on partnership assessments per quarter.	2.1 Through partnership working we will inspect and assess specialist services to ensure safe and effective care. We will use our findings to drive improvement in these areas. / Partnership assessments includes Health and Justice, Children’s service, Mental Health Act reviews and Ionising Radiation (Medical Exposure) Regulations work.	Director of National Operations
Strategic Theme: Smarter Regulation
3. We will manage our organisation well, determining and measuring this through appropriate assurance.	Milestone: Develop, test and then implement a new quality framework by September 2023.	3.1 Defining what good quality regulation is and implementing quality measures locally and centrally, we will provide data on our current status and a governance pathway from strategy to quality improvement informed by quality assurance.	Director of Finance, Commercial, Workplace & Performance
	Milestone: Deliver the internal audit programme within the financial year. / Result: 90% of audit recommendations are complete within agreed timescales.	3.2 Our Internal Audit programme will provide independent assurance of our risk management, governance and control measures that are in place. Where recommendations are made, we will ensure timely action is taken.	Director of Finance, Commercial, Workplace & Performance
	Milestone: Design and develop productivity metrics	3.3 Alongside the roll-out of our new methodology and processes we will develop metrics to understand and monitor our operational productivity.	Director of Finance, Commercial, Workplace & Performance
4. We will use insight to measure risk at service and national level and use the insight to prioritise our activities.	Milestone: Launch National and Service level profiles by October 2023.	4.1 We will embed National and Service level profiles in our regulatory approach to ensure all data and information is utilised in our understanding of the risk of services.	Director of Data and Insight
	Result: Increase % of inspections triggered by risk / Result: Monitor and analyse for trends the % of risk inspections resulting in rating less than good.	4.2 We will explore sector and regional variation in the outcomes of our assessment, specifically in relation to those with the most inherent risk, to ensure continuous learning and improvement in our insight approach.
5. We will have an always on regulation and ensure only services assessed as able to provide appropriate safe care are registered	Result: Reduce the average time between assessments	5.1 We will reduce the time between a service being rated and their next assessment to reduce the time between assessments, especially in poorly rated services. This will reduce the potential impact on people receiving poor care, as well as improve the accuracy of service ratings.
	Result: Increase by 5% site visits out of hours.	5.2 We will increase the number of our hours site visits for services where people live to ensure to ensure we have a wider experience of the service and the care people receive.
	Result: Monitor and improve days per quarter that Experts by Experience and Specialist advisors are used as part of assessment.	5.3 We will increase the proportion of time that people who use services or are experts in providing services, are involved in assessing service quality.
	Milestone: Create and test process for understanding quality of registration service across Q1 and Q2	5.4 We will develop our understanding of the quality of our registration service through a new process to measure it.	Director of National Operations
	Result: We will reduce the volume of applications pending completion that are over 10 weeks old	5.5 We will ensure we offer a timely registration service for providers.	Director of National Operations
6. We will train and develop our people, so they have appropriate capabilities and personal and career development; respond to their well-being needs and reinforce our equalities ambitions; whilst ensuring the key results for our people are supportive of cultural expectations.	Result: monitor % colleagues passing probation (equivalent for internal candidates)	6.1 To ensure our people have the appropriate capabilities for their role we will monitor completion of induction requirements and passing probation.
	Result: % of colleagues promoted from within the organisation. / Result: % of colleagues with career development plan / Result: Increase in completion of development opportunities	6.2 We will support our people with career progression through personal developments and participation in development.
	Result: Increase of % of colleagues with protected characteristics at all grades / Result: Increasing reporting of protected characteristics to 95%. / Result: Widening the People/Pulse Survey and ESR protected characteristics data capture (e.g. trans and non-binary, disability and neurodivergence breakdown), and going further than the Equality Act characteristics, e.g. menopause, social mobility.	6.3 We will reinforce and deliver our equalities ambitions as an organisation.
	Result: Increase positive sentiment on ‘Recommend CQC as a place to work’	6.4 Through our people survey we will see an increase in the volume of colleagues who provide a positive response to the question ‘recommend CQC as a place to work’, whilst continuing to drive improvement in this area.
	Result: Baseline (then increase) positive sentiment, ‘I feel empowered by my line manager.’	6.5 We will understand our colleague’s sentiment in relation to the support and line management they receive through our people pulse survey.
7. We will manage within our financial resources and measure that we are delivering effectively, efficiently and economically.	Result: Within 1% of our available fee funded envelope	7.1 To ensure we are making sound financial decisions we will ensure we manage our budget within our available fee funded envelope.	Director of Finance, Commercial, Workplace & Performance
	Result: Within our available Grant in Aid funded envelope	7.2 To ensure we are making sound financial decisions we will ensure we manage our budget within our available Grant in Aid funded envelope.	Director of Finance, Commercial, Workplace & Performance
8. We will deliver reliable, flexible processes and technology and measure that that they are responding to our needs and priorities.	Milestone: All staff and providers are using the new single assessment framework, regulatory framework and Regulatory Platform by 31 March 2024. / Milestone: All staff in corporate functions will be working in a new organisational structure and using the latest cloud-based technology by 31 March 2024.	8.1 All CQC will be using a new single assessment framework across all sectors and across the full breadth of our regulation, including registration, assessment, reporting and enforcement. / We will have defined structures, ways of working, capabilities, roles and responsibilities for our corporate functions and modernised CQC finance systems, to ensure future resilience, address current deficiencies and deliver a direct benefit to a wide range of stakeholders by upgrading the service offering available to support the business	Director of Transformation
	Result: Availability of systems - target 99.9%	8.2 We want to ensure our colleagues and providers who use our systems, have access to reliable consistent technology systems to support our work.	Director of Technology
	Result: Public and Provider Customer Satisfaction on our systems – target 90%	8.3 We will track customer satisfaction with our systems to understand the digital service we provide and inform improvement.	Director of Technology
	Result: Increase in positive feedback during people survey, for question ‘I have the equipment / technology to carry out my role’	8.4 We want to ensure our people have a positive experience with their equipment and technology, that makes it possible to do their work.	Director of Technology
Strategic Theme: Safety through learning
9. We will protect people who use services from risk of harm, by using our enforcement powers where there is poor practice.	Result: % of services that require enforcement action following regulatory activity / Result: Improve the timeliness in taking civil enforcement action.	9.1 We will analyse and monitor services that require enforcement following assessment to review for any trends or patterns. We will ensure where we need to take civil enforcement it is undertaken in a timely manner to minimise the risk of people receiving poor care and to ensure the services have the information necessary to take action.	Director of National Operations
	Result: Monitor % of civil enforcement which receive representations.	9.2 We will monitor where we receive representations to civil enforcement to ensure we can learn from any themes in both the challenges and the outcomes.	Director of National Operations
	Result: Baseline (and then improve) timeliness in criminal enforcement. / Result: Monitor % of successful prosecutions and guilty pleas.	9.3 Ensure we take timely criminal enforcement action that is successful in holding services to account and protecting people, and monitor the outcomes of criminal activity to consider any learning.	Director of National Operations
	Result: Reduction in prosecution of common incidents.	9.4 Through learning and engagement with the sector we will see a reduction in prosecution of common incidents (such as falls from windows, ligature risks and sexual abuse).	Director of National Operations
10. We will listen, learn and respond to people’s concerns about our organisation.	10.1 A measure will be included here in relation to ensuring we have suitable processes in place to listen, learning and respond as an organisation once the LLR is published. The proposed measure will be discussed with ET in April and Board in May 2023.
	Result: Baseline the timeliness in our complaints responses. / Result: Baseline the timeliness and volumes of Freedom of Information requests we receive and respond to.	10.2 We will respond to complaints about CQC, and Freedom of Information requests in a timely manner to ensure we are transparent and providing information / supportive of those who contact us.
	Milestone: Quarterly analysis of ratings review	10.3 We will respond to requests to review the ratings reviews that we have received and evaluate the reviews for any themes, trends or learning.
	Milestone: Support the Covid-19 inquiry.	10.4 As an organisation we will support the learning process from the COVID-19 pandemic, including providing information, documentation and supporting the COVID-19 inquiry.
	10.5 A measure will be included here in relation to CQC colleagues engaging with the Speak Up processes, once the LLR is published. The proposed measure will be discussed with ET in April and Board in May 2023.
	Result: Monitor % of recommendations with progress and on track.	10.6 To ensure visibility in our delivery we will monitor the recommendations made to CQC from stakeholders and the commitments we make through our publications and track the delivery and progress quarterly.
Strategic Theme: Accelerating Improvement
11. Using our independent voice, we will communicate our findings on the sectors and poor practice, and develop our knowledge of what good looks like	Milestone: Publication of our major reports across the financial year. / Result: Monitor and improve the number of people who access our major reports and publications through our website.	11.1 Our independent voice gives unique perspective on people’s experience and shines a light on inequalities in the sector. Throughout the year we will publish a number of major reports and evaluate and monitor the reach they have.
	Result: Output of quarterly analysis / (To include quarterly qual analysis on decision making for independent voice prioritisation)	11.2 Through quarterly analysis we will demonstrate that we have chosen the most important areas to focus on, based on our evidence and insights, and ensure that, in our publications, inequalities have been addressed.
	Milestone: Through using our people’s experience framework and piloting inequalities local outreach plans (Q3)	11.3 Our independent voice will have a strong focus on people’s experiences and seek to reduce inequalities. Independent Voice draws on findings from our people’s experience framework and inequalities outreach.
12. We will spotlight priority areas that need to improve, enable access to support where it’s needed most and where relevant encourage innovation and research.	Milestone: Launch of improvement campaigns / Result: Evaluate impact of improvement campaign	12.1 We will undertake a series of improvement campaigns throughout the year, and for each undertake an evaluation of the impact of the work, the results of which will inform our improvement campaigns for the following years.
	Milestone: Publish research into improvement cultures in services	12.2 We will commission and publish research in improvement cultures across services.
	Milestone: Produce strategic improvement plan by end of Q2.	12.3 We will produce a plan on activities we will drive improvement internally, and in the health and care system, whilst delivering our strategic commitments. Our plan will incorporate our work on our quality improvement strategy.
Core Ambition: Tackling inequalities in health and care
13. We will develop our approach to health and care inequality reduction through work with our partners, aligning our evidence base and improving our skills for assessment of providers and local systems	Milestone: Establish an appropriate structure for both enhanced internal and external working (Q1)	13.1 In order to ensure appropriate skills, approach and tactical response to drive health inequalities we will establish an appropriate structure to enhance both internal and external working.	Scott Durairaj
	Milestone: Test our health inequalities data (Q1)	13.2 We will test the strength of our evidence against the 42 Health Inequalities reduction plan created for 21-22
	Milestone: Obtain health inequalities reduction plans and align our findings to the CORE20PLUS5 (Q2)	13.3 We will obtain health inequalities reduction plans for 22-23 to identify health inequalities by footprint area, and this with key stakeholders, align our findings to the CORE20PLUS5 and use the conclusions throughout our regulation.
	Milestone: Build evidence to enable us to assess equity in access, experience and outcomes in providers (Q3)	13.4 We will build evidence to enable us to assess equity in access, experience and outcomes in providers in our Single Assessment Framework
Core Ambition: Assessing local systems
14. We will examine and understand how quality of care is experienced in local systems and use our findings to share best practice, challenge unwarranted variances and drive improvement.	Milestone: Create and publish a map to show service rating by integrated care system (ICS) and overlay the population data. (Q1)	14.1 We will review data and publish documentary evidence across all local authorities, the analysis will enable us to start to understand the quality of care in a local area or system and provide independent assurance to the public of the quality of care in their area.
	Milestone: Engagement activities with integrated care systems, providers and other regulators. (Q2)	14.2 Use our Integrated Care System insights, to engage, influence and drive improvement across sectors.
	Result: Volume of published Integrated Care Systems (ICS) assessments	14.3 We will launch our work to review and assess how Integrated Care Systems are delivering their responsibilities under the Health and Care Act 2022.
	Milestone: Volume of published Local Authority assessments	14.4 We will launch our work to review and assess how Local Authorities are delivering their Care Act functions.