PUBLIC BOARD MEETING

Date:	24 May 2023	Agenda item: 3.3 / Paper number: CM/05/23/33
Title of paper:	Quarterly Transformation and People Update
Purpose of paper:	For Assurance and To Note
Executive sponsor:	Kate Terroni, Interim Deputy Chief Executive and Mark Sutton, Chief Digital and Data Officer
Presenter(s) or lead person:	Amy Pritchard, Director of Transformation and Jackie Jackson, Interim Director of People
Summary: / This paper is provided to enable the Board to fulfil their duties in relation to: / Monitoring the progress and delivery of strategic change programmes / Ensuring financial probity and the efficient and effective use of resources / Recommendations: / The Board are asked to note the transformation delivery performance and the People Strategy Update. / ​​Information for Board to be aware of: / ​Impact on CQC and stakeholders - the continuation of Target Operating Model and Strategy implementation / ​Timeline for delivery – ongoing until 2024/2025
Governance: / Transformation, People, and Culture matters are considered throughout the governance forums within the organisation with regular updates provided to the Investment Committee, People Committee, Executive Team, and Board.
Strategy: / CQC’s Transformation Programme is key to delivering its strategic ambitions and this paper provides visibility of performance against delivery for the quarter ending April 2023. / Key Points / Key achievements over the last quarter include: / Board endorsement of the revised roll out approach for transforming our Regulatory Services (a service is what our people provide, as an act of valued, meaningful activity). / Appointment of Service Directors across our Regulatory Transformation work to provide robust leadership of the changes we are making to our Regulatory Services. / Launch of our Regulatory Governance, Leadership & Outreach Services (Regulatory Transformation). / Corporate Services Design approach approved by the Executive Team. / Performance Summary / Good progress has been made over the last quarter in delivering CQC’s strategic ambitions. The Regulatory Transformation Programme is now well underway and has delivered 3 new services in recent months and plans remain on track to deliver the remaining regulatory services throughout July and October. Our Regulatory Operations Programme has now closed having delivered its scope to reconfigure operational roles and structures to better meet the requirements of the new Single Assessment Framework and regulate services by network area, which also prepares us for Local Authority Assurance and Integrated Care System Assessment. We have also now begun work to re-design our corporate services to ensure they are efficient and effective in light of our new regulatory approach. / Portfolio Pillar 1: Regulatory Framework / This pillar is focused on the design of our new regulatory model, it includes our Single Assessment Framework as well as our approach to Assessing Integrated Care Systems and Local Authority Assurance. This work informs the people, process, digital and data requirements that are delivered by other programmes in the portfolio. / The formal closure of the Regulatory Framework Programme was approved in March following the successful delivery of the Single Assessment Framework and approaches to underpin the way in which we assess local authorities and integrated care systems. / Portfolio Pillar 2: Regulatory Operations / This Pillar focuses on delivering the people changes needed to support our new regulatory model, their role is to ensure that we have the right skills and culture in place to deliver on our new approach. / The formal closure of the Regulatory Operations Programme took place in May following the delivery of its objectives as outlined above. / Portfolio Pillar 3: Regulatory Transformation / This pillar focuses on the delivery of new end to end regulatory services that are digitally enabled, the objectives of this programme are to: / Embed our new regulatory framework in daily practice. / Unlock our ability to become more insight driven, dynamic and responsive to regulatory risk. / Create seamless, more efficient, and effective interactions for all people who interface with us as an organisation (internally and externally). / This programme is focussed on delivering new regulatory services in three core drops: April, July and October. In April, the programme launched its Regulatory Leadership, Governance and Outreach Services. These services are foundational and enable us to effectively implement and scale other regulatory services across the months of July and October. The Regulatory Governance Service, in particular, will ensure the Single Assessment Framework is effectively operationalised in the latter months and will also ensure our regulatory activity is prioritised and remains within capacity. Future releases will see the programme deliver new Registration, Contact, Operational Planning, Assessment, Enforcement and Market Oversight Services. We are also in the process of standing up teams to undertake Local Authority Assurance with a view to scaling this approach in quarter 4 along with providing the capability to undertake Integrated Care System Assessments. / Transforming Data and Insight / The programme was closed at the end of March having delivered our new data and insight enterprise data platform. Closure activities were completed including a benefits review and lessons learned. A post closure assurance review will be carried out in June. / Portfolio Pillar 4: Corporate Services / This pillar focuses on the delivery of our support services to ensure they: / Create cost efficient functions that provide value for money​. / Professionalise capabilities delivering high quality standards and ensuring effective ways of working. / The Programme Business Case for this programme will be finalised in June, with the programme objectives, scope, and individual function/directorate plans being agreed.
Finance: / There are no specific financial considerations for this paper. CQC’s Investment Committee, Executive Team, and Board are regularly updated on the financial performance of the Transformation Programmes.
Risk: / There are no specific risk considerations for this paper. Transformation risks are regularly discussed at the Executive Team and the Audit and Risk Assurance Committee with assurance provided to the Board.
People: / Director for People and Culture / We have commenced our recruitment activity for our new Director for People and Culture, with the advert going live the first week in May with a closing date of 8th June. We are aiming to have appointed the successful candidate by the end of July with a view to them starting in post in the Autumn. / Prior to going out to market we have undertaken a comprehensive review of our requirements for this critical role, engaging with our networks, trade unions, independent experts, and our executive search partner Moloney to test our thinking and ensure we are recruiting the right expertise for the future. / This has resulted in the creation of a new job description and title emphasising the key attributes, skills and experience we require to lead the implementation of our people strategies that will drive our transformation and our response to the findings of the Listening, Learning and Responding to Concerns Review (LLR). The LLR Review highlighted work to be undertaken on our culture, how we listen and interact at all levels, the Director for People and Culture will have a key part to play in this work. This is reflected in the new job description which has a strong emphasis on cultural change with a proven track record in delivering sustainable cultural change as an essential criterion. Our conversations with Moloney have identified that these are desirable skills within the current labour market, and they have advised that the title of Director for People and Culture will send a strong message as to the type of candidate we are looking for. / As part of our recruitment, we will undertake a robust process of assessment which will incorporate views from across the organisation. This will include key roles for our trade unions as chair of the engagement panel and our Diversity and Inclusion Manager as the independent member of our interview panel, which will also include Jenny Richardson, Department of Health and Social Care (DHSC) HR Director, to provide subject matter expertise to our decision making. We are currently seeking the appropriate governance and salary permissions via DHSC. We will keep the Board updated on our progress throughout this recruitment campaign. / Culture Update / The cultural work so far has identified how people inside CQC experience working here and what is important to them, resulting in a focus on a culture where people feel confident, trusted and empowered. This has informed the development of the Operations leadership modules and roll out of module 1 has now been completed. / The biggest cultural shift will be in relation to implementing the Single Assessment Framework. Our Senior Leadership Team will discuss proposals this week to engage all leaders this summer in what this means practically for our ways of working, and how leaders need to think and act differently. These sessions are expected to inform a set of shared cultural priorities, the activity that will support the work, and how we will measure success. / Pulse Survey / Our pulse surveys continue to inform how people experience the organisation. As a result of pulse survey feedback, the Executive Team have confirmed executive sponsorship for five workstreams that will support improved experiences. In June, the Pulse Survey Advisory Group will connect with workstream leads, working with them to embed regular feedback loops so that activity is informed by employee voice. / This week CQC’s Diversity &Inclusion (D&I) survey opened on 16th May and runs until 31st May and the results will inform CQC’s D&I strategy, staff employee network priorities and actions in support of the LLR Review recommendations. / The survey asks a number of questions around fairness and respect, plus other questions to help us report on the Workforce Race Equality Standard (WRES) and the Workforce Disability Equality Standard (WDES). The People Directorate will work with Pulse Survey Advisory Group and Equality Network representatives to support all Pulse Survey Advisory Group members in considering any connections with Directorate and Corporate priority areas. / Pulse Survey Action Group (PSAG) / As mentioned, the Executive Team have agreed to the five recommended corporate priorities and the need to link these with existing workstreams. PSAG members will be supported to embed feedback loops with business leads for these workstreams. / Priority theme Workstream Executive Sponsor / Communication, listening to colleagues and sharing feedback. Listening framework Chris Day, Director of Engagement / Leadership Leadership Team Development Kate Terroni, Interim Deputy CEO / Valuing colleagues Employee experience (People Plan) Joyce Frederick, Director of Policy and Strategy / Speaking up safely Speak up Mark Sutton, Chief Digital and Data Officer / Pay, reward and recognition Reward and Recognition Tyson Hepple, Executive Director of Operations / Sentiment of Our People / It’s critical through this transformational period to ensure effective engagement with colleagues and to encourage regular contribution. We are actively creating many opportunities for colleagues to engage, including local Joint Consultative Committee’s (JCC), Joint Negotiating and Consultation Committee (JNCC), Staff Forum, Equality Networks, Shadow Boards and Advisory Groups. Our more recent in-person Operational conferences provided an invaluable opportunity for people to meet face-to-face and to hear senior leaders reflect on the past year and, also, work together as a team. / The Operational conferences were a great opportunity to celebrate the many successes of the last 12 months, both as Operational Groups and individually. There was positive feedback about our new regulatory approach and technological platform, giving colleagues a much better sense of what the future will look like. / There have been some challenging but valuable conversations about the LLR Review and how we might work together going forwards. / Capability Building / We’ve completed an intensive “PowerBI Bootcamp”, that’s given all our data & insight colleagues new skills which will enable them to be creative with new and innovative analytical products. / In Operations, in readiness for the completion of the system, policy and process builds, we have completed learning needs analysis for the following service areas – Assessment, Criminal Enforcement, Registration Cancellations, Contact and Operations Planning Scheduling. The learning needs feedback will inform the content, delivery method, resource requirement, duration and priority of the learning and development products to support these areas. / The learning required to support our new Registration Cancellations Programme is planned for roll out by the end of May 2023.