BOARD MEETING

Date: 27 September 2023	Public Board Meeting	Agenda item: 3.2 / Paper number: / CM/09/23/32
Title of paper:	Corporate Performance Report (2023/24 – Q1)
Purpose of paper:	To Note/For assurance
Executive sponsor:	Kate Terroni, Deputy Chief Executive
Presenter(s) or lead person:	Chris Usher (Director of Finance, Commercial, Workplace & Performance)
Summary: / This paper is provided to enable the Board to fulfil their duties in relation to: / Holding the Executive to account for performance and the proper running of the organisation / Ensuring robust and effective systems of risk management / Ensuring financial probity and the efficient and effective use of resources / Recommendations: / The Board or Committee is asked to note and/or endorse an action underway.
Governance: / The performance against our business plan as been discussed with the executive committee, as well as sub-committees such as operations board.
Strategy: / The paper covers our performance against our business plan and associated KPIs.
Finance: / The paper cover our financial position at the end of the financial year.
Risk: / The paper covers the latest position on our corporate risk register and details any amendments since the last board discussion.
People: / The paper covers key people data in the business plan measures and their progress at the end of the financial year.

Business Plan performance

Our business plan metrics were reviewed and published in May 2023. Annex 1 provides an overview of our delivery at the end of quarter 1 against our business plan key results and our milestones, this paper highlights some of the key areas of our performance against the plan. This is the first end of quarter reporting since the revision of the metrics.

People and Communities

- Key Result 1 - To the end of July, we have met some of our corporate KPIs on safeguarding and whistleblowing, however some of our delivery is not in line with our targets or commitments. This remains a constant focus on our performance discussions to ensure all risk and potential cases of harm are responded to appropriately and in a timely manner. We launched our new regulatory platform in July 2023 which temporarily had an impact on our performance in safeguarding and whistleblowing KPIs, however our delivery has continued to increase since the end of July and September’s delivery is expected to be back within our normal levels of delivery.
- Key Result 2 - Our inspections continued to be focused on risk and using people’s experience and feedback. 16% of inspections this year to date have been directly triggered from people’s feedback. Other inspection triggers may also include people’s experience and feedback but in a more indirect way such as a combination of feedback which impacts our risk indicators.
- Key Result 3 & 4 - To the end of quarter one all National Customer Service Centre (NCSC) call lines exceeded their targets to answer calls within set time frames. In July 2023 our performance dipped slightly due to the pressures of our contact service roll-out on NCSC and our mental health and safeguarding lines fell below our target response rate. However, the time is takes for a case to be transferred to operational colleagues from NCSC is reduced from last financial year, which will have been positively impacted by our regulatory platform roll-out.

Smarter Regulation

- Key Result 2 - 85% of inspections this financial year were triggered by risk. Risk can be defined as either ‘Inherent Risk’ and ‘New and emerging risk’. ‘Inherent risk’ inspections are at services that our intelligence suggests there is a risk, or it may be in relation to a previous rating or having never been inspected previously. ‘New and emerging risks’ are where we receive information of concern, perhaps via the public or a staff member of a service speaking up, and we use this information to trigger an inspection.
- Key Result 5 - In the previous financial year 9.2% of inspections were undertaken out of hours. Up to the end of July 2023 10.2% of site visits were out of hours. There is a continued focus on the importance of out of hours inspections and ensuring that we have the policies and procedures internally to support this moving forward.
- Key Result 7 - 28.7% of registration applications within our system are over 10 weeks old. This has increased from last financial year, however we have also had a 7.8% increase in the volume of applications received. We monitor this volume as it is important that we offer a timely registration service.

Safety through learning

- Key Result 1 - In Q1, we received 66 complaints of which 41 were taken forward. Our Key Performance Indicator (KPI) for acknowledging complaints within 3 working days is 90%. In Q1 the complaints team achieved 98%.
- Key Result 3 - In May 2023 our most recent Pulse Survey was launched. As part of this survey, we have asked colleagues ‘I feel it is safe to challenge the way things are done here’. 29% of colleagues agreed or strongly disagreed with this question. Our initial aim is for our work and actions to increase this result to 51% which would bring us back to our result in September 2022.
- Key Result 4 - Of the 222 recommendations made to us, either internally or externally, 34.1% have a progress score. The tracking process is new for 2023/24 and we are confident of more timely and accurate updates as the process matures. There is a separate paper to board on the recommendations that were made as part of the Listening, Learning, Responding to Concerns review which has a greater progress score with 85.7% of recommendations with a status update.

Accelerating Improvement

Key Result 1 - In Q1 there were no major publications or reports published for us to monitor. As publications are due in July 2023, this key result we will be reported on for quarter two as we track the access to our major publications(Q2).

Our Milestones

As part of our business plan, as we proceed through a period of transformation, we have set a number of milestones within our business plan. Milestones are key achievements that are to be delivered across the financial year. We track the progress of each milestone on a quarterly basis.

Some of our milestones have interdependencies to our wider transformation, both in rolling out our single assessment framework, as well as our new regulatory platform. We’ve been successful in launching the Go Live 2 functionality for contact which implements the Regulatory platform for NCSC and operation colleagues to manage incoming information of concern. Further updates to this release, including notifications are in the final stages of build before testing and implementation. The design for all of the regulatory transformation components is virtually complete and build is over 50%. We continue to plan for an implementation to complete this financial year.

Finance

At the end of July, there is a £1.3m surplus on our revenue expenditure, however we are forecasting a £3.7m deficit for the financial year.

The forecast includes £1.9m of unfunded work supporting the Covid-19 inquiry with the remaining pressure driven by in year pay agreements which is being actively managed to mitigate.

Our capital budget is £1.8m overspent for the year to July and forecast to be £1.4m overspent for the end of the year. Current indications are this forecast overspend will increase further, with work underway to review.

Risk

There are two new short term risks proposed to be included within the risk register.

- Risk O5.1 – Siebel CRM recovery (New, sub risk of O5) This is a new risk in the light of the likely recovery time for one days’ loss of Siebel CRM being 6 days. This risk is owned by Anthony Snape. As more of our service is transferred to regulatory platform this risk will reduce and eventually will be not required.
- A new risk S9 is proposed: ‘The Healthcare Safety Investigation Branch maternity function transfer impact on capacity to deliver the change and our existing transformation objectives.’ Healthcare Safety Investigation Branch’s (HSIB’s) maternity programme will be hosted later this year by CQC. This will apply additional pressure to our resources and capacity to deliver our existing transformation and risk the transition of the HSIB functions being handled ineffectively. There is an increase in this risk due to a fixed deadline but the mitigations and actions for this risk are clear, and the project and delivery is not deemed at risk.

There is one change in risk scoring since the last update with board.
There is a risk that P3 (Our colleagues are insufficiently engaged in our culture change and ways of working). The proposal is for the residual risk to decrease from 25 to 20 (decrease in likelihood from 5 to 4). A culture change plan has been developed, with Kate Terroni as ET sponsor. The action plan has named owners and a timeline for delivery for each action covering the period Q3 of 2023/24 to Q3 of 2024/25.