No	Ref	Subject	Action Required	Owner	Date Raised	Date Due	Progress/ Comment	Date / Completed	Status
1	CM/07/23/23	Quarterly Assurance on People and Culture	The Board heard that job sharing data had not been an area of reporting focus. The Interim Chief Executive will check if this data was being captured and if so, this will be included in future reporting. If not being captured, we will start to do so and involve our Equality Networks in conversations around this.	Kate Terroni / Jackie Jackson	19/07/23	29/11/23	This would be reflected in the meeting’s report	29/11/23
2	CM/09/23/21	Update on Listening, Learning and Responding to Concerns review	Future reporting should continue with the granular assessment to demonstrate to people that we have done what we said we would do. A high-level qualitative assessment would also be helpful. The Director of Legal Services would take this forward.	Kate Staples	27/09/23	07/02/24
3	CM/09/23/22	Freedom to Speak up (FtSU)	Include learning and themes on why people feel it necessary to engage the speak up service as opposed to other forums within the organisation in the next update speak up update. The Speak up Guardian would take this forward.	Carolyn Jenkinson	27/09/23	25/09/24	This would be reflected in the next scheduled update to the Board.
4	CM/09/23/32	Corporate Performance report	Future reporting should exclude the use of the terms “monitor” and “on hold” as it would be more useful to have a sense of what good looked like and what we were trying to achieve. The Director of finance, commercial and workplace performance would take this forward.	Chris Usher	27/09/23	Ongoing	This would be reflected in future reporting.
5	CM/09/23/33	Pulse Survey Results	Further to the discussion it was agreed that the Board would be presented with the opportunity to comment on our values refresh at the November Board.	Kate Terroni / Jackie Jackson	27/09/23	29/11/23	This would be discussed at the 29 November Board
6	CM/09/23/35	National Complaints Team Report 2022/23	The Complaints team were asked to include in future reporting a formal “you said”, “we did” which would help in adding accountability to complaints handling.	Meeta Patel	27/09/23	Ongoing	The Complaints team would take this forward for future reporting

Status key:
Red - overdue
Green - on track
Blue - complete or propose to close.