PUBLIC BOARD MEETING

Date: 7th Feb 2024	CQC Public Board	Agenda item: 3.3 / Paper number: CM/24/02/33
Title of paper:	Learning Listening and Responding to Concerns (LLRC) Review - Update
Purpose of paper:	For discussion
Executive sponsor:	James Bullion
Presenter(s) or lead person:	Helen Rawlings
Summary: / To provide an update to CQC Board regarding the progress of the LLRC review / To present a current and forward view of work and outputs for the LLRC in the coming months / Recommendations: / The Board or Committee is asked to note and/or endorse an action underway. / Background / The LLRC review reported to board on 29th March 2023. In total the review delivered 84 recommendations which were all accepted. The Board agreed the management action plan on 24th May 2023. / In CQC public board on 27th September 2023 an update was given on progress against recommendations made. / All recommendations have been assigned a senior owner and delivery leads. There was an action agreed CM/09/23/21, ‘Future reporting should continue with the granular assessment to demonstrate to people that we have done what we said we would do. A high-level qualitative assessment would also be helpful. The Director of Legal Services would take this forward’. A further update on leadership of the LLRC review is given below. / In CQC public board on 29th November 2023 an update was given in the Executive Team report to CQC board. / Current progress / As of 23rd January 2024, the current progress against recommendations is represented in the performance dashboard at the end of this document. This demonstrates an improved position when compared to September 2023. / Five out of six workstreams contain recommendations with, ‘no progress to date’. Some of these recommendations are required to be addressed after other recommendations are completed and so the sequence of completion is important to consider. / Overall, the recommendations are categorised as follows: / met or almost met 16% / close to target 21% / moderate distance to target 28.4% / far from target 17.3% / no progress to date 16% / no status update 1.2% / Examples of work which has taken place since October 2023 in response to the recommendations from the LLRC review include: / Freedom to Speak Up (FTSU) month – Breaking Barriers / Freedom to Speak Up recruitment underway / CQC Senior Leadership training and development: Learning: Inclusion and Race / Inclusive Mentoring Scheme for 2024 / New policies on Code of Conduct and Dignity and Respect at Work / Publication of CQC 2023 Workforce Disability Equality Standard and Race Equality Standard reports together with action plans / Leadership, governance, and assurance / Executive leadership of the LLRC review is now with Regulatory Leadership under the direction of Chief Inspector of Adult Social Care and Integration. The Deputy Director of Integrated Care, Inequalities, and Improvement will provide ongoing leadership, oversight, and coordination of the responses to recommendations. / Responsibility for meeting the recommendations is with the senior owners and the CQC Executive Team. / The new Executive Team sub-committee – the Strategic Oversight, Prioritisation, and Improvement Committee (SOPIC) –which will provide oversight of the delivery of strategically aligned priorities, initiatives and programmes is now running. / The task and finish group focusing on the implementation of LLRC recommendations is running and as of January 2024 is receiving additional leadership support from the Deputy Director of Integrated Care, Inequalities, and Improvement. Together with the Head of Performance, reporting will go to the SOPIC. Leadership is also being provided to the ongoing evaluation process for the LLRC recommendations and communication and engagement updates across CQC. / Independent panel members / Following the publication of the LLRC review, it was recommended that CQC bring in the Independent Review Panel to receive their feedback on the progress of the evaluation and recommendation tracking. This supports the independent overview of CQC's progress. / CQC will now engage with all Independent Review Panel members and will work with them to receive feedback in line with the ongoing evaluation. / Evaluation / Evaluation of the LLRC review has been ongoing. This has included tracking completion of the recommendations, and work to understand the degree to which we have achieved the 10 aims set out in the review. / To evaluate the impact on CQC staff, the Staff Survey has included several questions designed for CQC to measure progress against the recommendations raised by the LLRC review. This survey is open for all staff to complete from 16 January – 6 February 2024. / We have also commissioned an independent research agency, SQW, to run focus groups and interviews with internal and external stakeholders to understand their experiences following changes made. In addition, we have built data collection into some of our core organisational processes, such as recruitment and the leaving well process, so we can see how we are performing on an ongoing basis. / A one year progress evaluation will be completed to report in May 2024 and a final evaluation report will come to Board in November 2024 (18 months report). This will include an overview of weather the response to the review has achieved the aims and identify why these have or have not been met. It will also include consideration of continuous improvement and ongoing evaluation of the work.
Governance: / CQC Executive Team and CQC Regulatory Leadership have considered this matter and receive regular updates on the LLRC review recommendation progress. / The reporting against the recommendations for the LLRC review reports into the Strategic Oversight, Prioritisation, and Improvement Committee (SOPIC) / There is further leadership support defined to support this work and progress against recommendations.
Strategy: / The response to the LLRC review shows continued commitment to the recommendations. The recommendations from the LLRC align with multiple elements of CQC strategy. It will deliver changes to experience and culture for both our internal CQC staff and externally for people who work with us, providers who we regulate and people who use and experience health and care services.
Finance: / There will be financial consideration for the ongoing completion of recommendations, evaluation and involvement of the independent panel members.
Risk: / There is a reputational risk to CQC if recommendations are not met. / There is a risk that the experience of people who work with us, our staff, those that we regulate, and people who use health and care services is not improved or gets worse if recommendations are not met. / The above risks are mitigated by the ongoing work to complete and embed recommendations form the LLRC review.
People: / A positive effect on workforce including the experience of our staff, equality, diversity and inclusion is expected as recommendations are met and embedded.

LLR Recommendations overview as of Sept 2023

LLR Recommendations overview as of January 2024