No	Ref	Subject	Action Required	Owner	Date Raised	Date Due	Progress/ Comment	Date / Completed	Status
2	CM/09/23/21	Update on Listening, Learning and Responding to Concerns review	Future reporting should continue with granular assessment to demonstrate to people that we have done what we said we would do. A high-level qualitative assessment would also be helpful. The Director of Legal Services would take this forward.	Kate Staples	27/09/23	07/02/24	This item is being presented at the February 2024 meeting.
3	CM/09/23/22	Freedom to Speak up (FtSU)	Include learning and themes on why people feel it necessary to engage the speak up service as opposed to other forums within the organisation in the next update speak up update. The Speak up Guardian would take this forward.	Carolyn Jenkinson	27/09/23	25/09/24	This will be reflected in the next scheduled update to the Board.
5	CM/09/23/33	Pulse Survey Results	Further to the discussion it was agreed that the Board would be presented with the opportunity to comment on our values refresh at the November Board.	Kate Terroni / Jackie Jackson	27/09/23	24/4/24	This will be discussed at Board following initial conversations with non-executives and the executive team around Spring 2024.
6	CM/09/23/35	National Complaints Team Report 2022/23	The Complaints team were asked to include in future reporting a formal “you said”, “we did” which would help in adding accountability to complaints handling.	Meeta Patel	27/09/23	Ongoing	The Complaints team will take this forward for future reporting

Status key:
Red - overdue
Green - on track
Blue - complete or propose to close.