PUBLIC BOARD MEETING

Date: 27 March 2024	Public Board Meeting	Agenda item: 3.2 / Paper number: CM/03/24/32
Title of Paper:	Culture Change/ Values Progress Report
Purpose of the Paper:	To note
Executive Sponsor:	Kate Terroni – Deputy Chief Executive
Accountable Director	Jackie Jackson – Director for People and Culture
Presenter(s) or lead person:	Jackie Jackson – Director for People and Culture
Summary: / This paper is intended to update on the progress made against our Culture Change Plan approved by the Board in October 2023. / In summary, good progress has been maintained against the actions and timescales presented in the Culture Plan and we are on target to present the recommended new values to the Board for approval in July 2024 / Recommendations: / The Board is asked to note and/or endorse the current culture activity that is underway.
Progress / Since Board approval of the Culture Change plan the focus has been on stage one of the plan specifically relating to the engagement of the organisation in identifying the values and associate priority behaviours, we require to deliver our Strategy. / Engagement with all colleagues is primarily being delivered through 2-hour workshops designed to direct colleagues to visualise the future where the single assessment framework is fully embedded and identify the priority values, they feel are required to deliver this consistently within our strategy. / We have now planned in all workshops including embedding these within Directorate conferences and events and with full attendance we anticipate the involvement of approximately 2500 colleagues. These workshops will cover all grades and there will be specific dedicated sessions for staff equality groups, staff forum and Trade Union groups. The value workshops are planned to run from March to May 2024. Board members are also planned to attend some of the Directorate Conferences therefore, they will be able to see this work progress and hear directly from colleagues on their thoughts on the future values and behaviours. / In support of this, a communications campaign has been launched in partnership with Internal Engagement, including a manager’s briefing pack that asks all our leaders to engage in conversations about our values within team meetings ahead of colleagues attending the workshops. This is intended to allow for local conversations regarding our values and ensure colleagues attending the workshops are prepared for the sessions. Briefings have been held with our leadership colleagues and Senior Leadership engagement will be continued through the Senior Leadership Group (SLT30) meetings. / We have also begun working with our Engagement and Policy and Strategy colleagues to gain insight and organisational learning from our external stakeholders, such as national professional organisations, care providers and Department of Health and Social Care. This engagement will seek views and insight on how our current values are received externally whilst looking to gain insight in relation to future values. At the time of writing, this engagement is in the process of being arranged, and an update on outcomes to date will be shared with the Board during the April Board Strategy Day. / Consultation with our Trade Unions has also begun, and the approach to refreshing the values was discussed at the Joint Negotiating and Consultation Committee (JNCC) on March 7th. Trade Union representatives expressed widespread support for this work. JNCC have requested a regular update on progress and agreed to promote this work with members. / Finally, the engagement of Board Members is ongoing, with 1-1 and group discussions on our future values currently being planned. The outputs of these will be collated and presented to the Board in the April Board Strategy Day for further discussion. / Appendix A below provides an overview of activity and timelines relating to stage one of the Culture Plan.
Governance: / This report provides a written update on our progress to the Board.
Strategy: / The culture plan was approved by ET and the Board in October 2023 and recognised as being essential to the delivery of our Strategy and the Single Assessment Framework.
Finance: / There are no financial considerations as part of this reporting.
Risk: There is a risk that colleagues will not have the space to engage with the workshops; however, this is being mitigated through incorporation into existing Directorate events where possible.
People: This programme highlights heavy engagement with colleagues, including staff representative groups.
Next Steps: Activity will progress as outlined above.

Appendix A – Culture Plan Stage One Timeline