PUBLIC BOARD MEETING

Date: 27 March 2024	Public Board Meeting	Agenda item: 4.2 / Paper number: CM/03/24/42
Title of Paper:	Independent Care (Education) Treatment Reviews (ICETR) Update
Purpose of the Paper:	For assurance
Executive Sponsor:	James Bullion, Chief Inspector of Adult Social Care and Integrated Care
Accountable Director:	Rebecca Bauers, Director of People with a Learning Disability and Autistic People
Presenter(s) or Lead Person:	Rebecca Bauers, Director of People with a Learning Disability and Autistic People / Helen Ferguson, Deputy Director of Delivery Unit
Summary: / This paper is to provide the Board with an overview of the current programme of activity underway in collaboration with NHSE on the delivery and relaunch of Independent Care (education) Treatment Reviews (ICETR’s). / ICETRs aim to reduce the use of long-term segregation (LTS) for people with a learning disability and autistic people. The reviews aim to ensure safe and effective care and treatment in the least restrictive setting and identify for individuals a clear plan for discharge and future care. The ICETR programme was initially co-led by NHSE and DHSC and was set up following CQC’s recommendation in the 2019 publication ‘Out of Sight, Who Cares?’ / The oversight panel, led by Baroness Hollins stated that CQC rather than DHSC should be asked to manage this programme, with an enhanced role for Mental Health Act Reviewers (MHARs). DHSC and NHSE jointly paused all ICETRs in March 2023. / Since the panels have been paused from March 2023, there is a backlog of 53 patients awaiting ICETRs. It must be noted that whilst Independent Panels have been paused since March 2023, Care (education) and Treatment Reviews (CETR) CETR’s continue to be held for those 53 patients in long term segregation and are undertaken by commissioners. / Care (Education) and Treatment Reviews (C(E)TRs) are part of NHS England’s commitment to transforming services for people of all ages with a learning disability and autistic people. C(E)TRs are for people who have been admitted to a mental health hospital or for people who are at risk of admission. They are undertaken by commissioners to ensure that people are only admitted to hospital when absolutely necessary and for the minimum amount of time possible. Care and Treatment Reviews (CTRs) are for adults and C(E)TRs are for children and young people. C(E)TRs are carried out by an independent panel of people. This includes an expert by experience, who is an autistic person or a person with a learning disability or a family carer with lived experience of services. The panel also includes a clinical expert who is qualified to work in healthcare and the commissioner who pays for the person’s care. / CQC submitted a business case to DHSC setting out a future model for ICETRs via grant in aid of approx. £1.67million for a CQC led programme, working jointly with NHSE in year 1, and a fully CQC led model in year 2. Regulatory Leadership have governance and oversight of the ICETR work programme, and this began in December 2024 following receipt of funds by DHSC. / A clear Memorandum of Understanding (MOU) has been agreed and reporting processes are in place to meet the requirements of the MOU between CQC, DHSC and NHS(e). The first year jointly with NHSE, setting the direction of activity including the recruitment of specialist MHAR chairs and outcomes for people to ensure all people currently in long term segregation (LTS) have at least one ICETR by December 2025. Recruitment is close to completion to ensure panels will be stood up from May 2024 with a clear trajectory to complete the backlog of 53 within year 1 which we will report on quarterly. The expected outcome for people and patients is that they will be able to be discharged from restrictive hospital settings into more suitable models of care to enable them to have better quality of life. / In terms of reporting progress and outcomes for people, we will provide an update in the Annual Mental Health Act Review report as we did last year and we will set up an external oversight panel from Sept 2024 that will be co-chaired by a person with lived experience to inform our independent voice publication after completion of the two-year programme. / Recommendations: / The Board is asked to note and/or endorse an action underway.
Governance: / ET, March 2023, paper provided relating to the future model for ICETRs / ET, November 2023, briefing note provided for information relating to Baroness Hollins final report on ICETRs and recommendations relating to CQC - approved both the business case, methodology, and delivery through regulatory leadership and national MHA Team / Regulatory Leadership Board, November 2023, overview provided of ICETRs / People and Culture Committee, November 2023, approval gained to agree a structure, (as already costed and funding approved by DHSC). Also, to agree to the start of recruitment and modelling of the programme leading to the appointment of various fixed-term roles to set up and deliver this programme. / ET, December 2023 / ET, February 2024 - update and assurance given on progress since funds received in December 2023
Strategy: / People and communities / Regulation that’s driven by people’s needs and experiences, focusing on what’s important to people and communities when they access, use, and move between services. / Safety through learning / Regulating for stronger safety cultures across health and care, prioritising learning and improvement and collaborating to value everyone’s perspectives. / Running through each theme are two core ambitions: / Assessing local systems / Providing independent assurance to the public of the quality of care in their area. / Tackling inequalities in health and care / Pushing for equality of access, experiences and outcomes from health and social care services.
Finance: / The 2-year ICETR programme will be fully funded by DHSC via grant in aid of approx. £1.67million, working jointly with NHSE in year 1, and a fully CQC led model in year 2. Funding was received in December 2023. / Format for quarterly returns discussed and agreed with DHSC finance, CQC finance business partner and David Nuttall, DHSC. Returns to be submitted on the 28th of the month for each quarter with detailed costings planned to date. A dedicated cost centre has been aligned with this project to capture accurate spending.
Risk: / As the ICETRs are currently paused, there are now 53 people with a learning disability and/or autism, in long term segregation, 53 people are awaiting a review, as well as additionally identified people requiring review, which may be detrimental to their safety, care and treatment the longer they are delayed and people remaining in long term segregation longer than necessary. 7 NHSE regions continue to identify those requiring an ICETR on a 6-weekly cycle and CQC have engaged in these regional meetings since December 2024. / On the 8th of November 2023, DHSC published a response in relation to Baroness Hollins’ final report which includes a contribution from CQC. CQC had prepared a news story relating to our intention to deliver an in-house ICETR programme. This activity does not feature on our corporate risk register currently. CQCs responsibilities in the delivery of this programme of work is in the public domain, to avoid any reputational damage if there are significant delays to the set up and delivery of this work we would reconsider.
People: / As part of the programme, we have engaged with the following groups to support in the future delivery. / Policy and Strategy – we are working with Policy and Strategy to ensure support for all related deliverables. / Recruitment – Grant in Aid will support recruitment for the additional roles required to support the programme. Roles have been advertised internally and externally and in line with MOC redeployment policy. / Editorial – We have engaged with our Comms colleagues in early conversations and planning. A paper will be taken to the IV panel in the autumn of 2024 to align to our external oversight panel purpose and reported outcomes. / Public engagement – to support the development of methods to seek feedback from patients and their carers/family members from current internal resource. / Research and evaluation – Engagement is underway to support the development of a learning review and evaluation of the programme of work including the development of recommendations to inform continued improvement from current internal resource and managing performance. Our external oversight panel will feed into this work that will be co-chaired by a person with lived experience. / Data & insight – We have agreed leads for Statutory Reporting/Strategic Insight and Data Architecture / Equality, Diversity and Inclusion – An Equality Impact Assessment has been completed and approved by the Head of Inequalities and Human Rights.