No	Ref	Subject	Action Required	Owner	Meeting Date	Date Due	Progress / Comment	Date / Completed	Status
1		Learning Listening and Responding to Concerns Review - Update	Priorities from the 84 LLRC recommendations are to be mapped out showing delivery over the next 3, 6 and 9 months so the Board can track progress.	James Bullion	07/02/24	22/05/24	Priority mapping and delivery will be addressed at the LLRC Evaluation update scheduled for the Private Board
2		Ofsted – Learning from our external environment	An update would come to the Public Board in 6 months (September) in relation to providers’ experience following the roll out of the SAF.	Joyce Frederick	07/02/24	25/09/24

Status key:
- Red – overdue
- Geen - on track
- Blue – Complete or propose to close