APPENDIX 1: Current Status of Equality Objective Deliverables

Table 1 (key)		Year 2 - January 2023	Year 3 - January 2024
Red	Successful delivery appears to be unachievable.	0	2
Amber and Amber *	Successful delivery feasible. However, management attention is required to resolve critical issues. (Amber * denotes impact of transformation delay)	12	14
Green	On track for time, cost and quality	9	8
Not started yet		0	0
Total		21	24

Notes:
- EO5 is reported on separately within the Quarterly People and Culture assurance report. To allow for comparison, we have removed the EO5 indicators from year 2 in this table.
- Ratings are presented using a three-point scale. Previous Amber-Red and Amber-Green ratings have been updated / converted to Amber ratings to allow for comparison.
- Some statuses may change pending delivery of work in Q4.

Table 2: Equality Objectives: 2023/24 deliverables

Equality Objective	Amplifying the voices of people more likely to have a poorer experience of care or have difficulty accessing care	RAG rating 2023/24	Overall	Comment
	a. All local teams have local inequalities outreach plans established, enabling targeted evidence gathering from people more likely to have poor access, experience and outcomes	Amber*	Amber↓	EO1 progress is rated Amber; lower than last year 2022/23 (Green). / Equality monitoring is necessary to amplify the voices of people who are more likely to face inequality. The inability to achieve implementation of equality monitoring continues to be a major ongoing risk to EO1 and EO2 both this year and for our 4-year objectives overall.
	b. We have established equality monitoring in Give Feedback on Care	Red
	c. We have piloted and evaluated equality and human rights reflective practice for local teams	Green
	d. We have plans in place for an initial evaluation of the new model to answer the question “How much is the people's experience category influencing regulatory action on inequalities?”	Amber*
	e. We have undertaken research with people more likely to have poor access, experience or outcomes from care about their experience of contacting us	Amber
	f. We have built our focus on people more likely to have poor access, experience or outcomes from care through public engagement activity such as targeted awareness campaigns and partnerships with voluntary and community sector organisations.	Green

Equality Objective	2. Using data to understand and respond to equality risks	RAG rating 2023/24	Overall	Comment
	a. We have started collecting provider equality monitoring at point of registration and have assessed use of other data for provider equality monitoring as an interim measure	Red	Red ↓	EO2 progress is rated Amber; similar to progress made in the previous year 2022/23 (Amber). / Equality monitoring ad mitigation of bias are key to understanding and responding to equality risks - and represent ongoing risks to achieving EO2 both this year and for our 4-year objectives overall (and LLR). / We have therefore limited the overall EO2 rating to Red to reflect this.
	b. Equality and health inequalities data is in place in our data profiles for relevant quality statements where data is available	Amber
	c. We have delivered work on agreed priorities to ensure we can make best use of the data we hold to understand equality risks	Amber
	d. We have plans in place for the mitigation of any risks of bias in our risk stratification approach	Amber
	e. We have developed our use of qualitative data to understand equality risks, for example relating to staff experience of equality and innovation to reduce health inequalities	Amber
	f. We have worked with others to develop national metrics for the Accessible Information Standard	Green

Equality Objective	3. Working with others to improve equality of access, experience and outcomes	RAG rating 2023/24	Overall	Comment
	a. We have initiated and developed a shared statement and commitment to tackling health inequalities across Arm’s Length Bodies, in collaboration with NHSE and NICE	Amber	Amber↓	EO3 progress is rated Amber, lower than last year 2022/23 (Green). / There has been progress on joint working with the Equality and Human Rights Commission and with NHSE on the Accessible Information Standard and the Patient Carer Race Equality Framework. / To meet EO3, a greater focus on the Women’s Health strategy and updating our position following RHO recommendations could be prioritised in Q4.
	b. Our work on the Sexual Safety Improvement Coalition and Accessible Information Standard (AIS) Improvement Coalition have driven improvement	Amber
	c. We have initiated one other Improvement Coalition – at present considering a coalition looking at improving workforce equality in adult social care with a focus on internationally recruited staff	Amber*
	d. We have delivered a joint action plan with the Equality and Human Rights Commission and partnered with other bodies on reducing inequalities through MOUs and Joint Working Protocols	Amber
	e. We have contributed to the delivery of Women’s Health Strategy and aligned our work with Race and Health Observatory on areas of joint interest	Amber
	f. We have taken opportunities to embed equality and human rights into joint inspections	Green

Equality Objective	4. Using our independent voice to reduce inequalities	RAG rating 2023/24	Overall	Comment
	a. We use our research contracts to deepen our understanding of work required to tackle inequalities and publish research findings on “what works in ICS tackling inequalities in local areas” and “reducing inequalities for people with dementia in adult social care” to drive improvement	Green	Green→	EO4 progress is rated Green, similar to the previous year, 2022/23 (Green). / This is due to advancements in ICS assessments, a stronger focus on inequality within independent voice pieces and research projects aimed at tackling inequalities. / To meet EO4, targeted messaging around inequalities and to reach diverse audiences groups could be prioritised in Q4.
	b. All ICS assessments will review and comment on equity in access, experience and outcomes	Green
	c. We consider inequalities in all our Independent Voice work and our approach to prioritisation of Independent Voice embeds a focus on inequalities	Green
	d. We have explored the use of findings from nationally set priorities for local inequalities outreach in independent voice work	Amber*
	e. We have published equality-focused national findings to lever improvement, for example sickle cell crisis pain relief in NHS trusts and following up equity in maternity reviews	Green
	f. Work collaboratively with engagement colleagues to ensure that any new or significant work on inequalities intended for an external audience is appropriately supported by targeted communications activity across a range of platforms, with consideration given to how to reach diverse audience groups and targeted messaging around inequalities.	Amber

Equality Objective	5. Our inclusive future: delivering on our workforce diversity and inclusion strategy	RAG rating 2023/24	Overall	Comment
	EO5: We aim to continue our transparency, reporting on our People Equality objective within our Quarterly People and Culture assurance report to the Board. This will capture our race and disability equity annual work (WRES/WDES).