PUBLIC BOARD

Date:	26th March 2025	Agenda item: 2.2 / Paper number: CM/03/25/22
Title of paper:	Priorities Programme Update
Purpose of paper:	For discussion
Executive sponsor:	Sir Julian Hartley, Chief Executive
Accountable Director:	Sir Julian Hartley, Chief Executive
Presenter(s) or lead person:	Sir Julian Hartley, Chief Executive
Summary: / This paper provides an update on the key organisational priorities for board assurance and discussion. Board is asked to discuss the Immediate Actions (IAs) and Foundational Improvements (FIs) and are invited to comment on progress.

Supporting information is available in Appendix A.

Immediate actions

Assessments that are stuck in the Regulatory Platform (RP):
Colleagues have taken action to reduce the number of assessments that are ‘stuck’ in the RP. As of 10 March 2025, 135 (out of 500) assessments remain ‘stuck’, and we are focused on reducing this number to zero.

Enabling New Assessments:
- It is imperative that we increase the number of assessments we carry out each month so that the public have a true picture of the quality of care.
- A number of workstreams continue to make progress to enable CQC to complete more assessments, including the hybrid approach using a modified way of working on the RP.

Information of Concern Cases (IoC) and Notifications Backlog:
- Work to reduce the backlog has progressed. The IoC backlog has reduced to 286 as of 10 March 2025, from a peak of 1,984 on the 9 January 2025.
- Supported by expert clinical resource from the NHS, colleagues are reviewing ways of working to strengthen the end-to-end process and improve operating procedures to help prevent a backlog from reoccurring.

Registration:
Registration Applications have been transferred back to CRM due to the issues with the RP. Colleagues have made progress in addressing the backlog of applications over 10 weeks old in the system. It has reduced to 29.6% as of 10 March 2025 from a peak in May 2024 of 61.6% and there are now no applications from 2023 present in the system.

Foundational Improvements

Integration of Operations and Regulatory Leadership:
- Work continues on reviewing the Operational Structures in place. Evaluation of the Operations Manager Pilot is underway.
- The Inspector/Assessor role change work has entered the consultation phase with a plan and timeline agreed upon in collective consultation with Trade Unions and communicated to all colleagues through briefing calls, written communications, and supporting documents.

Assessment Framework:
Based on recommendations and feedback, the Assessment policy and methodology will be revised. Planned changes will be consulted upon and interim measures will be implemented in the coming months.

Technology and IT systems and Data, Ratings, and the Register:
Building on the recommendations from the independent reviews and the known data quality and consistency challenges, a structured approach to prioritise and sequence system and data changes is in progress and will be aligned to planned changes in other priority areas.

Programme Infrastructure

The programme structure is implemented to enable the delivery of the Immediate Actions and Foundational Improvements. The infrastructure is there to:
- Drive delivery (against targets/timescales)
- Set out clear accountability and responsibility
- Manage interdependencies
- Ensure controls can be applied effectively.