No	Ref	Subject	Action Required	Owner	Meeting Date	Date Due	Progress / Comment	Date / Completed	Status
1	CM/11/24/52	Response to Ofsted Inquest – Protecting CQC colleague and Provider Welfare - Learning Resources	The paper was due to be presented to the Board in November 2024 but was deferred for consideration at the March meeting.	Chris Dzikiti	27/11/24	24/09/25	For consideration at the September meeting	Deferred to Sept. 2025
2	CM/09/24/24	WRES & WDES Report and Action Plan	JJ and NR to conduct a detailed examination of policies and procedures, outlining actions necessary to bring about significant change in Equality, Diversity, and Inclusion.	Jackie Jackson	25/09/24			All policies and procedures will be reviewed in line with the CQC Way / Propose to close.
3	CM/09/24/41	National maternity inspection end of programme report and supporting improvement resource	CD to evaluate in 12 months, whether this initiative has led to any positive outcomes.	Chris Day	25/09/24		This is a live issue. We recognise the scale of the challenges faced within the Maternity sector.	Propose to close.
5	CM/03/25/32	Q3 Performance Report Update	There were two main areas of concern with regard to achieving performance targets. These were in the areas of Freedom of Information requests and MNSI investigations. The Board requested a deep dive into these areas to discover the reasons behind the dropping performance in these areas in the next quarterly report.	FOI – Chris Usher / MNSI – Toli Onon	26/03/25	24/09/25	To be presented at the September Board Meeting as part of the End of 2025/26 / Quarter 1 Report
6	CM/03/25/32	Q3 Performance Report Update	Reliable insights on staff sentiment should be reintegrated into performance reporting to ensure the Board understands how colleagues are feeling.	Jackie Jackson/ / Suzanne Kirwan	26/03/25		There is a piece of work with Data & Information to look at how we undertake our employee sentiment moving forward, as part of this work we will factor in the reporting requirements to board. / Propose to Close
7	CM/03/25/34	Quarterly People and Culture Assurance Report	The Board welcomed the report and asked for it to be extended to cover other areas including: / Distribution of vouchers by race as well as by disability. / Higher stress related sickness levels in those with protected characteristics, and the potential under-reporting of stress. This could be due to people with long-term health conditions being adversely affected by stress but being recorded by the health condition rather than stress. / Disparity between statistics showing 10% of the workforce having at least 1 month of sickness absence in a 6-month period, against only 4% on long-term sick. An explanation of the reasons for this.	Jackie Jackson	26/03/25	24/09/25	A review is being carried out of all the People related performance stats and metrics. An update will be provided to Board in September.
8	CM/03/25/35	Mandatory Learning Update	Consideration to be given to the effectiveness of the mandatory training currently provided to staff. / This report should always be brought to Board at the same time as the Quarterly People & Culture report.	Jackie Jackson	26/03/25		Mandatory Learning will be included in the Quarterly Reports in future. / Propose to Close.

Status key:
- Red – overdue
- Geen - on track
- Blue – Complete or propose to close