CQC PUBLIC BOARD

Date:	25th June 2025	Agenda item: 3.1 / Paper number: CM/06/25/31
Title of paper:	Priorities Programme Update
Purpose of paper:	For discussion
Executive sponsor:	Julian Hartley, Chief Executive
Accountable Director:	Suzanne Kirwan, Director of Performance and Delivery
Presenter(s) or lead person:	Julian Hartley, Chief Executive & Suzanne Kirwan, Director of Performance and Delivery
Summary: / This paper provides an update on the programme established to deliver on the CQC’s key organisational priorities for CQC Board assurance and discussion. / Supporting information is available in Appendix A. / Recommendations: / The Board is asked to discuss the Immediate Actions (IAs) and Foundational Improvements (FIs) and is invited to comment on progress. / Immediate Actions / Assessments that are stuck in the Regulatory Platform (RP): / As of 8th June, 20 (out of 500) assessments remain ‘stuck’, colleagues remain focused on reducing this, noting that some are currently subject to legal discussions. CQC has contacted impacted providers and apologised for delays in the completion and publication of the assessments. / Enabling New Assessments: / CQC is targeting 9000 assessments by September 2026. There has been an overall increase in the volume of assessments completed: in May 2025 colleagues completed 465 assessments compared to 319 in December 2024. / Colleagues continue to operate the interim assessment approaches (Hybrid and Location Assessment Plans). / Information of Concern Cases (IoC) and Notifications Backlog: / The backlog of 5000 IoC cases based on the static cut of the data reported to the January Health and Social Care Select Committee has been cleared. / To further strengthen assurance and ensure that the most serious priority cases are acted on without delay new targets and KPIs have been updated. / Registration: / The percentage of Registration Applications over 10 weeks old in the system is 35.2% as of 9th June. / Registration Teams continue to work on clearing the backlog so that new providers can start delivering services and help more people access the care they need, focusing on the oldest applications first. / Foundational Improvements / Technology and IT Systems and Data, Ratings, and the Register: / Colleagues were invited to provide feedback on a high-level Technology, Data, and Insight Roadmap. The roadmap showed key activities and proposed timelines to implement the changes required to rectify the digital challenges CQC faces, including the development of applications on the Regulatory Platform. Feedback is being analysed and will be built into the programme’s overarching plan. / Co-design of CQC’s shared data strategy is underway and improvements are being implemented to the current data provision across the organisation. / Integration of Operations and Regulatory Leadership: / All four Chief Inspectors have been recruited. / The Inspector/Assessor role change was completed on 12th May. There is now a single Inspector role within CQC. Any recruitment to Inspector roles, since the beginning of the year, now has the requirement for sector experience as an ‘essential criteria’. / Review of the Operational Structures in place continues, including transitioning inspection teams and leadership structures to sector-specific. / Assessment Framework / From April through to July, the Policy Team will complete a series of provider roadshows to examine core aspects of CQC’s regulatory approach. These sessions are an opportunity for providers to support the development of a new CQC handbook and set of ratings characteristics, as well as the development of changes to CQC’s assessment approach. / Plans are in development for further engagement and testing of key areas of the Assessment Approach, ahead of formal consultation later this year. / Our purpose and values / In February 2025, CQC commenced a foundational piece of work to build a new collective vision for what good quality regulation looks and feels like. As part of this work, CQC brought together over 2,500 colleagues, providers, public representatives, and wider stakeholders through a series of events to agree on what the vision should be and how CQC moves from its current position to where it needs to be as a regulator. / This work will be launching internally in July, with further information and integration throughout the summer.
Governance: There are no formal governance matters arising from this paper. The update provides assurance to the Board.
Strategy: This Priorities Programme will enable CQC to improve its performance and support the realisation of the proposed measures contained within the 2025/2026 business plan.
Finance: In line with HM Treasury Green Book standards, the programme is developing a business case. This paper itself has no financial considerations.
Risk: Risk management within the programme is lined to Corporate and Portfolio Risks Frameworks.
People: There are no people considerations in this paper. Each project/initiative will take into consideration workforce, equality, diversity, and inclusion matters throughout delivery.