No	Ref	Subject	Action Required	Owner	Meeting Date	Date Due	Progress / Comment	Date / Completed	Status
1	CM/11/24/52	Response to Ofsted Inquest – Protecting CQC colleague and Provider Welfare - Learning Resources	The paper was due to be presented to the Board in November 2024 but was deferred for consideration at the March meeting.	Chris Dzikiti	27/11/24	24/09/25	For consideration at the November 2025 meeting	Deferred to Nov. 2025
2	CM/06/25/32	Draft Business Plan	To add baseline figures to the performance metrics to demonstrate current position.	Chris Usher	25/06/25	24/09/25	Update Required / Email to EP / 16/09/25	Confirmation of completion 17/09/2025 / Propose to Close
3	CM/06/25/32	Draft Business Plan	Amend the following metric % of providers who have positive sentiment on ‘the new portal is an improvement on the previous portal’.	Esther Provins	25/06/25	24/09/25		Propose to Close / As Technology Roadmap develops and timeline for changes to the portal are clear a new measure will be proposed to Board to measure the success of the portal. Propose this metric be closed.
4	CM/06/25/34	Dementia Strategy & Independent Voice	Submit workplan to ET for approval. Aim to release final statutory guidance during Dementia Action Week in May 2026.	Chris Badger / Stefan Kallee/ / Jo Wallace	25/06/25	May 2026	Check status in May 2026

Status key:
- Red – overdue
- Geen - on track
- Blue – Complete or propose to close