# Action plan 2025 to 2026
## Foster inclusion and belonging for our colleagues
Action(s)	Start date	Target End Date	Delivery Lead	Status/Priority	Notes
Develop new Terms of Reference for EDI Co-ordinators, including their role in governance and directorate representation.	Q2 2024	Q3 2025	Inclusion and Wellbeing	Priority in progress	Facilitates CQC Way, EDI objectives at a directorate level and feedback culture
Executive Leaders to collaborate with EDI Co-ordinators, localising the strategy using directorate-level People Survey data, embedding feedback mechanisms, implementing ‘Connect with Me Time’, and reviewing progress regularly.	2025	Q3 2025	Inclusion and Wellbeing	Priority	Linked to action 1
Update 2023 Terms of Reference for Equality Networks and Executive Sponsors, including a fair appointments process for Chairs and their Committees, and strengthened Director engagement alongside Sponsor roles.	Q2 2024	Q4 2025/26	Inclusion and Wellbeing	Started in September
Refresh the Equality Network guidance to support effective network management and empower Chairs in their roles.	Q2 2024	Q4 2025/266	Inclusion and Wellbeing		Sequencing based on ToR and new ET Sponsor alignment
Provide training for Equality Network Chairs and Executive Sponsors, building on the 2023 Chairs’ external training programme.	Q1 2025	Q1 2026	Inclusion and Wellbeing		Sequencing based on ToR and new ET Sponsor alignment
Review Employee Staff Forum and Joint Network Voice frameworks; establish a joint Employee Voice advisory group with executive participation if it improves effectiveness.	Q4 2024	Q1 2026	Inclusion and Wellbeing		Sequencing based on ToR and new ET Sponsor alignment
Review current learning and develop evidence-based, academically sound anti-racism training; collaborating with the Race Equality Network to enhance mental health and wellbeing support.	Q1 2024	Q2 2026	Learning and OD	Priority in progress	E- Learning complete Q2 2025 / Workshops 2025-2026
Publish guidance to support the Workplace Adjustments Policy.	N/A	Q2 2025	Inclusion and Wellbeing	Complete	LLRC delivery, promote to embed with wider WA package
Develop an application to digitise the Workplace Adjustments Passport, supporting business planning and management inconsistency.		Q1 2026	Technology	Priority	LLRC delivery, / To agree new start date within Tech Road map
Raise awareness of job sharing and part time working, developing good practice with case studies.	Q1 2025	Q4 2025/6	Inclusion and Wellbeing		Work with CEN/DEN following ET Sponsor alignment to support achieving Disability Confident Leader Level 3 and Carers Confident Level 2. / Build on 2024 SLT 30 communications and events to role model different backgrounds.
Launch an Inclusive Mentoring programme for disabled and ethnic minority colleagues, with formal recognition in professional development	Q1 2024	Q4 2025/2026	Learning and OD	Priority in progress
Collect maternity returner data to inform updates to maternity, paternity and parental leave policies, aligning with new legislation and guidance	Q3 2025	Q2 2026	People Policy	In progress
Develop a new Trans, Non-Binary, and Gender Diverse Policy	Q4 2024	Q4 2025/2026	People Policy	Priority in progress	Supports work responding to Supreme Court ruling, publication affected by EHRC and DHSC guidance being published following ruling
Review and improve our Overseas Assignments Policy approach	Q2	Q4 2025/2026	People Employment Practice	Priority in progress	2025 Carers Week and 2024 CEN feedback
Refresh Equalities, Human Rights, Diversity and Inclusion e-learning, expanding to a comprehensive offer for all protected characteristic inclusion, further to bullying, harassment and discrimination learning and QI learning to embed the CQC Way behaviours. Bring together 2025 anti-racism and bullying, harassment mandatory e-learning, ensuring tailored content for leadership and managers through the CQC Way Leadership Strategy and improving the Successful Manager Programme.	Q3 2025	Q1 2026	Learning and OD	Priority to start	Iterated from 2024-2025 plan actions; develop learning on workplace adjustments, develop LGBT+ learning to compliment the new policy.
Executive Grades to implement meaningful EDI objectives, with a directorate focus and ensure alignment with the anti-racism approach.	Q4 2025/26	Q1 2026	Inclusion and Wellbeing	Priority	Follows Performance refresh with CQC Way

## Recruit talented colleagues
Action(s)	Start date	Target End Date	Delivery Lead	Status/Priority	Notes
Implement recruitment improvements and use a communications campaign to close the feedback loop on key areas. / Continue collaboration with Equality Networks and focus on improving adverse impacts for ethnic minority candidates based on data, considering data outcomes for other protected characteristics groups. / A plan with timelines for regular reporting to the People and Culture Committee will be used.	Q1 2025	2026	Resourcing	Priority in progress	See paused 2024-2025 recruitment actions to inform improvements
Embed a bi-monthly SLT review of recruitment, promotion, and succession planning focused on equity and diversity to address gaps and achieve representation, promotion, and retention goals for underrepresented groups, supporting the work in recruitment to improve ethnic minority outcomes. / This should align with EDI objectives at a directorate level which will also focus on inclusion metrics, e.g. bullying, discrimination.	Q2 2024	Q4 2025/26	Strategic / People Business Partners	Priority in progress- pilot in Tech, Data and Insights to support org-wide establishment	Iterated 2024-2025 plan action; / Regular review of data and actions at Directorate, Executive and Board levels to assess and enable publication of progress, this will include WRES, WDES, Development of targeted action using improved data.
Explore monitoring appointments against flexible working adverts and recruitment adjustments to refine approach.	Q4 2025	Q4 2025/26	Resourcing		New

## Invest in our colleagues
Action(s)	Start Date	Target End Date	Delivery Lead	Status/Priority	Notes
Embed a bi-monthly SLT review of participation in L&D programmes and high-visibility opportunities, e.g. projects, Committee attendance and deputisation, to ensure equitable access and develop diverse talent for senior roles, focusing on ethnic minority, disabled, and other underrepresented groups. / This will support ILP cohort 1 with development plans and preparing for succession planning, as well as monitoring promotion rates. / This should align with EDI objectives at a directorate level which will also focus on inclusion metrics, e.g. bullying, discrimination as well and compliments recruitment action 2 above.	Q1 2024	Q4 2025/26	Strategic People Business Partners	Priority in progress- pilot in Tech, Data and Insights to support org-wide establishment	Iterated 2024-2025 action wording; monitoring and reviewing Executive sponsorship impact for top talent through activities like mock interviews, application reviews, and sub-committee involvement. Consider creating a roster of Executives for these support roles.
Promote career monitoring for Inclusive Mentoring programme participants, monitoring uptake by grade and characteristics, and against promotions.	Q3 2025	Q4 2025/26	Learning and OD	Priority to start	New
Refresh the Talent and Performance frameworks. As part of this, agree an overall CQC promotion goal.	Q3/4 2025	Q1 2026	Learning and OD	Priority to start	New, CQC Way work connected and see paused actions to inform refresh. Align with Apprenticeships
Launch the Future Leaders programme with ringfenced places for underrepresented colleague groups.	Q3 2025	Q1 2026	Learning and OD	Priority to start	New, development programme, separate to 2024 SMP
Launch Inclusive Leadership Pathway cohort 2 for disabled and ethnic minority colleagues.	Q2 2025	Q4 2025/2026	Learning and OD	Priority in progress
Deliver cohorts 4-5 Successful Manager Programme, reporting to People and Culture Committee on progress quarterly and ensuring cohorts 1-3 complete all learning including new inclusive communications learning developed to action survey bullying behaviours.	2024	Q4 2025/2026	Learning and OD	Priority in progress	Iterated following 2024 launch, supports inclusive manager upskilling, includes HR Advice and Guidance drop ins based on feedback
Develop a Leadership Strategy following an external review. A single set of unified, core leadership and management standards for managers will be developed with accompanying training.	Q1 2024	2026	Learning and OD	Priority to start	Review timeline and content as part of CQC Way activities to embed Values and equalities learning, supports EDI objectives

# Action plan 2024 to 2025 Paused
## Foster inclusion and belonging for our colleagues
Action(s)	Start date	Reason
Evaluate impact of 2024 Dignity and Respect at Work and Code of Conduct Policy publication and raise awareness during Anti-Bullying Week in November. / Develop signposting guidance, making clear the connection with Freedom to Speak Up. As part of this, explore refreshing Dignity at Work Advisors, how we use data anonymously from Employee Voice representative groups and comprehensive support for individuals who report bullying, harassment, discrimination, and victimisation.	Q4 2025	In progress through FTSU review / Paused until after FTSU review
Develop an Equity, Diversity, and Inclusion policy.	Q1 2025	Values, FTSU, learning are priorities
Explore submission of Times Top 50 Employers for Gender Equality Index, which will also support our Women in Technology activity.	Q3 2025	Not a GEN priority
Explore future participation with the Neurodiversity Index.	Q4 2025	Focus on DCL Level 3 by 2027

## Recruit talented colleagues
Action(s)	Start date	Reason
Board and senior manager grades understanding of progress towards race and disability equality included as an essential criterion in job descriptions.	2025	Review as part of Recruitment improvements plan and leaders learning timeline
Develop an internal register for job-sharing partners and use a campaign to show visible role models.	Q4 2024-2025	Review as part of Recruitment improvements plan
Develop an alumni register of Top Talent so hiring managers can contact with job opportunities.	Q3 2025	Review as part of Talent refresh timeline * Move to Talent action in future
Improve exit data for targeted actions by Directorates, ensuring any agreed new questions are included on Menopause, Social Mobility, Disability sub-groups, Gender identity, Mental Health, and Wellbeing.	Q3 2025	Review as part of Recruitment improvements plan
Start to monitor Social Economic Background for recruitment and representation for targeted interventions.	Q3 2024	Review as part of Recruitment improvements plan for another #Countmeincampaign

## Invest in our colleagues
Action(s)	Start date	Reason
Use the DHSC’s Arm’s Length Bodies Talent Management Group to build leadership capacity and capability, vacancy sharing and learning and development opportunities.	Q1 2025	DHSC paused
Embed weekly protected time for learning and development (including on inclusion) that is recorded in Personal Development Plans and reported on at Directorate level. / Increase engagement with different colleagues by implementing networking opportunities, such as “coffee calls”.	Q2 2024	Review as part of Talent refresh timeline
Develop Outstanding People Awards, e.g. Outstanding Executive, Outstanding Network, Outstanding leaders. / Promote Reward and Recognition to improve micro affirmations.	Q4 2025/26	Review as part of CQC Way activities timeline
Publish Ethnicity Gap report intersectional with Gender Pay Gap report to inform development of actions. Govt contingent	2025	Govt publishing new guidelines
Develop ‘stay interviews’ (an alternative to ‘exit interviews’) for managers to undertake, providing safe spaces and opportunities to feedback on career experiences. These can be an opportunity to improve ability to talk about race and disabilities. / Conduct interviews for colleagues promoted internally by grades to determine the routes leading to progression, e.g., was it more often by informal routes such as recommendation or being given a high-profile project- track by and race and disability how work that leads to promotions is allocated.	Q4 2025-2026	Review as part of Talent refresh timeline
Develop an audit to review who is accessing prestige level training or development, and what is the progression journey for colleagues after accessing training or development opportunities.	Q4 2025-2026	Review as part of Talent refresh timeline

# Action plan 2024 to 2025 Completed
## Foster inclusion and belonging for our colleagues

1. Refresh People Policies with communication plans, ensuring there is a process to review the impact and update accordingly. Equality impact assessments should be completed and refreshed based on policy feedback to ensure they are supportive and accessible by all colleagues. Key completed to support below- Critical Illness, Flexible Working, Freedom to Speak Up (LLRC),
2. Launch and promote the Menopause and Hormonal Change Policy.
3. Sign the Menopause Workplace Pledge.
4. Refresh our Workplace Adjustments Policy and develop a Workplace Adjustments library. Introduce specialist support to facilitate application.
5. Introduce Workplace Passports.
6. Launch an Accessibility Hub in March 2024 and work with Academy to develop learning.
7. Published Accessibility Guidance.
8. Refresh the Lone Working Codes of Practice in preparation for The Worker Protection (Amendment of Equality Act 2010) Act 2023 update.
9. Publish new Prevention of Violence and Aggression at Work Codes of Practice to ensure no colleague experiences verbal or physical abuse at work, inside and outside CQC.
10. Publish Public Sector Equality Duty and Equality Impact Assessment guidance.
11. Implement a People Equalities communications calendar to promote understanding and allyship, for example, with speakers and Brave Spaces, co-ordinating with mental health and wellbeing activities.
12. Raise awareness of job sharing and part time working, developing good practice with case studies.
13. Refresh Values (CQC Way).
14. Launch Freedom to Speak Up e-learning. Introduce a new template to improve FTSU monitoring by diversity and triangulated with wider People data.
15. Strengthen e-learning with bullying, harassment, and discrimination training, ensuring a focus on protected characteristics and caring backgrounds. This may mean we develop best practice charters for email etiquette.
16. Include disability breakdown in People Survey and widen the question for adjustments, so a range of colleagues can answer for example, caring responsibilities.
17. Renew Carers Level 1 accreditation.
18. Complete Business Disability Forum Smart Audit to identify actions and help us achieve Disability Confident Leader (3).
19. Renew Disability Confident Level 2.
20. Evaluate and improve Employee Voice participation at Executive team sub committees and Board meetings.
## Recruit talented colleagues
1. External consultant review.
2. Evaluate Independent Panel Member intervention at shortlisting.
3. Promote and monitor flexible working in job adverts reporting at Executive and Directorate level
4. Publish a diversity data dashboard for all protected characteristics
5. Use a communications pan to improve Employee Service Records completion, including for sharing mental health conditions. Widen the records to include socio-economic background if possible.
## Invest in our colleagues
1. Monitor career trajectories for Cohort 1 of the Inclusive Leadership Pathway participants following completion.
2. Launch and evaluate Successful Manager Pathway Programme, ensuring managers are equipped to lead inclusively, foster psychological safety, manage challenging conversations, and apply People policies.
3. Monitor Talent framework, via the Senior Leadership and All Colleague Talent Reviews. Introduce Bi-annual Talent boards at Directorate, Executive team to moderate annual 9-box grids and succession plans and monitor colleague progress and development. Remuneration Committee will retain oversight for assurance.
4. Monitor Career conversations at all grades following campaign window.
5. Launch a suite of apprenticeship programmes.
6. Refresh corporate induction learning, ensuring awareness of our strategy, our work on culture and Employee Voice groups, such as our Equality Networks.
7. Publish Ethnicity Pay Gap report.
8. Comms Campaign with Leaders to highlight different role models for skills/experience/backgrounds.