PUBLIC BOARD MEETING

Date:	24 September 2025	Agenda item: 5.1 / Paper number: CM/09/25/51
Title of paper:	Independent care (education) and treatment review (ICETR) Update
Purpose of paper:	Update and for discussion
Executive sponsor:	Chris Badger Chief Inspector Adult Social Care and integration Care & Arun Chopra- Chief Inspector for Mental Health
Accountable Director:	Rebecca Bauers, Director for People with a Learning Disability and Autistic People
Presenter(s) or lead person:	Rebecca Bauers, Director for People with a Learning Disability and Autistic People

Summary: / The following paper provides Board with an update on current progress of the Independent Care (Education) and Treatment Reviews (IC(E)TR) work programme that began in December 2023 following receipt of GIA funds from the Department of Health and Social Care (DHSC). Now in its 3rd phase, this is the first time CQC have provided chairs (Mental Health Act Reviewers) and managed the programme. In the first 2 phases CQC supported DHSE appointed chairs with Mental Health Act Reviewers. / This request was made by the previous government’s health Minister, following Baroness Hollins’ publication My Heart Breaks – report into Long Term Segregation in November 2023. The programme is designed to enable an independent review of Long-Term Segregation (LTS) to make sure people with a learning disability and autistic people are safe and give clear, achievable recommendations about care, treatment, and discharge, to enable people to leave LTS and lead the lives they wish with the right support networks around them. CQC is using its powers under section 120 Mental Health Act to make recommendations and require an action plan in response. Following the IC(E)TR we consider whether there are any identified shortfalls in care that raise regulatory or human rights issues, for both the person and or that may be indicative of more systemic issue for the wider population group. These issues are shared with the inspection team for an appropriate regulatory response using the Health and Social Care Act. / Since beginning IC(E)TRs in May 2024, we have received positive feedback from supporters about their experiences. We will continue to seek feedback from people about their experience of the IC(E)TR and their supporters to understand the impact on their lives and the real difference it is making for them. We also seek to influence commissioning practice and to market shape. / The DHSC has included the required funding to extend the programme into its submission to the Treasury. Confirmation of the funds are needed to enable CQC to plan either a continuation of the programme or closure. DHSC have confirmed we will know the future of the programme after the business planning process has concluded in September 2025. / Recommendations: Board is asked to reflect on the themes emerging and discuss the update on the progress over the 15 months of the 2-year programme of the Independent Care (Education) and Treatment Reviews. ET has endorsed the continuation of a future programme if GIA funds are granted. / Key Discussion: / Progress to date / We commenced this important programme of work as planned in May 2024, following the recruitment and training of our Mental Health Act Reviewer’s as Chairs for our IC(E)TR programme. Panels were phased in to ensure quality, test the new end-to-end process and learn from the debriefs. Panels take 4 to 6 weeks to plan to ensure the day runs smoothly. We have established positive relationships with external NHSE regional teams who are now fully engaged in the programme. / By the end of August 2025, we will have completed 71 IC(E)TRs for people in long-term segregation. When we started this two-year programme in November 2023, there were 95 people in long-term segregation. Since then, this has reduced to 74 people. Early indicators show that this is in part due to the anticipatory levers of regulatory influence and the rise in profile of this programme since CQC set up the programme. The remaining people waiting for an IC(E)TR will have their reviews completed by November 2025. Follow up with providers to monitor IC(E)TR report recommendations and follow-up interviews with people, their supporters, and commissioners to better understand the impact of the IC(E)TR programme on their lives will continue until March 2026. / By December 2025, all 95 people originally waiting for an IC(E)TR will have either received an IC(E)TR or been discharged from LTS. Data to July 2025 shows that 19 of the 71 people who have had an IC(E)TR have been supported to leave LTS either to a ward or to a new home in the community. Please see further details in the slide appendixes. / Ensuring Oversight / CQC has set up an external oversight panel, chaired by Dr Clenton Farquharson and Professor Oliver Shanley which meets quarterly both face to face and virtually. The purpose of this group is to have independent oversight of the IC(E)TR programme, which includes looking at the quality of IC(E)TR reports and the impact of the review on the person’s life and their supporters. We will listen to people and learn from their lived experience, making sure this is at the centre of all that we do. Our national report will reflect peoples’ voices and their experiences. / External Oversight Panel Viewpoint / The external oversight panel has highlighted ongoing concerns, particularly around the lack of focus on personalised care and support across the system which have been highlighted by the IC(E)TRs. They stress the importance of a commissioning approach based on human rights and value base, to ensure that people have homes that truly meet their needs and hold stakeholders to account. / CQC-led Delivery / CQC assumed full operational control of the IC(E)TR programme in March 2025, having worked with NHSE colleagues since December 2023. / Added value from CQC’s approach / There are significant differences in how CQC operates the IC(E)TR programme, in the way we collect and analyse data, and how we report on findings and people’s experiences. Our focus is on ensuring people’s human rights are protected, improving people’s lives and wellbeing. Robust feedback and follow-up mechanisms have been created to ensure we seek people’s voices to understand the impact of this programme of work. The feedback has been positive. / A relative said, “I just want to thank you so much for your report. There's a lot to digest, and I suspect that I will have to read it several times to take it all in. It has made me feel really emotional and I really hope that the clarity in it will prompt proper action to help E. I cannot thank you enough. Please pass on my thanks to all the team involved. / A provider and commissioner said – "The ICETR put the service user at the forefront of discussion and allowed person centred discussion. The family of the service user were provided a space in which they felt heard and could develop a further understanding of the work being done.” / One person told us in a follow up interview “I am looking forward to going swimming in the morning for the first time since admission to the hospital. They said this meant a lot to them as they used to go swimming with their family as a child and had fond memories of this” / A panel Chair told us after a follow up from an ICETR, “The person is able to discuss things more with staff and communication is more open, and they are able to access outside space more. However, staff are still very risk adverse and do not support and encourage the person to step outside their comfort zone” / National reporting / CQC wants to improve people’s lives and influence providers and commissioners to consider the most appropriate model of personalised care and support for the person to live their life as a citizen. We want to do this by speaking about the IC(E)TR programme in our national reports. / We want to talk about what makes a difference to people’s lives and understand the drivers and barriers for getting people out of long-term segregation. / We want to talk about the importance of people getting the right support from the right services at the right time when moving out of long-term segregation. This means understanding what will eradicate the use of LTS. / To do this, analysts look at key areas of interest such as ‘what is working well and what is not working well for people in LTS, together with the work being done to help people be ready to leave LTS.’ Our oversight panel are working with us to identify best practise using human rights-based models and policy positions where LTS is not used. / As part of our commitment to DHSC, findings from the IC(E)TR programme are planned to feed into 3 main outputs: / The State of Care report – publication October 2025 / Monitoring the Mental Health Act report - publication January 2026 / IC(E)TR Independent Voice product – TBC 2026 / Early analytical findings from the IC(E)TR programme have been incorporated into this year’s State of Care report. We are seeking feedback from members of the external oversight panel, to inform / the report. / Top level findings are around the following areas: / Discharge planning: Discharge planning was seen as an important aspect of supporting people to leave LTS. However, it was clear that some people had not had discharge plans discussed with them. / Services and professionals working together: Enabling people to leave long-term segregation cannot happen through the inpatient team alone. It requires joined-up care between services and professionals, including having the most appropriate specialist community teams actively involved active involvement from the relevant integrated care boards (ICB) and local authority, commissioners working to solve barriers, and skills-sharing and knowledge-sharing to ensure that the person is supported during the transition to life outside of LTS. / Arrangements for future accommodation: Panel chairs said that there were 2 main routes out of LTS: into a ward in the same hospital, out of hospital into the community. People in services that do not have the ability to combine this approach could face a longer time in long-term segregation while suitable step-down support is identified.
Governance: / ET reviewed and agreed the approach during 2023. / Public Board approved and endorsed the approach in March 2024. / An MOU was agreed with DHSC in Oct 2023 and is reported on back to DHSC quarterly / Correspondence to ET in November 2024 / ET updated and approved September 2025
Strategy: / The programme aligns with CQC’s strategic priorities: / People and communities / Regulation that is driven by people’s needs and experiences, focusing on what is important to people and communities when they access, use, and move between services. / Safety through learning / Regulating for stronger safety cultures across health and care, prioritising learning and improvement and collaborating to value everyone’s perspectives. Assessing local systems / Providing independent assurance to the public of the quality of care in their area. / Tackling inequalities in health and care / Pushing for equality of access, experiences, and outcomes from health and social care services.
Next Steps and Funding: / We will continue the current programme and will provide a public report in Spring/Summer 2026. We will wait for confirmation of funds to continue with a future programme. Continue to work with and strengthen stakeholder engagement. / If the GIA funding bid is successful, the IC(E)TR team will recruit 2 more MHA Chairs and work with our regulatory colleagues to more effectively challenge the use of LTS together with the prevention agenda to influence commissioning and market shape better community provision for people. We will continue to learn from and improve our processes and continue to follow up and listen to individuals and their supporters to influence practice and enable people to lead their best lives as citizens. Prevention of admission into LTS is critical to the eradication of the use of this restrictive practice. Where we have seen system partners adopt a position to not use LTS, we will shine a light on this personalised human-rights based approach to enable other system partners to learn and adopt. / Finance: The ICETR Programme is funded until Dec 2025 by GIA. Confirmed funding required has been included in DHSC envelope to Treasury for 26/27 funding
Risk: Unconfirmed future funding for 26/27 impacts our ability to plan for the future and leaves the programme with a level of uncertainty. In terms retention and recruitment of chairs and delivery of activity for people.
People: Awaiting funding confirmation to realise the resourcing secured to support the continuation and further development of the programme.

Appendix A

ICETR Summary Statistics for July/August 2025 – Appendix 1