PUBLIC BOARD, 23 February 2022

TITLE: Quarterly Change & People Update

Executive Sponsor: Kirsty Shaw - Chief Operating Officer
Presenter: Amy Pritchard, Director of Transformation / Gill Nicholson, People Director
PURPOSE: FOR ASSURANCE

This paper is provided to enable the Board to fulfil their duties in relation to:
- Monitoring the progress and delivery of strategic change programmes
- Ensuring financial probity and the efficient and effective use of resources

PROPOSAL OR RECOMMENDATION

Information for Board to be aware of:
- Impact on CQC and stakeholders - the continuation of Target Operating Model and Strategy implementation
- Timeline for delivery – ongoing until FY24/25
Board are asked to note on the delivery performance.

BACKGROUND

This paper is an established component of CQC’s governance of its strategic transformation portfolio, it provides visibility of performance against delivery for the quarter ending January 2022.

KEY POINTS
Summary
Key achievements over the last quarter include:
- We have completed initial work to define stage three of our new ways of working. This will be further developed over the first part of next year so that we can better define our objectives of this phase.
- We have developed and implemented our new Annual Provider Survey
- The first stage of our detailed design of Operations and Regulatory leadership has been completed.
Transformation Update
Performance Summary
Overall portfolio performance remains Amber/Green. We continue to make improvements in how we resource our portfolio of change alongside confirmation of deliverables and dependencies linked to finalising phase one of our new ways of working. We have also set out the plan for our second phase and have developed an indicative plan for phase three.
We have introduced a new Portfolio Management tool which enables us to have much more transparency and control across our portfolio of change.
Our engagement activity has been focussed on continued discussions and engagement with our colleagues, providers, the public and wider stakeholders on how we are developing our future approach and what our new ways of working could mean for them. Key topics included multidisciplinary team working, relationship management and our new assessment approach.
Programme Performance
Portfolio Pillar 1: Regulatory Framework
This pillar is focused on the design of our regulatory model to guide how we develop our new regulatory services and shape what skills we need for the future.
Over the last quarter we have continued to develop our single assessment framework (for providers) to incorporate our risk-based strategy and an approach for Local Authority Assurance and Integrated Care Systems. We have also agreed the high-level requirements to support the delivery of our objective around Peoples Experience.

Portfolio Pillar 2: Organisational Design and Development
This Pillar will deliver our organisational changes to ensure we have the skills and culture we need to deliver our new strategy.
During the last quarter we have completed the first stage of the detailed design for our Operations and Regulatory Leadership function. In collaboration with colleagues across the organisation, we identified four cultural themes that will support a more autonomous and empowered way of working. These are Governance and Leadership, Data-led, Collaboration and Learning and Psychological Safety and Trust.
We have agreed a set of efficiency saving quick wins as part of our corporate governance review, which will improve the current service and commence streamlining activities.
We have completed the first stage of our Management of Change for Executive 2 level colleagues. People Directorate has engaged with operational Director colleagues in conversations about the new configuration at executive level and what this means for them. We will begin to deploy resources into the new structure in the next quarter.
Portfolio Pillar 3: Regulatory Services
This pillar will develop and deliver new services, processes, data and technology aligned to embedding our new policy and regulatory approach as defined under pillar 1.
In our Transforming Data and Insight programme, we have implemented our Annual provider survey and the first stage of our data integration has completed. This has allowed us to successfully test our approach for future data migration activity. Our Management of Change for Data and Insight has progressed to next phase.
In our Regulatory Platform programme, we have successfully implemented a new provider fees solution. We have appointed operational Service Owners to drive the end state vision and design of services. These Service Owner roles will work ensure all aspects of the service hang together to deliver the necessary objectives (people, process, technology, data).
Our Corporate Services programme is the third strand in this pillar and is focused on driving transformation in our Finance function through the provision of a new finance system. The delivery partner for this work has been selected and onboarding is underway. Work has initiated to move to the next phase of delivery.

People Strategy Update
Capability building
In the last quarter the Academy has been analysing the learning needs within the Data and Insight Unit, based on new ways of working, processes and the technical capability requirements arising from the Transforming Data and Insight programme. Additionally, capability gaps are emerging from the Management of Change assessments through to March 2022.

We have continued the focus on building capability across CQC in managing change, at all levels. Learning from those undergoing management of change processes will be rolled out to other parts of the organisation as appropriate, and management and leadership development requirements are currently being scoped.

Culture
We have completed a series of conversations, across the organisation, to develop our understanding of both what is important to our people in how they experience work and what will be critical in terms of behaviours, ways of working and culture to enable us to be our best individually and collectively to deliver our strategy as an organisation. The analysis of this work has led to the development of some core principles which we will apply to all aspects of our transformation. We will also use this work to start gathering stories of the great ways of working that already exist across CQC and using these to showcase and celebrate what we want to see and do more of as we progress.

Recommendation
None
Discussion and implications
None
Conclusion and Next Steps
We ask the Board to note progress in delivering what is an ambitious transformation and people agenda. In the coming quarter we will focus on:
- To conclude phase 2 and phase 3 planning to enable robust implementation of new ways of working.
- Continue management of change activity to populate our new operating model
- To continue to engage with our colleagues to gather examples and stories of great ways of working.
- To continue to focus on building capability across CQC in managing change.
- To conclude the portfolio scope (IOM2) and structure in readiness for the new FY
- Draft the initial IOM3 objectives and high-level implementation plan
- Complete commercial activity for a managed service provider for specific user centred design roles
- Created a single catalogue of Services
- Developed key messages and video/podcast products for colleagues to describe key dates and impacts as a result of the Operations and Regulatory Leadership design decisions
- Mobilise resources for the start of IOM 2

Appendices
None
Those who contributed to this paper
- Nina Snell – Head of Transformation Delivery
- Gill Nicholson – People Director

 CONTRIBUTIONS

The following groups/people have been involved in forming this paper:

Groups/people	Involvement?	Feedback
HR	Yes	People update comes directly from HR colleagues.
Finance	Not applicable
DHSC	Not applicable
Executive Team	Not applicable
Board Committee	Not applicable
Executive Committee	Not applicable
Trade Unions	Not applicable
Staff Networks	Not applicable
Other – please specify	Not applicable