# People Plan: Our Workforce Race Equality Action Plan
April 2022 – March 2023

## WRES Indicators: 1
Objective:
To establish a workforce which is representative of the communities we serve
Actions:
- Work with Race Equality Network (REN) to continue to promote the importance of self-declaring ethnicity on ESR to help reduce the percentage of “Not Stated” to our target of 95% (currently 91%). Raising awareness through campaigns, articles and videos promoted to all colleagues throughout the year to highlight the importance of having accurate ESR data. We will work with Network Chairs to encourage the self-reporting in their Networks. As well as considering sending direct emails to employees to encourage self-reporting, if they have not done so already.
- The Academy and Organisational Development teams will run the Reverse Mentoring Programme again in 2022, to include both Black and Minority Ethnic colleagues and disabled colleagues, with greater focus on intersectionality. This will allow senior leaders the opportunity to mentor Black and Minority Ethnic colleagues, give opportunity for Black and Minority Ethnic colleagues to shadow senior leaders and help Black and Minority Ethnic colleagues progress within the organisation. Organisational Development and the Race Equality Network will work with the Senior Leadership Team to promote mentoring and understand the importance of mentoring a diverse group of people, including Black and Minority Ethnic colleagues.
- Continue to build the CQC’s employer brand, as a great place to work for Black and Minority Ethnic colleagues on these diversity recruitment sites, it will draw in a wider pool of Black and Minority ethnic people shortlisted for our Grade A and Executive roles. We have begun advertising Executive and Grade A job roles onto both Vercida and Diversity Jobs.com. This year we will review how effective these diversity job websites have been to attract diverse talent at our Grade A and Executive advertised roles.
- The Race Equality Network will continue to hold monthly talks with colleagues in senior roles, often Black and Minority Ethnic colleagues, to discuss their career pathway, opportunities and potential challenges and progression into their roles.
Timescales:
- April 2022– Start to evaluate the diversity recruitment websites and recruitment campaigns with quarterly reviews.
- 2022 Q3 - Begin the Reverse Mentoring Programme
Lead:
People Analytics and Insight Manager, Diversity & Inclusion Manager OD, REN, Academy and Recruitment
Why or link to D&I Strategy ambitions:
For CQC to achieve its strategic ambition, it is important that our colleagues are representative of the communities we serve.

## WRES Indicators: 1, 2 & 7
Objective:
Implement Independent Panel Members (IPM) for all recruitment activity
Actions:
- We will evaluate the use of Independent Panel Members (IPMs), which currently are used for all Grade A, Executives and Expression of Interest (EOI) recruitment panels.
- With the evaluation of the IPMs, we are hoping to utilise IPMs in the shortlisting process for all Grade A and above. This will help mitigate biases and hopefully increase the amount of Black and Minority Ethnic colleagues being shortlisted to attend an interview.
- We will increase the IPM pool we currently have. We will work with the Equality Networks, People Leads and Senior Leadership team to promote, hire and train new IPMs to increase the IPM pool to the threshold necessary to extend the IPMs to shortlisting.
Timescale:
- March - Start to evaluate and review IPMs.
- April - Campaign to increase IPMs.
- 2022 Q1 - Begin introducing IPMs into shortlisting process.
Lead:
Recruitment, REN
Why or link to D&I Strategy:
IPMs play an important role in ensuring the recruitment process is fair, open and transparent. Strategic Ambition: Inclusive policies and practices.

## WRES Indicators: 1, 2 & 7
Objective:
Develop an inclusive recruitment toolkit and ensure robust feedback is provided to applications internally and externally.
Actions:
We will design an Inclusive Recruitment Toolkit with Recruitment and REN to help hiring managers best support Black and Minority colleagues through interviews.

Timescales:
May 2022– start building the Inclusive Recruitment Toolkit.
Lead:
Recruitment, D&I Manager, OD, REN
Why or link to D&I Strategy:
To ensure our recruitment process is open, fair and inclusive. Constructive feedback is key to enabling candidates to strengthen their interview techniques and progress their careers. s. This requires a shift in behaviour for recruiting managers to take ownership for providing feedback. Strategic Ambition: Inclusive policies and practices.

## WRES Indicators: 1, 2 & 7
Objective:
Understand and respond to adverse impact within the recruitment process
Actions:
- We have worked with Digital to remove the option to upload a CV onto our recruitment site. This enables us to uphold anonymous shortlisting and reduces the likelihood of bias influencing selection outcomes.
- For all recruitment campaigns, we monitor adverse impact for Black and Minority Ethnic and disabled applicants. This involves a review of the diversity of the applicant pool at the shortlisting stage and where any adverse impact is observed we will ask hiring managers for a further review of those not shortlisted. We are also monitoring the diversity of initial applications and offers to ensure we are representative of the working population and again to identify any adverse impact within the process.
- We have transformed the Recruitment for Leaders training to be an e-learning module. This was done so all hiring managers can complete the training before starting the recruitment process. The e-learning involves understanding common biases that present themselves at interviews. We will explore making the Recruitment for Leaders training (which we have transformed into an e-learning module) mandatory for all line managers/hiring managers, in order to help mitigate biases at interview.
Timescale:
Ongoing
Lead:
Recruitment team, all recruiting managers
Why or link to D&I Strategy:
Remove any barriers throughout recruitment process. Strategic Ambition: Inclusive policies and practices

## WRES Indicators: 1 & 2
Objective:
Develop a positive action programme to improve representation of Black and Minority Ethnic colleagues in Grade A and above
Actions:
The Action for Race Equality Group (AREG) and Recruitment team are starting a recruitment Quality Improvement project examining the interview process for Executive 1 grades and implementing processes to make Executive hiring more fair, unbiased and anonymous.
Timescale:
Begun January 2022
Lead:
AREG, Recruitment team, Academy Learning and Development team, Race Equality Network, OD team
Why or link to D&I Strategy:
To ensure all colleagues build skills and experience and have access to internal development opportunities. Strategic Ambition: Inclusive Policies and Practices

## WRES Indicators: 1, 2 & 7
Objective:
Review the Expression of Interest (EOI) process for internal recruitment
Actions:
Expressions of Interest (EOI) opportunities will be advertised through our recruitment site and not shared and hired locally. This enables a fairer and more transparent process for people to be aware of what EOI opportunities are available, allowing them to feel more confident to apply for EOIs, without fear of biases.
Lead:
Recruitment team, HR Business Partners, People leads
Why or link to D&I Strategy:
Review of the current EOI process is important in improving the perceptions held by 51% colleagues that CQC offers fair career progression and promotion. Strategic Ambition: Inclusive policies and practices.

## WRES Indicators: 1 & 7
Objective:
Use our talent management model to develop a diverse talent pool of Black and Minority Ethnic colleagues, ready for promotional opportunities (including secondment and stretch projects)
Actions:
- This year we are introducing the “Inclusive Leadership Pathway” (ILP) to support colleagues who go onto the NHS’ “Ready Now” and “Stepping up” programmes, as well as the Disability Rights UK programme. The ILP has been designed by Academy, Disability Equality Network and Race Equality Network Chairs, to support Black and Minority Ethnic and/or disabled colleagues who are on the external apprenticeships. It includes stretch projects, funded learning, and coaches. We have identified CQC trained Black and Minority Ethnic coaches, who will be paired up with Black and Minority Ethnic colleagues going through these programmes. Therefore, the colleagues will receive expert coaching from coaches who can relate to them the most. The induction of the ILP this year should hopefully improve the experience of these colleagues going on upcoming 2022 courses (such as Level 3 Leadership and Level 5 Project Management Apprenticeships) and being able to apply their learning to the CQC and feel more confident to progress into leadership roles.
- The Academy and Organisational Development teams will run the Reverse Mentoring Programme again in 2022 to include both Black and Minority Ethnic colleagues and disabled colleagues, with more of a focus on intersectionality. This will facilitate shadowing and mentoring of senior colleagues for Black and Minority Ethnic colleagues; and help them to progress within organisation. It will also provide greater understanding for senior leaders of the challenges Black and Minority Ethnic colleagues face in the workplace. Organisational Development and REN will work with the Senior Leadership Team to promote mentoring and understand the importance of mentoring a diverse group of people, including Black and Minority Ethnic colleagues.
- The Talent team will share the upcoming Shaping Our Future Leaders and Apprenticeship programmes with the Equality Networks, including joining their Network days to promote the upcoming programmes. For these programmes, we hold a percentage of candidates who are Black and Minority Ethnic and/or Disabled in our potential candidate’s pool. This enables us to make sure Black and Minority Ethnic candidates and disabled candidates get the opportunity to apply and hopefully accepted onto our Shaping Our Future Leaders Programmes.
- The Talent team created “register your interest” forms prior to the sign up for the apprentice programmes. We will examine whether there is a noticeable gap between Black and Minority Ethnic candidates filling out the form and those who apply for the apprentice.
- AREG working with the Talent team to investigate CQC’s current talent management model and whether the current system develops a diverse talent pool of Black and Minority Ethnic colleagues.
Timescales:
Q1 2022 – Inclusive Leadership Pathway begins.
Lead:
Talent team, People leads, Line managers, AREG
Why or link to D&I Strategy:
To contribute to our ambition of having better representation of Black and Minority Ethnic colleagues in Grades A and above. Strategic Ambition: Inclusive policies and practices

## WRES Indicators: 4 & 7
Objective:
Review of the current individual learning requests (ILR) for funded learning
Actions:
Through a QI project, the AREG, alongside Talent and Academy teams, are reviewing the current Individual Learning Requests for funded learning, to see if the current process can be improved.
Lead:
Academy, Talent
Why or link to D&I Strategy:
Career development is important for an ambitious and progressive organisation and access to funded learning should be equitable to all. Strategic Ambition: Inclusive policies and practices.

## WRES Indicators: 7
Objective:
Undertake pilot of ethnicity pay gap monitoring
Actions:
- Review best practice in ethnicity pay gap reporting across private and public sector
- Collate relevant data to produce ethnicity pay gap report
- Consider any appropriate actions
Timescale:
Q1 2022/23
Lead:
Data Analyst, People Directorate, Race Equality Network
Why or link to D&I Strategy:
Understand if Black and Minority Ethnic colleagues face a pay gap and implement actions to address this. Strategic Ambition: Inclusive engagement

## WRES Indicators: 3
Objective:
Reduce the likelihood of Black and Minority Ethnic colleagues entering the formal capability process compared to white colleagues.
Actions:
- We will work with the People Directorate and Race Equality Network to conduct a deep dive and identify any prevalent issues which can shed light on the increase.
- Continue to use Equality Impact Assessments (EIA) as part of all people management policy reviews which requires the Diversity and Inclusion Manager to sign this off at each review.
Timescale:
Q1 2022
Lead:
HR Advice and Guidance, Race Equality Network
Why or link to D&I Strategy:
We want to ensure that our Black and Minority Ethnic colleagues are not disproportionally impacted. Strategic Ambition: Inclusive policies and practices

## WRES Indicators: 5 & 6, 8
Objective:
Reduce the gap between Black and Minority Ethnic and white colleagues who through our people survey, report that they have experienced internal bullying, harassment and/or discrimination
Actions:
- OD will work with the AREG and all the Equality Networks to introduce an internal campaign that promotes CQC’s zero tolerance of bullying and harassment. This campaign aims to make the CQC is an organisation that people are encouraged to and feel able to report bullying and harassment in, even if that’s from external stakeholders.
- The new Anti-bias and fairness e-learning training module will become mandatory learning for all colleagues from April 2022. After completion, it takes the user to their “My Performance” page and encourages colleagues to select one of the behavioural Diversity & Inclusion Success Profiles We hope the training and direct link to colleague’s Success Profiles will encourage colleagues think about their biases towards Black and Minority Ethnic colleagues and choose a Success Profile to exemplify going forward.
- We will continue to highlight our Black and Minority Ethnic colleagues lived experiences through our All Colleague Conference, Black History Month events and on our CEO’s All Colleague Calls. To reduce the stigma and to make colleagues aware that CQC values and supports all our Black and Minority Ethnic colleagues.
- OD will continue to work with REN Chairs, to identify whether there are trends and patterns in teams or directorates, where Black and Minority Ethnic colleagues are being bullied or harassed.
- Academy and OD will run the Reverse Mentoring Programme in 2022 to include both Black and Minority Ethnic colleagues and Disabled colleagues. This will allow senior leaders to understand any bullying and harassment Black and Minority Ethnic colleagues may experience in the workplace and help address and reduce it throughout the CQC.
- Academy, Organisational Development and the Race Equality Network will work together to create a new CQC tailored e-learning product for colleagues and managers to be aware of bullying and harassment Black and Minority Ethnic colleagues may face.
- We will utilise the People Surveys and exit interviews to identify trends, concerns and potential areas for improvements for Black and Minority Ethnic colleagues.
- We will build a stronger relationship between the Race Equality Network (REN) and Freedom To Speak Up (FTSU) Guardians and Ambassadors, To encourage Black and Minority Ethnic colleagues and/or REN members to raise bullying and harassment concerns and broaden knowledge of the support available from FTSU network. We will run a joint network event for February’s Stand Up to Bullying Day chaired by a FTSU Ambassador and Network Chairs as panel members.
- Explore and review the most recent People Survey results for additional data and comments regarding the type and origination of bullying and harassment reported.
Timescale:
- 2022 Q2 - Create new bullying and harassment e-learning products
- 2022 Q3 - Begin the Reverse Mentoring Programme
Lead:
AREG, OD, HR Advice and Guidance, Race Equality Network
Why or link to D&I Strategy:
We want to create an inclusive culture where all our people valued and respected without fear of experiencing harassment, bullying or discrimination from anyone. Strategic Ambition: Inclusive cultures

## WRES Indicators: 9
Objective:
Having a representative Board that is reflective of CQC workforce
Actions:
- We will work closely with our Executive members so they can understand the importance of self-reporting. This CQC also with the increase of 1 or 2 Black and Minority Ethnic Non-Executive Board Members.
- Academy and Organisational Development will run the Reverse Mentoring Programme again in 2022 to include both Black and Minority Ethnic colleagues and Disabled colleagues. This will allow the opportunity for the Executive team to be mentored by Black and Minority Ethnic colleagues and understand the experience of being a Black and Minority Ethnic colleague at CQC, as well as give opportunity for Black and Minority Ethnic colleagues to shadow the Executive team leaders.
- Continue to work closely with the DHSC recruitment team to reinforce the CQC’s commitment to attract and recruit more Black and Minority Ethnic colleagues
Timescale:
2022 Q3 - Begin the Reverse Mentoring Programme
Lead:
Board Chair, Recruitment team
Why or link to D&I Strategy:
For CQC to achieve its strategic ambition, it is important that our people are representative of the communities we serve. Strategic Ambition: Inclusive policies and practices.

## WRES Indicators: All indicators
Objective:
Increase awareness and understanding of Black and Minority Ethnic colleagues lived experiences
Actions:
- Continue to hold curious conversations to highlight and raise the profile of individuals’ lived experiences.
- Increased promotion of equality network-led events to embed the ambitions of the Diversity and Inclusion Strategy.
- Reverse Mentoring Programme for all senior leaders
- Ensure the lived experiences of our Black and Minority Ethnic colleagues are shared through different mechanisms e.g. Schwartz rounds, All Colleague Calls
Timescale:
- Ongoing
- 2022 Q3 - Begin the Reverse Mentoring Programme

Lead:
- Organisational Development team
- Academy Learning and Development team
- Joint Network Voice
Why or link to D&I Strategy:
To continually provide our senior leaders with insights into the lived experiences of our Black and Minority Ethnic colleagues within CQC. Build skills of Black and Minority Ethnic colleagues. Strategic Ambition: Inclusive leadership and accountability and Inclusive Culture

Read more…
- Working for CQC - our commitment to equality
- Last year's action plan: Workforce Race Equality Standard 2021