MEETING	PUBLIC BOARD MEETING / 19 May 2021
Agenda Item / Paper Number	5 / CM/05/21/05
Agenda Title	Corporate Performance Report (2020/21 – Year End)
Executive Sponsor	Kirsty Shaw, Chief Operating Officer
Author	Chris Usher, Director of Finance, Commercial, Workplace and Performance / Stephanie Tarrant, Head of Performance

PURPOSE OF PAPER:

Actions required by the Board:
- Note 20/21 Year End performance, highlights and areas we have not delivered against plan.
- Note financial position.
- Comment on the areas of Performance where we ended under plan and action.

IMPACT:

The Performance Report covers commitments set out in our 2020/21 Business Plan and delivery against our organisational priorities across 2020/21 financial year. Where we have underperformed stakeholders will want to be assured there are adequate measures being put in place to improve the position.

Summary

This paper and annex summarise our end of year performance against our 2020/21 business plan as well as our delivery against our priorities during the current period of the COVID-19 pandemic.

The Performance Annex March 2021 (Annex 1) gives an overview of:
Performance against Business Plan targets;
Progress against Internal Audit recommendations

Recommendation

  1. It is recommended that the Board note the 20/21 performance at the end of March 2021, as well as our delivery to date, and comment on the areas where are under plan.

Discussion and implications

Throughout 2020-21 we have responded to the pandemic and set priorities each quarter whilst monitoring our progress against our corporate business plan.

Effective and efficient registration service

3.1 Registration timeliness: During the financial year we have processed 29,542 applications.  Complex applications have taken 115.2 days to process and simple applications 21.1 days. Simple applications are made up of applications processed by Registration Support and those which are reduced risk. During this year we have understood the service better with data and evidence to drive improvement initiatives.  We have successfully centralised Unregistered Provider and Sales and Transfer activity and also extracted what can be done as desk-based applications.  During this coming year we are focussing on providing clarity to provider groups about what a successful application to be registered contains.

During the pandemic, we have managed issues with workforce availability and being unable to cross the threshold of a service to conduct site visits the way our methodology supports.  Alongside this we have proactively responded to emerging and evolving prioritisation of registration applications to support our response to COVID-19. This means that services providing treatment for COVID-19, including settings that support discharge of positive patients from acute settings, testing and vaccination centres and services which increase overall capacity to provide care in relation to COVID-19 were given priority, these priorities have been continually reviewed alongside the government response to the pandemic. We continue to monitor and realign priorities across registration ensuring we communicate with providers who have applications within the registration process and offer escalation and communication channels to discuss registration needs and priority.

3.3 Registration Representations: Since April 2020, 91% of NOPs have been adopted against a target of 90%. Out of 92 representations, seven notices were overturned due to the evidence received. A notice of proposal can be used if an application is rejected or it is proposed that the provider is registered but with additional conditions, representations can be received if further evidence is submitted to challenge the outcome.

We use intelligence to regulate registered services

3.4 Safeguarding: Throughout the 12 months, 97% of safeguarding alerts have been processed in 1 day against a target of 95%. For safeguarding concerns, where other key stakeholders are already involved, we have a target of recording our action within 5 days. 95% of safeguarding concerns have mandatory action recorded in the timescale, against a target of 95%.

3.5 Whistleblowing: Across the last 12 months there has been a gradual increase in the volume of whistleblowing enquiries that are received each month, with a total of 15,829 being received. As part of our performance reporting we monitor the timescale to record an outcome from whistleblowing enquiries. Over the last 12 months it was 4 median days to record a concluded outcome. We have conducted a review of our whistleblowing process throughout the year and from 1 April 2021 we will be capturing how we have mitigated risk for each whistleblowing enquiry received.

3.6 Using information of concern: Safeguarding and Whistleblowing continue to be key intelligence in identifying risk. Across the 12 months 54.24% of inspections triggered by risk were in response to information of concern. We categorise information of concern as enquiries related to whistleblowing, safeguarding, complaints and concerns.

3.7 Regulatory Action: In March 2020 routine inspections were paused, however we continued to inspect due to risk or concerns. In May we implemented Emergency Support Framework (ESF) and in October Transitional Monitoring Application (TMA). Using the new regulatory models, as well as inspection, 51% of registered locations have had regulatory activity across the year.

3.8 Adult Social Care – Designated Settings and Infection Prevention Control (IPC) Inspections: In response to the pandemic Adult Social Care commenced thematic inspections focusing on Infection Prevention and Control (IPC). As well as IPC inspections, Adult Social Care also supported the establishment of designated sites so that people have COVID-19 could be discharged from hospital in a timely way, freeing up capacity in the system. As of 19 April, 144 designated settings have been approved, equating to 2253 beds. 1606 IPC inspections have taken place focusing on IPC completely and 29.88% of all residential homes have had their IPC reviewed as part of an inspection.

We use enforcement when we need to keep people safe

3.9 Enforcement - Urgent Actions: Where we have made a decision to take urgent enforcement, we aim to serve the notice within 3 days. Our target is to do this in at least 70% of situations. Since April 2020, 94% were served within 3 days.

We provide timely information that is useful for the public and providers

3.10 Independent Voice: The IRMER Annual Report, Controlled Drugs Annual Report, Mental Health Act Annual Report, Annual Report and Accounts 2019/20 and State of Care are all complete and published.

We develop our regulation and our organisation through a programme of change and quality improvement

3.11 Change: The change portfolio covering various projects and programmes is being tracked based on delivering to time, cost and quality. Overall, the portfolio is currently RAG rated amber.

3.12 QI: At the end of 2020/2021, there were over 80 QI projects underway in the organisation. 10 of these were overseen by the Improvement Board, and the remaining majority were smaller QI initiatives being led by colleagues at a team-level. Throughout 2020/21 work has been on going to ensure QI benefits management and measurement of improvement is aligned to our transformation programme. Measures and aims for improvement are determined at start of each project and the improvements in provider/service user/colleague experience, time and / or quality and are translated where possible to demonstrate the return on investment expected. There have been 32 projects closed in year. Six have been closed with clear benefits captured, the others are finalising the benefits review.

Equip our people and organisation to deliver our purpose now and in the future

3.13 People
Turnover: As of 31 March 2021, CQC’s rolling 12-month turnover rate is 7.6%, a decrease from the previous year where it was 10.6%.
Sickness: Despite the COVID-19 outbreak, our sickness rates remain low with the percentage of full-time equivalent days available lost to sickness in 2020/21 (until 31 March 2021) at 3.2%. Compared to the previous 2 years, there has been a slight increase in mental health sickness absences and stress/anxiety still remains the top absence reason.
Diversity: As of 31 March 2021, Black and minority ethnic colleagues make up 13.8% of the workforce, in comparison to the labour market which is 12%. As of 31 March 2021, CQC colleagues who are disabled make up 8% of the workforce, in comparison to the labour market which is 14.6%. There are 9.37% black and minority ethnic colleagues in senior roles.
3.14 Finance: for the financial year 2020-21 our revenue budget was £10.0m underspent, largely reflecting the impact of Covid-19 on our activity. This included a £0.6m shortfall on provider income, which was significantly less than estimated earlier in the year. The underspend will be retained to enable delivery of current and future regulatory activity in support of our new strategic aims. Our capital budget ended the year £0.4m underspent, with expenditure largely supporting delivery of transformational change programme.

Risk Register

4.1 How risks have evolved in 2020-21: 2020-21 has seen our corporate risks change and evolve significantly. We have managed several key risks, in particular those relating to Covid-19:

4.11 The risk that not able to enter premises and remain mainly limited to remote inspections, or we do not have an effective intelligence led approach, meaning there is a risk that poor practice and patient harm goes undetected.

4.12 A failure to adapt our regulatory model to the pace of change in health and social care organisation and delivery - including due to Covid-19.

4.13 Financial pressures causing a deterioration in quality of ASC services making it more difficult for CQC to deliver its purpose to ensure the quality of care.

4.14 The UK’s relationships with the EU and the rest of the world and impacts upon processes for the health and care system, including the recruitment and retention of a skilled health and care workforce; access to medicines, medical goods and non-medical consumables; and arrangements for reciprocal healthcare.

4.15 The potential challenges for well-being of our own people from the impact of Covid-19, including home working, potential for isolation etc.

4.16 We also managed risks relating to delivering a challenging change programme; a changing regulatory model with the need to support the Government’s pandemic response in a flexible way, with developing a credible Strategy for publication in May 2021, as well as information and cyber security risks.

4.2 Risk register changes in Q4:

4.2.1 R1 (Effective regulator) – There is a reduction from 16 (high) to 12 (medium). Whilst R1 was rated highly at a time when there was enormous pressure due to the pandemic, the situation has changed. The risk of COVID-19 has reduced, and our priorities are on inspection. It is recognised that we haven’t completed the evaluation of our new digital regulatory tools, but we have had contact with over 50% of registered locations during the pandemic.

4.2.2 R4 (The UK’s relationships with EU and rest of the world) – There is a reduction from 12 (medium) to 8 (medium). There is residual risk in the sector, mainly in relation to pharmaceuticals but if no additional concerns by end of Q1 then this risk will be reviewed with a further reduction considered.

4.2.3 R9 (Our Strategy) – There is a reduction from 12 (medium) to 6 (medium). The initial feedback on the Strategy is positive. It is proposed to remove this risk from May with delivery being tracked through other corporate risks.

4.2.4 R10 (People Engagement and Well-Being) - Scoring is held at 9 (medium). Whilst it is recognised there is still a lot of change within the organisation which impacts our people – new Strategy, pressures of the pandemic and transforming our organisation, the outcome of the recent Pulse survey will enable further understanding of this risk.

4.2.5 R12 (Our Funding) - Scoring has reduced from 12 (medium) to 6 (medium). Concerns about provider fee debt have lessened and funding is agreed and in place for 2021-22.

4.2.6 Introduction of a new risk for 2021-22 - The Executive team have identified a new risk to be introduced around access to data streams. CQC’s increased need to be insight driven requires data to be available to us from across the system, which involves us to work closely with all areas of the sector to gather the data. Secondly, there is a risk in relation to the effectiveness of data depending upon its quality and age. Finally, there is risk if we are not able to appropriately share data we gather with strategic partners. This risk will be set out in the Risk Register for 2021-22.

Internal Audit Actions

5.1 There are 19 internal audit action plans that we are tracking across CQC. There are no actions to report on for HWE. We report on progress by the number of individual actions within plans and whether they are: closed; on track; or overdue.

5.2 As of the 31st March, 144 actions (56%) are closed, 89 (35%) are on track and 22 (9%) are overdue for CQC.

Conclusion and Next Steps

Board will continue to be appraised of performance monthly across the new financial year.