MEETING	PUBLIC BOARD MEETING / 19 May 2021
Agenda item and Paper No	6 / CM/05/21/06
Agenda Title	Quarterly Change & People Update
Sponsors	Kirsty Shaw, Chief Operating Officer / Mark Sutton, Chief Digital Officer
Authors	Amy Pritchard, Director of Transformation / Gill Nicholson, People Director
PURPOSE OF PAPER:
To provide the Board with an update on delivery against the transformation programme and the people strategy.

Summary

Key achievements over the last quarter include:

- Agreed the nature and sequence of the change priorities that will deliver our new strategy and operating model.
- Launched ‘Our Future Way of Working’ in February marking the beginning of an ongoing dialogue with colleagues, providers and stakeholders around how, why and when we will change (see Appendix A for detail).
- Introduced the Workforce Disability Equality Standards setting out our commitment to improving the experiences of our Disabled colleagues.

Refreshed our new talent approach, to engage and inspire all colleagues to make the most of opportunities available to them.

Introduced the MIND workplace wellbeing index to celebrate the good work we are doing to promote positive mental health and identify areas of focus for improvement.
Transformation Update
Work is currently underway to formally establish a portfolio that is aligned to realising our new strategy and operating model. Activity will be geared around 3 core pillars that come together to deliver a series of transition states and new capabilities over the next 3 years;

- Regulatory Model – Defines regulatory policy
- Operating Model and Organisation Design – Defines structures, skills and capabilities
- Regulatory Services – Defines services, products, processes, data and technology
Highlights for this period are as follows;

Transforming Our Organisation
This programme has designed the new operating model the will deliver the CQC strategy, its core premise is founded upon becoming an insight driven organisation with inbuilt agility and flex to respond at pace to changes in the regulatory environment. As we move into the next phase which is about implementing this model through the new portfolio structure described above this programme will be disbanded, having successfully created a clear anchor against which to execute the strategy.

Regulatory Platform Programme
The focus of this programme is to design, build and implement a series of end to end regulatory services that are aligned to our target operating model transition states. At the end of year 1 our ambition is to be able to test place-based working through actionable and intelligible insight with subsequent transition states and services building out beyond this point.
Transforming Data and Insight Programme
The transforming data and insight programme are tasked with delivering the insight driven aspect of our model. As such it is designed to revolutionalise the technology we use to manage and analyse data whilst changing the way we work to maximise its impact in our regulatory activity so that we can target our people on the areas that pose the greatest risk.

Registration Transformation Programme
As we transition and align our portfolio to deliver a new strategy, we have actively sought opportunities to consolidate activity and ensure alignment to our digital roadmap. Moving forwards development of our digital ‘Register with CQC’ service will move to the Regulatory platform programme as newly available technology will enable us to scale the service at quicker rate. This initiative will form part of a broader set of projects designed to deliver new regulatory services.

Improving Regulation Today Programme
Moving forwards much of the work in this area will be subsumed into a programme that is designed to set out our end to end regulatory framework, essentially the policy and legal parameters that will inform the design in the programmes outlined above. All of the critical learning and requirements that relate to closed cultures and liberty protection safeguards will form attributes of this framework so that they form a fundamental part of our future regulatory approach.

People Strategy Update

Employee Experience

Talent and Career Pathways
A refresh of our approach to Talent Management has been launched. This supports and encourages all colleagues to focus on their career within CQC, helping us to identify and develop a more diverse talent pipeline and deliver our future strategy. We will deliver the first phase of our new talent approach this quarter.

Resourcing
Work is underway to incorporate success profiles into our assessment process, allowing us to better support and understand a candidate’s abilities and fit for the role. We have completed an independent review of some of our internal processes with a focus on diversity and inclusion. The recommendations are mapped into our Diversity and Inclusion action plan.

Employee Insights

People Analytics
We have developed a People data pack to provide an overview of progress on our key People metrics and priorities.

Pulse Survey
Our latest Employee Voice Pulse Survey was live in March which has gathered feedback from all colleagues on their experience of working at CQC. Planning for the next pulse survey in late June/early July is underway, with the primary theme for the survey being wellbeing.

Inclusion

Workforce Disability Equality Standard
The Workforce Disability Equality Standard (WDES) is an NHS standard which helps us understand and improve the experiences of disabled colleagues. CQC is implementing the WDES for the first time this year and have developed a robust action plan to address some of the key issues that have emerged.

Workforce Race Equality Standard
The Workforce Race Equality Standard (WRES) is an NHS standard which helps us understand and improve the experiences of colleagues from Black and Minority Ethnic backgrounds.  We have developed an action plan for publication, linked to our Diversity and Inclusive Strategy and supported by the newly formed Action for Race Equality Group, which includes members from our Race Equality Network and D&I experts.

Reverse Mentoring
We have implemented a Reverse Mentoring programme for our Black and Minority Ethnic colleagues as part of our work on race equality. All senior leaders are currently being mentored by a BME colleague in CQC.

Wellbeing
We participated in the MINDS Workplace wellbeing survey. Results available from June 2021 will inform recommendations on areas of focus for the future.

Line Management capability
Our new approach to deliver learning materials as part of our Leadership and Management faculty is now ready for roll out.

Leadership

Success Profiles and My Performance
Success Profiles are now integrated into our My Performance approach and colleagues are now creating task-based and behavioural objectives on the performance system. Over 2280 colleagues joined and engaged in the update briefings.

Conclusion
We ask the Board to note progress in delivering what is an ambitious transformation and people agenda. In the coming quarter we will focus on:

- Full mobilisation of CQC’s strategic change portfolio aligned to agreed priorities.
- Approval of the business case for Transforming Data and Insight.
- Continuing to focus on the important inclusion and wellbeing agendas.
- Launch and embed Success Profiles into our recruitment activity.
- Progress our work on culture aligned to the Transformation programme
- Launch our refreshed recognition scheme.