MEETING	PUBLIC BOARD MEETING / 22 September 2021
Agenda Item / Paper Number	6 / CM/09/21/06
Agenda Title	Quarterly Change & People Update
Executive Sponsor and Job Title	Kirsty Shaw, Chief Operating Officer / Mark Sutton, Chief Digital Officer
Author and Job Title	Rohit Thakker, Reporting and Governance Manager
Presenters and Job Title	Amy Pritchard, Director of Transformation / Gill Nicholson, People Director

PURPOSE OF PAPER:

Actions required by the Board (delete as appropriate):
Note

IMPACT:
Information for Board to be aware of (delete as appropriate):
- Impact on CQC and stakeholders - the continuation of our new Ways of Working and Strategy implementation
- Timeline for delivery – ongoing until FY24/25

Summary

Key achievements over the last quarter include:
- Aligned the transformation priorities to support delivery of our strategy and new ways of working
- Extensive internal engagement through a series of connect & explore deep dive workshops to agree the first stage of our new ways of working, including the design of a new regulatory approach and supporting organisational structures. We have seen engagement from a third of the organisation with representatives from all directorates at all levels. Outputs of these discussions will now inform the next phase of this work
- Each Directorate has established a D&I co-ordinator which is a voluntary role with a view to provide visible leadership and promote good practice on D&I across CQC and supported by the D&I Manager.
- Pulse survey on wellbeing provides some insightful data to continue to help us shape our approach to all elements of the people plan.

Transformation update
We are adopting a phased approach to implementing our new ways of working, breaking them down into stages which are built upon year on year. Each stage will focus on the delivery of a prioritised set of capabilities (a capability is the power or ability to do something), which will build over time to deliver our new ways of working, and in turn, our ambitious strategy to be an insight driven organisation with regulatory consistency.
The transformation portfolio is organised around 3 core pillars that come together to deliver each transition stage over the next 3 years. The first of these stages will focus on developing the foundations of being an insight led organisation with strong data quality and will test, in shadow form, place-based working. We will also have piloted our regulatory leadership and professional lead roles so that our Chief Inspectors can influence and shape policy and practice across sectors.

Highlights for this period are as follows:
     Pillar 1: Regulatory Framework
This pillar is focused on the development of our regulatory model to guide how we develop our new regulatory services and shape what skills we need in the future.
We have completed work to align our change activity to support delivery of the first stage of our new ways of working implementation, with specific focus on the new Regulatory Model. This enables us to manage change in a controlled way and ensure it supports delivery of the new operating model and strategy. As part of this work, we set out a high-level definition of a single end to end (provider level) assessment framework. We are now working to demonstrate we can apply this single quality assessment framework across the full breadth of our regulatory services, starting with Registration through to publication of our ratings. The team are now focussed on designing the next phase of the Regulatory Model which will include setting out our approach to systems regulation, LA assurance and incorporating peoples’ experiences into how we assess quality.
     Pillar 2: Organisational Design and Development
This Pillar will deliver our organisational changes to ensure we have the skills and culture we need to deliver our new strategy.
We continue with our extensive engagement with colleagues across the organisation as we co-design our new ways of working. We have agreed the design of our new Hub and Local Networks structure so that we can better coordinate our regulatory activity and, in line with our communications plan, have commenced engagement with our people; utilising personas (stories of how things will change) to help colleagues look ahead and understand the journey.
     Pillar 3: Regulatory Services
This pillar will develop and deliver new services, processes, data and technology
Our Transforming Data and Insights work is on track to deliver the foundational changes that will enable us to become an insight-driven organisation. This includes establishing a new Intelligence Unit which will create the capacity and capability to transform how we optimise data and insight in our regulatory approach.

In our Regulatory Platform programme, we are creating systems and processes that revolutionise how we collect and use data, helping us to become a more efficient, flexible and insight-driven regulator
People Strategy update
Employee Experience
Talent
This quarter sees the completion of our Senior Leadership talent Review. Our internal Shaping our Future leaders programme will commence later this year, focusing on Grade D-B aspiring managers. We have also begun to process applications for our Level 3 and Level 5 Management apprenticeships. Positively, all Black, Asian and Minority Ethnic and Disabled applicants gained a place on their preferred programme.

In addition, we have secured 10 places on the NHS Leadership Academy, Manchester and Birmingham Universities pilot Level 7 Senior Leadership apprenticeship which combines the apprenticeship with the Elizabeth Garrett Anderson programme and a master’s degree.

Employee Insights
People Surveys
In September we are launching an exercise to procure a new contract for Our People surveys from April 2022 when our current contract expires. Planning is also underway for the main Our People Survey to take place in late October/early November 2021. Results from the July Our People Pulse Survey are contained within a separate paper for this Board meeting.

Diversity, Inclusion and wellbeing

Reverse Mentoring
The Reverse Mentoring programme has now been completed and we are currently evaluating the programme. Learning from this progamme will inform future programmes for both our Black and Minority Ethnic and disabled colleagues

Mental health and wellbeing Strategy
The most recent pulse survey results provide an update on people’s mental health and wellbeing, what is influencing is influencing how people feel and active management in place.  This information has been shared with the Executive Team, People Committee and CQC colleagues to inform next steps at individual, team and organisational level.

Line Management Capability

We are pleased to report that since July, 56 colleagues within Intelligence and Digital have completed a new learning module on Embracing Change and 87% of respondents reported that the module was useful to their role which indicates a positive start. This module forms part of a suite of learning modules called The Successful Manager which are being widely marketed to managers within CQC during September. Alongside this we are also launching a new 360 feedback tool for managers during September.

Recommendation

None

Discussion and implications

None

Conclusion and Next Steps

We ask the Board to note progress in delivering what is an ambitious transformation and people agenda. In the coming quarter we will focus on:
- Agreeing our implementation approach which involves creating a ‘model operations’ environment to test how our proposed changes will work in practice
- Create a consistent, transformation wide implementation approach to enable us to describe to our internal and external stakeholders the types and timings of changes that will affect how they operate or receive our services
- Continuing to focus on the important inclusion and wellbeing agendas
- Take action on our Senior Leadership talent Review and Executive Team talent board outcomes
- Progress our work on culture aligned to the Transformation programme
- Design of a Leadership strategy (due to ET in October) to ensure we are aligning our leadership capabilities with our future ambition
- Continue to engagement and seek feedback with regard to our Successful Managers modules, specifically the Embracing Change module
- All staff virtual conference begins on 30th November, with a view to using it as a strong platform for engagement, communication and inspiration of our people.

Appendices

None

Those who contributed to this paper

- Nina Snell – Head of Transformation Delivery
- Gill Nicholson – People Director