PUBLIC BOARD, 17 November 2021

TITLE: Quarterly Change & People Update

Executive Sponsor: Kirsty Shaw - Chief Operating Officer
Presenter: Amy Pritchard, Director of Transformation / Gill Nicholson, People Director
PURPOSE: FOR ASSURANCE

This paper is provided to enable the Board to fulfil their duties in relation to:
- Monitoring the progress and delivery of strategic change programmes
- Ensuring financial probity and the efficient and effective use of resources

PROPOSAL OR RECOMMENDATION

Information for Board to be aware of:
- Impact on CQC and stakeholders - the continuation of Target Operating Model and Strategy implementation
- Timeline for delivery – ongoing until FY24/25
Board are asked to note on the delivery performance.

BACKGROUND

This paper is an established component of CQC’s governance of its strategic transformation portfolio, it provides visibility of performance against delivery for the quarter ending October 2021.

KEY POINTS
Summary
Key achievements over the last quarter include:
- We have undertaken detailed work to define the objectives to support phase two roll out of our new ways of working. This has culminated in a high-level roadmap for implementing our new assessment framework, peoples experience, local authority assurance and systems level assessment.
- Phase one of our organisation design approach has been agreed, namely our top-level functional design for Regulatory Services.
- We continue to progress the development of our Leadership strategy and future investment.
Transformation Update
Performance Summary
Overall portfolio performance is currently Amber/Green, which is a direct result of improvements made in recent months in resourcing and the confirmation of deliverables and dependencies linked to implementing phase one of our new ways of working. These aspects have now been fully embedded within programme plans, resource profiles and financial forecasts; enabling critical path (key milestones) identification at the portfolio level.
We are adopting a phased approach to implementing our new ways of working, breaking them down into stages which are built upon year on year. The transformation portfolio is organised around 3 core pillars that come together to deliver each stage over the next 3 years, and in doing so will realise our strategic objectives at the same time.
We have now begun planning for the second phase of this work with high-level objectives being agreed to inform programme priorities. This will be quickly followed by planning for phase three before the end of this calendar year to ensure that our overall operating model implementation remains within agreed parameters.
Our engagement activity over the last quarter has been focussed on communicating the latest scope, plans and timelines associated with the transformation portfolio, specifically communicating design decisions around having a Regulatory Leadership function, centralised hub and four networks supported by multi-disciplinary teams.
Externally, we have engaged with all our partners and stakeholders on the elements which sit within our regulatory model programme, including our approach to Integrated Care Systems (ICS) and Local Authority Assurance.
Programme Performance
Portfolio Pillar 1: Regulatory Framework
This pillar is focused on the design of our regulatory model to guide how we develop our new regulatory services and shape what skills we need for the future.
Following the first release of the regulatory model work has been focussed on embedding the single assessment framework requirements in parallel programmes for delivery and implementation. Efforts have also been directed towards progressing key legislative change requirements including Liberty Protection Safeguards (LPS) and Closed Cultures (CC) as well as developing our thinking around people’s experience, systems level assessment and local authority assurance.
Portfolio Pillar 2: Organisational Design and Development
This Pillar will deliver our organisational changes to ensure we have the skills and culture we need to deliver our new strategy.
During the last quarter we have continued extensive engagement with colleagues across the organisation to co-design new ways of working, including work on culture, defining our aspirations in this space and how we will bring them to life.
Portfolio Pillar 3: Regulatory Services
This pillar will develop and deliver new services, processes, data and technology aligned to embedding our new policy and regulatory approach as defined under pillar 1.
Over the last quarter we finalised plans for the new data and insight function, reflecting how the unit will embed the insight capability and requirements of the new regulatory model by utilising new insight tools, systems and processes to derive deeper insight to drive operational decision making.
In our Regulatory Platform programme, we implemented Direct Monitoring Activity (DMA) enabling us to publish the results of our monthly provider monitoring activity. Focus is now on applying the single assessment framework to a new set of processes and supporting technology which cover how we will register providers in the future, continually assess them and publish our findings. We are also transforming the way that providers will be able to interact with us by developing a new digital portal.
Our Enabling Services programme is the third strand in this pillar and is focused on driving transformation in our Finance function through the provision of a new finance system, the onboarding of a delivery partner to support this activity is imminent.

People Strategy Update
Employee Experience
The people management policies continue to be refreshed; we continue to engage with our Equality Networks, Staff Forum and trade unions. Currently the Reasonable Adjustments policy and procedure is under consideration. This links closely with the objectives and focus of the Workforce Disability Equality Standard Group (WDES) and ensures we are aligned in our communications. Ultimately, we want to increase confidence in colleagues to share their disability status so they can get the right so we can tailor our internal processes to best support all those we employ.
Talent and Resourcing
This quarter sees the commencement of some of our development programmes. Our Grade A programme has started with great feedback from all who attended, 32 colleagues are now enrolled to start their Level 3 or Level 5 Management apprenticeship, 36 colleagues have secured their place on our Shaping Our Future Leaders programme and 10 colleagues have been offered a place on the NHS Leadership Academy Level 7 Senior Leadership apprenticeship.
We have secured the opportunity for four colleagues to attend the next Disability Rights UK programme starting early 2022 and we are looking to widen our apprenticeship offering with more programmes starting in 2022.
Employee Insights
People Surveys
The main Our People Survey will launch on 17 November and will be open to all colleagues for three weeks until 7 December. This is the main colleague engagement survey that now takes place once every two years, having last been undertaken in November 2019.
The content of the survey has been shared and discussed with key internal stakeholders, network chairs and Trade Unions. Some slight changes have been made from the 2019 survey to reflect the changing context of the organisation, but many questions are consistent with those from 2019, which will allow us to report on upward or downward trend. We aim to have high-level results available to share at the first Executive Team meeting in January, with a report to Board following.
Diversity, Inclusion and wellbeing
Diversity and Inclusion
The Organisational Development (OD) team continue to deliver on the commitments made within the D&I strategy 2020-23. Our newly appointed D&I directorate coordinators are being provided with their terms of reference and a support and learning framework is being designed. We are beginning to draft the Workforce Disability Equality Standard (WDES) and Workforce Race Equality Standard (WRES) reports and updated actions plans in preparation for presenting to the Executive Team and Board in Quarter 4.
Mental Health and Wellbeing Strategy
The MH and Wellbeing strategy aims to influence individual, line manager and organisational ways of working across CQC so that:
- We are all actively managing our health and wellbeing
- We have a culture of openness and discussion
- We feel supported in keeping healthy
Quarterly people data evidenced a small increase in people self-reporting on a mental health condition.
A well supported Mental Health campaign was held in October. This included a line manager best practice panel session, a new MH peer support network and colleagues sharing experiences in different forums including 19 written personal stories on mental illness.
Line Management Capability
The Successful Manager
After a very successful pilot in the Intelligence team we have now commenced roll-out of this programme to all line managers across the organization. Booking on the programme have been exceptional will all spaces for programs to 1st January 2022 fully booked within days; further sessions have been slotted in to accommodate the initial high demand.
Leadership and change
Future Leadership strategy 2021-24
Our future leadership strategy (2021-2024) was discussed by People Committee in October. This strategy, which is central to supporting our transformation, describes the drivers for our leadership for the future, core skill requirements for leaders, our approach to leadership events and meetings and proposals for planned Leadership development programmes.
Connect & Share All Colleague virtual conference
Following the success of last year’s conference, we are holding another inclusive virtual conference for all colleagues between 30 November and 2 December. This will provide an opportunity to share key strategy and transformational messages with colleagues and enable colleagues to take part in a broad range of learning and development sessions.
Recommendation
None
Discussion and implications
None
Conclusion and Next Steps
We ask the Board to note progress in delivering what is an ambitious transformation and people agenda. In the coming quarter we will focus on:
- To conclude phase 2 and phase 3 planning to enable robust implementation of new ways of working.
- The important inclusion and wellbeing agendas
- Monitor take up and continually advertise our leadership programmes to those groups targeted. Continue to action on our Senior Leadership talent Review and Executive Team talent board outcomes
- Continue to engagement and seek feedback regarding our Successful Managers modules, specifically the Embracing Change module
- All staff virtual conference begins on 30th November. This will provide a strong platform to engage, connect and inspire our colleagues.
Appendices
None
Those who contributed to this paper
- Nina Snell – Head of Transformation Delivery
- Gill Nicholson – People Director

 CONTRIBUTIONS

The following groups/people have been involved in forming this paper:

Groups/people	Involvement?	Feedback
HR	Yes	People update comes directly from HR colleagues.
Finance	Not applicable
DHSC	Not applicable
Executive Team	Not applicable
Board Committee	Not applicable
Executive Committee	Not applicable
Trade Unions	Not applicable
Staff Networks	Not applicable
Other – please specify	Not applicable